Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

LEARNER GUIDE

For

Project Management Masterclass

Course Code: C523

Conducted by

Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

Version 3.0

DOCUMENT VERSION CONTROL RECORD

| Version Number | Effective Date of Release | Summary of Included Changes | Author |
| --- | --- | --- | --- |
| 15.0 | 1 June 2026 | Six-topic learner guide aligned to the 2021 PMP exam content outline | Tertiary Infotech Academy Pte Ltd |
| 3.0 | 19 July 2026 | Rebuilt against the PMI PMP Examination Content Outline (July 2026): domain weighting People 33% / Process 41% / Business Environment 26%; sustainability and AI content added; expanded to 24 hands-on labs; every topic mapped to its ECO tasks and learning outcome | Tertiary Infotech Academy Pte Ltd |

TABLE OF CONTENTS

Right-click and choose “Update Field”, or press F9, to build the table of contents.

# How to Use This Guide

This Learner Guide accompanies the 4-day Project Management Masterclass. It follows the same six topics as the slide deck and the Lesson Plan, and the 24 hands-on labs referenced here are the same labs you complete in class.

Each topic chapter contains the teaching notes for that topic, the Examination Content Outline tasks it delivers, the labs that practise it, and a set of review questions. Work through the chapter after the session, then attempt the review questions without referring back.

The course is aligned to the PMI Examination Content Outline published for the July 2026 exam update. Where this guide differs from older PMP material, the 2026 outline governs.

## Learning Outcomes

| Ref | Learning Outcome |
| --- | --- |
| LO1 | Scope medium-scale project requirements to drive timely completions. |
| LO2 | Develop project plans based on realistic timelines and resource allocations. |
| LO3 | Implement methodologies effectively to address project exigencies and derive solutions from identified root causes. |
| LO4 | Analyze program risks and engage stakeholders through scheduled touchpoints to discuss potential issues. |
| LO5 | Coordinate project deliverables against set objectives, costs, and timelines, and implement corrective actions. |

## Examination Content Outline — July 2026

| Domain | Weighting | What it covers |
| --- | --- | --- |
| Domain I. People | 33% | How you lead, align and communicate with the humans on and around the project. |
| Domain II. Process | 41% | How you plan, deliver, measure and close the work itself. |
| Domain III. Business Environment | 26% | How the project connects to governance, compliance, risk and organisational change. |

Exam format: 180 questions (170 scored, 10 unscored pretest) in 240 minutes. Two 10-minute breaks — the first after the case-study section, the second midway through the independent questions. About 40% predictive; the remaining 60% split between adaptive/agile and hybrid.

## The Running Case Study

Every lab builds on the Contoso Training Portal Upgrade — a hybrid project to modernise a training provider's course registration and learner communications. It has a fixed launch date, a limited budget, a mandatory compliance review, and product increments delivered in sprints. Artifacts you produce in early labs become inputs to later ones, so by the capstone you hold a complete project management plan.

# Topic 1. Business Environment

Where projects come from, why they are funded, and the governance, compliance and change context they must survive in.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| Business Environment T1 | Define and establish project governance | Establish structure, rules, procedures, reporting, ethics and policies using OPAs; Define success metrics; Outline governance escalation paths and thresholds |
| Business Environment T2 | Plan and manage project compliance | Confirm compliance requirements (security, health and safety, sustainability, regulatory); Classify compliance categories; Determine potential threats to compliance; Use methods to support compliance; Analyze the consequences of noncompliance; Determine the approach and actions to address compliance needs; Measure the extent to which the project is in compliance |
| Business Environment T7 | Support organizational change | Assess organizational culture; Evaluate the impact of organizational change on the project and determine actions |
| Business Environment T8 | Evaluate external business environment changes | Survey changes to the external business environment (regulations, technology, geopolitical, market); Assess and prioritize impact on project scope/backlog; Continually review the external business environment for impacts |
| Process T3 | Help ensure value-based delivery | Identify value components with key stakeholders; Prioritize work based on value and stakeholder feedback; Assess opportunities to deliver value incrementally; Examine the business value throughout the project; Verify a measurement system is in place to track benefits; Evaluate delivery options to demonstrate value |

## What This Topic Covers

Foundation and project fundamentals

Strategic alignment and business value

Development approaches: predictive, agile, hybrid

Organisational culture and change management

Project governance and escalation

Compliance, sustainability and AI in projects

## What a project is, and why that definition matters

A project is a temporary endeavour undertaken to create a unique product, service or result. Two words carry the weight. *Temporary* means it has a definite beginning and end — it is not the ongoing operation that follows. *Unique* means the deliverable differs in some material way from what came before; if you are producing the same thing repeatedly, that is operations, not a project. The exam tests this boundary constantly: maintaining a running payroll system is operations, replacing it is a project.

Temporary — a defined start and finish, not perpetual

Unique — the output differs materially from previous outputs

Progressive elaboration — detail increases as the project advances

Delivers business value, which is the reason it was funded at all

## The triple constraint and why quality sits in the middle

Scope, time and cost form the classic triangle, with quality dependent on all three. Change any one and at least one other must move, or quality absorbs the damage. In practice this is the single most useful conversation tool a project manager has: when a stakeholder asks for more scope at a fixed date and budget, the triangle is what you draw. Modern practice extends this to six constraints — scope, schedule, cost, quality, resources and risk.

Increase scope with fixed time and cost, and quality falls

Compress schedule, and cost rises (crashing) or risk rises (fast tracking)

Cut budget, and either scope or quality must give

Never silently absorb a change — make the trade-off explicit and documented

## Development approaches across the value delivery spectrum

Predictive (waterfall) approaches plan scope thoroughly up front and control change formally; they suit stable requirements and high-compliance environments. Adaptive (agile) approaches accept that requirements will emerge, and deliver in short increments so feedback arrives early. Hybrid blends them — for example, a fixed regulatory scope delivered predictively alongside a user-facing component delivered in sprints. The July 2026 exam splits roughly 40% predictive, 60% adaptive and hybrid, so you cannot pass on waterfall knowledge alone.

Predictive — scope fixed early, change via formal change control

Iterative — repeated cycles refine the same deliverable

Incremental — successive slices each add usable functionality

Agile — both iterative and incremental, with continuous feedback

Hybrid — deliberately combines approaches per component

## Enterprise environmental factors and organisational process assets

EEFs are conditions you do not control but must work within: market conditions, regulation, organisational culture, the infrastructure you are handed. OPAs are the assets your organisation gives you to reuse: templates, historical data, lessons learned, procurement rules, defined processes. The exam distinction is simple but heavily tested — EEFs constrain you, OPAs help you.

EEF internal — culture, structure, existing systems, staff capability

EEF external — regulation, market conditions, standards, geopolitics

OPA processes — policies, procedures, templates, defined workflows

OPA knowledge — historical data, lessons learned, estimating databases

## Governance, escalation and phase gates

Governance is the framework of authority: who decides what, within which thresholds, and what happens when a threshold is breached. A governance board or steering committee provides oversight; the project manager operates within delegated tolerances. When a problem exceeds your tolerance — a cost overrun beyond the agreed percentage, a risk above the agreed severity — you escalate. Phase gates are the scheduled decision points where the project is formally reviewed and authorised to continue, be redirected, or be stopped.

Define escalation thresholds BEFORE you need them

Escalating within an agreed threshold is competence, not failure

Phase gates permit a go / no-go decision, including cancellation

Governance defines success metrics, not just spending limits

## Compliance, sustainability and AI — the 2026 additions

The July 2026 outline raised Business Environment from 8% to 26% of the exam and named sustainability explicitly across compliance, cost of quality and risk response. Compliance is no longer only legal and regulatory: environmental impact, workplace health and safety, ethical practice and data security all sit inside the compliance envelope. Artificial intelligence enters as both a tool (estimation, risk detection, reporting) and a governance concern (bias, explainability, data protection).

Classify compliance categories, then assess threats to each

Analyse the consequences of non-compliance, not just the requirement

Measure the extent of compliance — it is a metric, not a binary

AI used on a project needs its own governance and audit trail

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | PMP Exam Orientation and Study Plan | All domains | LO1 | 20 min | 25 min | Personal study plan, Domain self-assessment |
| 02 | PESTLE and TECOP External Environment Scan | BE T8 | LO1 | 20 min | 25 min | PESTLE scan, TECOP risk themes |
| 03 | EEF/OPA Inventory with Governance and Escalation Thresholds | BE T1 | LO1 | 20 min | 25 min | EEF/OPA inventory, Escalation threshold table |
| 04 | Compliance, Sustainability and AI Governance Register | BE T2 | LO4 | 20 min | 25 min | Compliance register, AI governance controls |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

Distinguish a project from operations, and give an example of each from your own workplace.

Your sponsor asks for additional scope while holding the date and budget fixed. Explain the trade-off using the triple constraint.

Classify each of the following as an EEF or an OPA: a lessons-learned database, a new data-protection regulation, the organisation's procurement policy, the existing IT infrastructure.

What is the difference between a governance escalation threshold and a phase gate?

Name three compliance categories beyond legal and regulatory that the 2026 outline expects you to consider.

How does the July 2026 exam update change the weighting of Business Environment, and why does that matter for your study plan?

# Topic 2. Start the Project

Turning an idea into an authorised project: the business case, the charter, the stakeholders and the team.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| People T1 | Develop a common vision | Help ensure a shared vision with key stakeholders; Promote the shared vision; Keep the vision current; Break down situations to identify the root cause of a misunderstanding of the vision |
| People T4 | Engage stakeholders | Identify stakeholders; Analyze stakeholders; Analyze and tailor communication to stakeholder needs; Execute the stakeholder engagement plan; Optimize alignment among stakeholder needs, expectations, and project objectives; Build trust and influence stakeholders to accomplish project objectives |
| People T5 | Align stakeholder expectations | Categorize stakeholders; Identify stakeholder expectations; Facilitate discussions to align expectations; Organize and act on mentoring opportunities |
| People T6 | Manage stakeholder expectations | Identify internal and external customer expectations; Align and maintain outcomes to internal and external customer expectations; Monitor internal and external customer satisfaction/expectations and respond as needed |
| Process T1 | Develop an integrated project management plan and plan delivery | Assess project needs, complexity, and magnitude; Recommend a development approach (predictive, adaptive/agile, or hybrid); Determine critical information requirements (e.g., sustainability); Recommend a project execution strategy; Create an integrated project management plan; Estimate work effort and resource requirements; Assess consolidated plans for dependencies, gaps, and continued business value; Maintain the integrated project management plan; Collect and analyze data to make informed project decisions |

## What This Topic Covers

Project integration and the charter

Business case, cost-benefit and benefits management

Identify, analyse and prioritise stakeholders

Align and manage stakeholder expectations

Form the team and build shared understanding

Determine the project approach

## The business case and why projects get funded

Projects exist to deliver benefit. The business case is the documented economic feasibility study that justifies the investment: the problem or opportunity, the options considered, the recommended option, and the financial and non-financial returns. It is prepared before the charter and is the reference point you return to whenever someone proposes a change that erodes the value the project was funded to deliver.

Cost-benefit analysis compares the cost of the work to the benefit gained

Payback period — how long until the investment is recovered; shorter is better

Net present value (NPV) — future cash flows discounted to today; positive is good

Internal rate of return (IRR) and benefit-cost ratio (BCR) — higher is better

Opportunity cost — the value of the option you did NOT choose

## The project charter

The charter authorises the project and, critically, authorises the project manager to apply organisational resources to it. It is issued by a sponsor external to the project with the authority to fund it. Without a charter you have no mandate. It stays deliberately high level — names, objectives, high-level requirements, summary milestones and budget, key risks, and the approval criteria.

Authorises the project's existence and the PM's authority

Signed by the sponsor, not written by the sponsor alone

Contains measurable objectives and success criteria

Records assumptions, constraints and high-level risk

Is not re-baselined — it is the founding document

## Identifying and analysing stakeholders

A stakeholder is anyone who affects, is affected by, or believes they are affected by the project. That last clause matters: perceived impact generates real behaviour. Identification is continuous, not a one-off task at initiation. The stakeholder register records who they are, their interest, influence, expectations and your engagement strategy.

Power/interest grid — the most commonly examined classification

Salience model — power, legitimacy and urgency combined

Directions of influence — upward, downward, sideward, outward

Engagement levels — unaware, resistant, neutral, supportive, leading

The SEAM records Current (C) versus Desired (D) engagement per stakeholder

## Aligning and managing expectations

The 2026 outline separates engaging stakeholders (People T4) from aligning their expectations (T5) and managing those expectations over time (T6). Alignment is the facilitation work of getting parties with different definitions of success to agree one definition. Management is the ongoing monitoring of satisfaction and responding when it drifts.

Identify expectations explicitly — unstated expectations become disputes

Facilitate discussion where expectations conflict; do not arbitrate silently

Monitor internal and external customer satisfaction continuously

Build trust deliberately; influence follows trust, not authority

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 05 | Business Case and Cost-Benefit Analysis | Process T3 | LO1 | 25 min | 25 min | Business case, NPV/ROI/payback model |
| 06 | Project Charter | Process T1 | LO1 | 20 min | 25 min | Approved project charter |
| 07 | Stakeholder Register, Power/Interest Grid and Salience Model | People T4, T5 | LO4 | 25 min | 25 min | Stakeholder register, Power/interest grid, Salience classification |
| 08 | Team Charter, Ground Rules and Shared Vision | People T1, T2 | LO3 | 30 min | 15 min | Team charter, Ground rules, Vision statement |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

What does the project charter authorise that no other document does?

A project has an initial investment of $200,000 and returns $60,000 per year. Calculate the payback period and state one limitation of using it alone.

Compare the power/interest grid with the salience model. When would you prefer each?

A stakeholder is currently resistant but needs to be supportive. How would you record and act on that in a SEAM?

Explain the difference between engaging stakeholders and aligning their expectations, per ECO People T4 and T5.

Why is 'anyone who believes they are affected' included in the definition of a stakeholder?

# Topic 3. Plan the Project

Building the integrated plan — scope, schedule, cost, quality, resources, communications, risk and procurement.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| Process T1 | Develop an integrated project management plan and plan delivery | Assess project needs, complexity, and magnitude; Recommend a development approach (predictive, adaptive/agile, or hybrid); Determine critical information requirements (e.g., sustainability); Recommend a project execution strategy; Create an integrated project management plan; Estimate work effort and resource requirements; Assess consolidated plans for dependencies, gaps, and continued business value; Maintain the integrated project management plan; Collect and analyze data to make informed project decisions |
| Process T2 | Develop and manage project scope | Define scope; Obtain stakeholder agreement on project scope; Break down scope |
| Process T4 | Plan and manage resources | Define and plan resources based on requirements; Manage and optimize resource needs and availability |
| Process T5 | Plan and manage procurement | Plan procurement; Execute a procurement management plan; Select preferred contract types; Evaluate vendor performance; Verify objectives of the procurement agreement are met; Participate in agreement negotiations; Determine a negotiation strategy; Manage suppliers and contracts; Plan and manage the procurement strategy; Develop a delivery solution |
| Process T6 | Plan and manage finance | Analyze project financial needs; Quantify risk and contingency financial allocations; Plan spend tracking throughout the project life cycle; Plan financial reporting; Anticipate future finance challenges; Monitor financial variations and work with the governance process; Manage financial reserves |
| Process T7 | Plan and optimize quality of products/deliverables | Gather quality requirements for project deliverables; Plan quality processes and tools; Execute a quality management plan; Help ensure regulatory compliance; Manage cost of quality (CoQ) and sustainability; Conduct ongoing quality reviews; Implement continuous improvement |
| Process T8 | Plan and manage schedule | Prepare a schedule based on the selected development approach; Coordinate with other projects and operations; Estimate project tasks (milestones, dependencies, story points); Utilize benchmarks and historical data; Create a project schedule; Baseline a project schedule; Execute a schedule management plan; Analyze schedule variation |
| Business Environment T5 | Plan and manage risk | Identify risks; Analyze risks; Monitor and control risks; Develop a risk management plan; Maintain a risk register (e.g., poor IT security); Execute a risk management plan (risk response for security and sustainability risks); Communicate the status of a risk impact on the project |
| People T8 | Plan and manage communication | Define a communication strategy; Promote transparency and collaboration; Establish a feedback loop; Understand reporting requirements; Create reports aligned with sponsors and stakeholder expectations; Support reporting and governance processes |

## What This Topic Covers

The integrated project management plan

Scope: requirements, WBS and baselines

Schedule: activities, dependencies, critical path

Cost: estimating, budget and reserves

Quality: planning and problem-solving tools

Resources, communications and procurement

Risk: identification, analysis and response

## The integrated project management plan

The project management plan is not one document but the integration of all subsidiary plans — scope, schedule, cost, quality, resource, communications, risk, procurement and stakeholder engagement — plus the three baselines (scope, schedule, cost). Integration is the point: the plans must be internally consistent, and a change to one usually forces a change to others.

Subsidiary management plans define HOW each knowledge area will be run

Baselines are the approved versions against which performance is measured

Changes to a baseline require an approved change request — always

Rolling wave planning elaborates near-term work in detail, later work coarsely

## Scope: from requirements to work packages

Scope work moves from elicitation (what do stakeholders need?) through definition (what will we deliver?) to decomposition (what work produces it?). The Requirements Traceability Matrix links each requirement forward to the deliverable, test and acceptance that satisfies it. The WBS decomposes the deliverables — not the activities — down to work packages, and obeys the 100% rule: the WBS contains all the work and only the work.

Scope creep — uncontrolled additions without change control

Gold plating — the team adding unrequested extras; never acceptable

The WBS decomposes DELIVERABLES; the activity list decomposes the work

The WBS dictionary carries the detail for each work package

Scope baseline = scope statement + WBS + WBS dictionary

## Schedule: dependencies, estimating and the critical path

Activities are sequenced by dependency type (mandatory, discretionary, external, internal) and relationship (finish-to-start being the most common). Durations are estimated by analogous, parametric, three-point or bottom-up methods. The critical path is the longest path through the network and therefore the shortest possible duration; activities on it have zero float. Compressing it means crashing (adding cost) or fast tracking (adding risk).

Three-point (PERT): (O + 4M + P) / 6, with σ = (P − O) / 6

Total float — delay available before the project end date slips

Free float — delay available before the NEXT activity is affected

Critical path activities have zero total float by definition

Crashing adds cost; fast tracking adds risk and potential rework

## Cost: estimating, budgeting and reserves

Cost estimates roll up from work packages into the cost baseline, to which contingency reserve is added for identified risks. Management reserve sits above the cost baseline for unknown-unknowns and requires management approval to access. The distinction is examined frequently: contingency is inside the baseline and under your control, management reserve is outside it and is not.

Cost baseline = work package estimates + contingency reserve

Budget at completion (BAC) = cost baseline + management reserve

Contingency reserve — for identified (known) risks; PM controls it

Management reserve — for unidentified risks; management controls it

## Quality: planning it in, not inspecting it in

Quality is conformance to requirements and fitness for use. It is cheaper to prevent than to inspect, and far cheaper to fix early than late — the cost of change curve rises steeply as the project progresses. The cost of quality splits into conformance costs (prevention, appraisal) and non-conformance costs (internal failure, external failure). External failure — the customer finds the defect — is the most expensive outcome of all.

Prevention — training, process design, prototyping; the cheapest lever

Appraisal — inspection, testing, audits; finds defects before the customer

Internal failure — rework caught in-house

External failure — the customer finds it; cost includes reputation

Root cause tools: 5 Whys, fishbone, Pareto, control charts

## Risk: identification through response

Risk is an uncertain event that, if it occurs, has a positive or negative effect on objectives. Risks are future and uncertain; issues are present and certain. Qualitative analysis prioritises risks by probability and impact; quantitative analysis models their aggregate effect in money or time. Response strategies mirror each other for threats and opportunities.

Threats: escalate, avoid, transfer, mitigate, accept

Opportunities: escalate, exploit, share, enhance, accept

EMV = probability × impact, summed across outcomes

Secondary risk arises FROM your response; residual risk remains after it

A risk that has occurred is no longer a risk — it is an issue

## Procurement and contract types

Contract type determines who carries cost risk. Fixed-price contracts place risk on the seller and suit well-defined scope. Cost-reimbursable contracts place risk on the buyer and suit uncertain scope. Time and materials sits between the two and suits small or urgent engagements where scope is not yet clear.

Firm fixed price (FFP) — seller carries the cost risk entirely

Fixed price incentive fee (FPIF) — shared risk with a performance incentive

Cost plus fixed fee (CPFF) — buyer carries cost risk; fee is fixed

Cost plus incentive/award fee (CPIF/CPAF) — buyer risk with incentives

Time and materials (T&M) — hybrid; cap it or it becomes open-ended

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 09 | Requirements Elicitation and Traceability Matrix | Process T2 | LO1 | 30 min | 20 min | Requirements list, RTM |
| 10 | MoSCoW and Kano Prioritisation with Product Backlog | Process T3 | LO1 | 30 min | 20 min | Prioritised backlog, Story point estimates |
| 11 | Work Breakdown Structure and WBS Dictionary | Process T2 | LO1 | 30 min | 20 min | WBS, WBS dictionary, Scope baseline |
| 12 | Network Diagram, PERT Estimating and Critical Path | Process T8 | LO2 | 35 min | 25 min | Network diagram, Critical path, Float table |
| 13 | Cost Estimating, Budget and Reserve Analysis | Process T6 | LO2 | 25 min | 25 min | Cost estimates, Cost baseline, Reserve plan |
| 14 | Risk Register, Probability/Impact Matrix and EMV Decision Tree | BE T5 | LO4 | 30 min | 30 min | Risk register, P/I matrix, EMV decision tree |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

State the 100% rule and explain what it prohibits.

Given O=4, M=6, P=14 days, calculate the PERT estimate and the standard deviation.

Distinguish total float from free float, and state the float of an activity on the critical path.

A risk has a 30% probability and a $80,000 impact. Calculate the EMV and explain how you would use it.

Contrast contingency reserve with management reserve, including who controls each.

Which contract type would you choose for a well-defined deliverable with a fixed specification, and who carries the cost risk?

Distinguish scope creep from gold plating, and state why gold plating is never acceptable.

List the five threat response strategies and their opportunity mirrors.

# Topic 4. Lead the Project Team

The People domain in practice — leadership style, motivation, conflict, coaching and communication.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| People T1 | Develop a common vision | Help ensure a shared vision with key stakeholders; Promote the shared vision; Keep the vision current; Break down situations to identify the root cause of a misunderstanding of the vision |
| People T2 | Manage conflicts | Identify conflict sources; Analyze the context for the conflict; Implement an agreed-on resolution strategy; Communicate conflict management principles with the team and external stakeholders; Establish an environment that fosters adherence to common ground rules; Manage and rectify ground rule violations |
| People T3 | Lead the project team | Establish expectations at the team level; Empower the team; Solve problems; Represent the voice of the team; Support the team's varied experiences, skills, and perspectives; Determine an appropriate leadership style; Establish clear roles and responsibilities within the team |
| People T7 | Help ensure knowledge transfer | Identify knowledge critical to the project; Gather knowledge; Foster an environment for knowledge transfer |
| People T8 | Plan and manage communication | Define a communication strategy; Promote transparency and collaboration; Establish a feedback loop; Understand reporting requirements; Create reports aligned with sponsors and stakeholder expectations; Support reporting and governance processes |
| Process T1 | Develop an integrated project management plan and plan delivery | Assess project needs, complexity, and magnitude; Recommend a development approach (predictive, adaptive/agile, or hybrid); Determine critical information requirements (e.g., sustainability); Recommend a project execution strategy; Create an integrated project management plan; Estimate work effort and resource requirements; Assess consolidated plans for dependencies, gaps, and continued business value; Maintain the integrated project management plan; Collect and analyze data to make informed project decisions |

## What This Topic Covers

Direct and manage project work

Craft your leadership skills

Build a collaborative team environment

Empower the team and support performance

Training, coaching and mentoring

Manage conflict and negotiate

## Leadership style and the servant leader

There is no single correct leadership style; the ECO asks you to *determine an appropriate* style for the situation, team maturity and organisational context. Servant leadership — the dominant model in adaptive environments — inverts the usual hierarchy: the leader's job is to remove impediments, grow people and make it safe to raise problems, so the team can do the work.

Servant leadership — serve the team so the team can deliver

Transformational — inspire through vision and individual attention

Transactional — exchange reward for defined performance

Laissez-faire — hands off; only works with a mature, self-organising team

Situational — deliberately vary the style by person and circumstance

## Team development and motivation

Tuckman's model — forming, storming, norming, performing, adjourning — describes how teams mature, and each stage calls for different leadership. Storming is normal and necessary, not a failure. Motivation theory tells you what to reach for: Herzberg separates hygiene factors (whose absence demotivates) from motivators (whose presence motivates), which is why a pay rise fixes dissatisfaction but does not create engagement.

Forming — provide direction and clarify purpose

Storming — facilitate conflict; do not suppress it

Norming — reinforce the working agreements the team has built

Performing — delegate and remove blockers; stay out of the way

Adjourning — recognise contribution and capture lessons learned

## Conflict management — the most examined People topic

Conflict is inevitable and, handled well, productive. The five modes trade off assertiveness against cooperativeness. Collaborating (problem solving) produces a genuine win-win and is the preferred answer in most exam situations, because it addresses the underlying need rather than splitting the difference. Forcing and avoiding are appropriate only in narrow circumstances — emergencies, or trivia not worth the cost of resolution.

Collaborate / problem solve — win-win; the usual best answer

Compromise / reconcile — lose-lose; both give something up

Smooth / accommodate — lose-win; preserves the relationship

Force / direct — win-lose; fast, but damages trust

Withdraw / avoid — defers; appropriate only for trivia or cooling off

## Communication

Communication consumes most of a project manager's time. The channels formula, N(N−1)/2, shows why: adding people to a team increases the communication burden quadratically. A communications management plan defines who needs what information, in what format, how often, and through which method — push, pull or interactive.

Channels = N(N − 1) / 2 — ten people means forty-five channels

Push — sent to recipients (email, reports); no confirmation of understanding

Pull — recipients retrieve it (portals, dashboards); suits large audiences

Interactive — real-time exchange; the only mode that confirms understanding

Tailor the message to the stakeholder — this is an explicit ECO enabler

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 15 | RACI Responsibility Assignment Matrix | People T3, Process T4 | LO2 | 20 min | 25 min | RACI matrix, Resource plan |
| 16 | Tuckman Diagnosis and Motivation Theory Application | People T3 | LO3 | 20 min | 25 min | Team stage diagnosis, Motivation action plan |
| 17 | Conflict Resolution Role-Play across the Five Modes | People T2 | LO3 | 20 min | 30 min | Conflict analysis, Resolution strategy |
| 18 | Communication Plan, Channels Formula and Status Report | People T8 | LO4 | 20 min | 30 min | Communications management plan, Status report |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

Describe the leadership action appropriate at each stage of Tuckman's model.

Explain why a pay rise may remove dissatisfaction without creating motivation, using Herzberg's theory.

A designer and a developer disagree on a screen layout. Which conflict mode would you use first, and why?

Calculate the number of communication channels for a team of 12, and state what the result implies for your communications plan.

Distinguish push, pull and interactive communication, and state which confirms understanding.

What does 'represent the voice of the team' require of a project manager in practice?

# Topic 5. Monitor and Control the Project

Measuring truth against plan: earned value, quality control, change control, issues and impediments.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| Process T9 | Evaluate project status | Develop project metrics, analysis, and reconciliation; Identify and tailor needed artifacts; Help ensure artifacts are created, reviewed, updated, and documented; Help ensure accessibility of artifacts; Assess current progress; Measure, analyze, and update project metrics; Communicate project status; Continually assess the effectiveness of artifact management |
| Business Environment T3 | Manage and control changes | Execute the change control process; Communicate the status of proposed changes; Implement approved changes to the project; Update project documentation to reflect changes |
| Business Environment T4 | Remove impediments and manage issues | Evaluate the impact of impediments; Prioritize and highlight impediments; Determine and apply an intervention strategy to remove/minimize impediments; Reassess continually to ensure blockers are being addressed; Recognize when a risk becomes an issue; Collaborate with relevant stakeholders on an approach to resolve issues |
| Business Environment T5 | Plan and manage risk | Identify risks; Analyze risks; Monitor and control risks; Develop a risk management plan; Maintain a risk register (e.g., poor IT security); Execute a risk management plan (risk response for security and sustainability risks); Communicate the status of a risk impact on the project |
| Business Environment T6 | Continuous improvement | Utilize lessons learned; Help ensure continuous improvement processes are updated; Update organizational process assets (OPAs) |
| Process T7 | Plan and optimize quality of products/deliverables | Gather quality requirements for project deliverables; Plan quality processes and tools; Execute a quality management plan; Help ensure regulatory compliance; Manage cost of quality (CoQ) and sustainability; Conduct ongoing quality reviews; Implement continuous improvement |

## What This Topic Covers

Monitor and control project work

Evaluate project progress and earned value

Control quality with statistical tools

Manage changes and integrated change control

Manage issues, impediments and risk

Implement ongoing improvements

## Earned value management

EVM integrates scope, schedule and cost into a single set of measures, and it is the most calculation-heavy topic on the exam. Three inputs drive everything: planned value (what you said you would have done by now), earned value (what you have actually completed, valued at budget) and actual cost (what you spent doing it). Everything else derives from those three.

CV = EV − AC   ·   SV = EV − PV   (positive is good in both cases)

CPI = EV / AC   ·   SPI = EV / PV   (above 1.0 is good in both cases)

EAC = BAC / CPI when current variances are expected to continue

ETC = EAC − AC   ·   VAC = BAC − EAC

TCPI = (BAC − EV) / (BAC − AC) — the performance needed to finish on budget

## Integrated change control

Every change request follows the same path regardless of who raised it: record it, assess its impact across scope, schedule, cost, quality and risk, take it to the change control board for a decision, then either implement and update the baselines and documents, or record the rejection. The exam's most common trap is the option that implements a change without assessing impact or obtaining approval — it is always wrong.

Never implement an unapproved change, however senior the requester

Assess impact across ALL constraints before recommending a decision

Corrective action realigns performance with the plan

Preventive action reduces the probability of future variance

Update the baselines and affected documents after approval

## Controlling quality with statistical tools

Control charts distinguish variation that is inherent in the process (common cause) from variation that signals something has changed (assignable cause). A point outside the control limits is out of control. So is the rule of seven: seven consecutive points on one side of the mean indicates a non-random pattern even when every point sits inside the limits.

Control limits (UCL/LCL) are calculated from the process, usually ±3σ

Specification limits come from the customer and are a different thing

Rule of seven — seven consecutive points on one side signals assignable cause

Pareto — the 80/20 rule; fix the vital few categories first

In control does not mean acceptable; it means predictable

## Issues, impediments and risk that has arrived

The 2026 outline gives impediment removal its own task. The distinction matters: a risk is uncertain and future; when it occurs it becomes an issue and moves from the risk register to the issue log. Impediments and blockers are anything stopping the team from progressing, and clearing them is explicitly the project manager's job.

Recognise the moment a risk becomes an issue and re-classify it

Evaluate impact, then prioritise — not every impediment is urgent

Apply an intervention strategy, then reassess that it actually worked

Escalate beyond your threshold rather than absorbing the impact silently

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 19 | Kanban Board with WIP Limits and Lead/Cycle Time | Process T9 | LO5 | 20 min | 25 min | Kanban board, Cycle time measurements |
| 20 | Earned Value Management and Schedule Compression | Process T9 | LO5 | 25 min | 35 min | EVM calculation sheet, Forecast (EAC/ETC), Compression decision |
| 21 | Root Cause Analysis with 5 Whys, Fishbone and Pareto | BE T4 | LO3 | 25 min | 35 min | 5 Whys chain, Fishbone diagram, Pareto chart |
| 22 | SPC Control Chart and Statistical Process Analysis | Process T7 | LO5 | 30 min | 30 min | Control chart, Stability verdict, Capability summary |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

A project has BAC $500,000. At week 10: PV $200,000, EV $180,000, AC $210,000. Calculate CV, SV, CPI, SPI and EAC, and state the project's health in one sentence.

A senior stakeholder instructs you to implement a change immediately. State your correct sequence of actions.

Distinguish common cause from assignable cause variation, and explain the rule of seven.

When does a risk become an issue, and what changes in your documentation at that moment?

Compare crashing with fast tracking, including the cost and risk consequences of each.

Explain how a Pareto chart directs your quality improvement effort.

# Topic 6. Close the Project

Landing the project: acceptance, transition, benefits realisation and the knowledge that outlives the team.

## Examination Content Outline Coverage

| Task | Task statement | Enablers |
| --- | --- | --- |
| Process T10 | Manage project closure | Obtain project stakeholder approval of project completion; Determine criteria to successfully close the project or phase; Validate readiness for transition (e.g., to operations or next phase); Conclude closure activities (lessons learned, retrospectives, procurement, financials, resources) |
| Business Environment T6 | Continuous improvement | Utilize lessons learned; Help ensure continuous improvement processes are updated; Update organizational process assets (OPAs) |
| People T7 | Help ensure knowledge transfer | Identify knowledge critical to the project; Gather knowledge; Foster an environment for knowledge transfer |

## What This Topic Covers

Project and phase closure

Benefits realisation and value confirmation

Knowledge transfer and lessons learned

PMP exam strategy and readiness

## Closing the project or phase

Closure is a formal process, not simply stopping work. Deliverables are accepted against the acceptance criteria agreed at the start; the product is transitioned to the receiving organisation with the knowledge needed to run it; procurements are closed and contracts archived; resources are released; and lessons learned are transferred into the organisational repository so the next project inherits them. Projects terminated early are closed through exactly the same process.

Obtain formal stakeholder approval of completion — not informal agreement

Validate readiness for transition before handing over

Archive contracts, financial records and project documentation

Release resources deliberately, with recognition

Update OPAs so the organisation learns; this is the durable output

## Benefits realisation

The project ends before the benefits arrive. The benefits management plan names the benefits owner, the metrics and the measurement timeframe, so that value is confirmed after handover rather than assumed at closure. The 2026 outline's emphasis on value-based delivery makes this explicit: verify a measurement system is in place to track benefits.

Benefits are usually realised after the project closes

A named benefits owner carries accountability past project end

Metrics and baselines must exist before you can claim value

Examine business value throughout — not only at the gate reviews

## Preparing for the examination

The exam is 180 questions in 240 minutes: about eighty seconds each. Ten questions are unscored pretest items, indistinguishable from the rest. Two ten-minute breaks are offered, the first after the case-study section — and once you start a break you cannot return to the previous section, so review before you break, not after.

180 questions (170 scored, 10 pretest) in 240 minutes

People 33% · Process 41% · Business Environment 26%

About 40% predictive, 60% adaptive and hybrid

Six question types, including the new graphic-based items

Read for what the question ASKS — 'first', 'best', 'next' change the answer

## Hands-on Labs for This Topic

| Lab | Title | ECO | LO | In class | Self-study | Produces |
| --- | --- | --- | --- | --- | --- | --- |
| 23 | Project Closure, Benefits Realisation and Lessons Learned | Process T10, BE T6 | LO5 | 60 min | 0 min | Closure checklist, Final report, Lessons learned register |
| 24 | Capstone: Consolidated Project Plan and Mock Exam | All domains | LO1-LO5 | 105 min | 15 min | Consolidated project management plan, Mock exam score analysis by domain |

Full step-by-step instructions for each lab are in the labs/ folder of your course materials. You complete the core steps in class; the extension steps are self-study that finishes the artifact.

## Review Questions

List the activities required to formally close a project or phase.

Why are benefits usually realised after the project has closed, and who is accountable for them?

What is the difference between the lessons learned register and the lessons learned repository?

A project is terminated early. Which closure activities still apply?

State the exam's question count, scored count, duration and break structure.

Explain the significance of the words 'first', 'best' and 'next' in a situational exam question.

# Complete Lab Index

24 labs totalling 1285 minutes (21.4 hours) of hands-on practice: 705 minutes timetabled in class across the four days, and 580 minutes of extension work you complete as self-study.

| Lab | Title | Day | Topic | ECO Task | LO | In class | Self-study |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 01 | PMP Exam Orientation and Study Plan | Day 1 | T1 | All domains | LO1 | 20 | 25 |
| 02 | PESTLE and TECOP External Environment Scan | Day 1 | T1 | BE T8 | LO1 | 20 | 25 |
| 03 | EEF/OPA Inventory with Governance and Escalation Thresholds | Day 1 | T1 | BE T1 | LO1 | 20 | 25 |
| 04 | Compliance, Sustainability and AI Governance Register | Day 1 | T1 | BE T2 | LO4 | 20 | 25 |
| 05 | Business Case and Cost-Benefit Analysis | Day 1 | T2 | Process T3 | LO1 | 25 | 25 |
| 06 | Project Charter | Day 1 | T2 | Process T1 | LO1 | 20 | 25 |
| 07 | Stakeholder Register, Power/Interest Grid and Salience Model | Day 1 | T2 | People T4, T5 | LO4 | 25 | 25 |
| 08 | Team Charter, Ground Rules and Shared Vision | Day 1 | T2 | People T1, T2 | LO3 | 30 | 15 |
| 09 | Requirements Elicitation and Traceability Matrix | Day 2 | T3 | Process T2 | LO1 | 30 | 20 |
| 10 | MoSCoW and Kano Prioritisation with Product Backlog | Day 2 | T3 | Process T3 | LO1 | 30 | 20 |
| 11 | Work Breakdown Structure and WBS Dictionary | Day 2 | T3 | Process T2 | LO1 | 30 | 20 |
| 12 | Network Diagram, PERT Estimating and Critical Path | Day 2 | T3 | Process T8 | LO2 | 35 | 25 |
| 13 | Cost Estimating, Budget and Reserve Analysis | Day 2 | T3 | Process T6 | LO2 | 25 | 25 |
| 14 | Risk Register, Probability/Impact Matrix and EMV Decision Tree | Day 2 | T3 | BE T5 | LO4 | 30 | 30 |
| 15 | RACI Responsibility Assignment Matrix | Day 3 | T4 | People T3, Process T4 | LO2 | 20 | 25 |
| 16 | Tuckman Diagnosis and Motivation Theory Application | Day 3 | T4 | People T3 | LO3 | 20 | 25 |
| 17 | Conflict Resolution Role-Play across the Five Modes | Day 3 | T4 | People T2 | LO3 | 20 | 30 |
| 18 | Communication Plan, Channels Formula and Status Report | Day 3 | T4 | People T8 | LO4 | 20 | 30 |
| 19 | Kanban Board with WIP Limits and Lead/Cycle Time | Day 3 | T5 | Process T9 | LO5 | 20 | 25 |
| 20 | Earned Value Management and Schedule Compression | Day 3 | T5 | Process T9 | LO5 | 25 | 35 |
| 21 | Root Cause Analysis with 5 Whys, Fishbone and Pareto | Day 3 | T5 | BE T4 | LO3 | 25 | 35 |
| 22 | SPC Control Chart and Statistical Process Analysis | Day 3 | T5 | Process T7 | LO5 | 30 | 30 |
| 23 | Project Closure, Benefits Realisation and Lessons Learned | Day 4 | T6 | Process T10, BE T6 | LO5 | 60 | 0 |
| 24 | Capstone: Consolidated Project Plan and Mock Exam | Day 4 | T6 | All domains | LO1-LO5 | 105 | 15 |

## Tools Used in the Labs

| Tool | Purpose | URL |
| --- | --- | --- |
| 5 Whys | Drill from a symptom to its root cause by asking 'why' five times. | https://alfredang.github.io/5whys/ |
| Fishbone Diagram | Group candidate causes into categories around a problem statement. | https://alfredang.github.io/fishbone/ |
| Pareto Chart | Rank defect categories to find the vital few driving most of the pain. | https://alfredang.github.io/paretochart/ |
| System Thinking | Map reinforcing and balancing loops behind a recurring problem. | https://alfredang.github.io/systemloop/ |
| SPC / Control Chart | Plot a process over time against control limits to separate signal from noise. | https://alfredang.github.io/novaspc/ |
| Statistics | Descriptive statistics, distributions and hypothesis testing on project data. | https://alfredang.github.io/novastats/ |
| RACI Matrix | Assign Responsible, Accountable, Consulted and Informed per work package. | https://alfredang.github.io/raci/ |
| Kanban Board | Visualise work in progress, limit WIP and expose bottlenecks. | https://alfredang.github.io/kanban/ |
| Scrum Simulator | Run sprint planning, review and retrospective mechanics. | https://alfredang.github.io/scrum/ |
| Mind Mapping | Expand a central idea into branches for requirements discovery. | https://alfredang.github.io/mindmapping/ |
| Design Thinking | Empathise, define, ideate, prototype and test a solution. | https://alfredang.github.io/designthinking/ |
| Pivot Analysis | Slice project data by dimension to expose trends and outliers. | https://alfredang.github.io/novapivot/ |

# Preparing for the PMP Examination

## Exam Structure

| Element | Detail |
| --- | --- |
| Questions | 180 (170 scored + 10 pretest) |
| Duration | 240 minutes |
| Breaks | Two 10-minute breaks — the first after the case-study section, the second midway through the independent questions. |
| Approach mix | About 40% predictive; the remaining 60% split between adaptive/agile and hybrid. |
| Domains | People 33% · Process 41% · Business Environment 26% |

## Question Types

| Type | What it asks of you |
| --- | --- |
| Multiple choice | One best answer from four options — the bulk of the exam. |
| Multiple response | More than one correct answer; the item tells you how many. |
| Matching | Drag items from one column to match a second column. |
| Enhanced matching | Matching that includes an image or diagram for context. |
| Graphic-based (NEW) | Read a chart, graph, diagram or image, then answer from it. |
| Case study | A scenario with supporting visuals, then a series of linked questions. |

## Formula Reference

| Formula | Expression | Reading |
| --- | --- | --- |
| Cost variance | CV = EV − AC | Positive is under budget |
| Schedule variance | SV = EV − PV | Positive is ahead of schedule |
| Cost performance index | CPI = EV / AC | Above 1.0 is under budget |
| Schedule performance index | SPI = EV / PV | Above 1.0 is ahead |
| Estimate at completion | EAC = BAC / CPI | When current variance is expected to continue |
| Estimate to complete | ETC = EAC − AC | Remaining expected cost |
| Variance at completion | VAC = BAC − EAC | Forecast budget variance |
| To-complete performance index | TCPI = (BAC − EV) / (BAC − AC) | Efficiency needed to finish on budget |
| Three-point (PERT) | (O + 4M + P) / 6 | Weighted average estimate |
| PERT standard deviation | (P − O) / 6 | Estimate uncertainty |
| Expected monetary value | EMV = probability × impact | Summed across outcomes |
| Communication channels | N(N − 1) / 2 | Grows quadratically |

## Study Plan After the Course

Week 1-2: Re-read this guide topic by topic and redo the labs on a project of your own.

Week 3-4: Drill practice questions by domain, weighting your time Process 41%, People 33%, Business Environment 26%.

Week 5-6: Practise the graphic-based and case-study question types specifically — they behave differently from plain multiple choice.

Week 7-8: Sit at least three full 180-question mock exams under timed conditions, reviewing every wrong answer to its underlying concept.

Submit your PMI application, logging this course's 30 contact hours and topping up the remaining 5 hours of project management education.