Tertiary Infotech Academy Pte Ltd

ACTIVITY 2 — FACILITATOR GUIDE

PESTLE and TECOP External Environment Scan

| TYPE Workshop | DURATION 75 minutes | MAPS TO LO4 | TOPIC 1 - Business Environment |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to run a structured PESTLE scan of the environment surrounding the Contoso Training Portal Upgrade.

What learners produce

pestle scan, tecop scan, backlog impacts — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

Laptop with internet access for the live problem-solving tools

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Read the environment briefing | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 2 | Build and score the PESTLE table. Create artifacts/02-pestle-scan.md. For each of the six categories, record at least one factor. Score impact 1-5 and likelihood 1-5, then compute Score = Impact x Likelihood. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 3 | Run the TECOP scan. PESTLE looks outward at the market. TECOP looks at the *risk dimensions of the project itself* and catches things PESTLE misses - particularly operational and organisational exposure. | Have one group present a single row rather than the whole artifact — depth over coverage. |
| 4 | Rank and take the vital few. Combine both tables, sort by score descending, and take everything scoring 16 or above. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 5 | Translate factors into scope and backlog consequences. This is the step most people skip, and it is the step the ECO actually assesses. A scan that changes nothing is decoration. Create artifacts/02-backlog-impacts.md: | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 6 | Set the review cadence. ECO Business Env T8 says "*continually* review the external business environment for impacts". Define who looks, when, and what triggers an out-of-cycle review. | If a group finishes early, ask what changes at twice the scale or half the budget. |
| 7 | Answer the exam-style scenarios | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 8 min | Brief the scenario, confirm the inputs and assign roles |
| 28 min | Work the first half of the steps individually, then pool as a group |
| 28 min | Complete the remaining steps and finalise the deliverable |
| 11 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 75 minutes

Discussion & decision prompts

Run a structured PESTLE scan of the environment surrounding the Contoso Training Portal Upgrade — how did your group decide, and what would change that decision?

Run a TECOP scan to surface risk dimensions PESTLE tends to miss — how did your group decide, and what would change that decision?

Score each factor for impact and likelihood, and rank them — how did your group decide, and what would change that decision?

Every PESTLE letter (P, E, S, T, L, E) has at least one factor; a scan missing a category is not a PESTLE scan — can every member of your group defend it?

Where would pestle and tecop external environment scan have saved you time or money on a real project you have worked on?

What good looks like

Every PESTLE letter (P, E, S, T, L, E) has at least one factor; a scan missing a category is not a PESTLE scan.

Every score is the product of impact and likelihood, and you can state both numbers for any factor.

Your TECOP table surfaced at least one factor that does not appear anywhere in your PESTLE table. If the two tables are identical, you used PESTLE twice.

Every factor scoring 16+ has a named destination artifact in a later lab - not a vague "monitor".

Your cadence names an owner, a frequency, and at least three out-of-cycle triggers.

In Scenario 1 you chose B and can explain why "add to risk register and continue" is wrong for an event that has already happened.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd