Tertiary Infotech Academy Pte Ltd

ACTIVITY 5 — FACILITATOR GUIDE

Business Case and Cost-Benefit Analysis

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO1 | TOPIC 2 - Start the Project |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to build a quantified benefits model from the Lab 03 baseline metrics.

What learners produce

business case, cba model, benefits map — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

Laptop with internet access for the live problem-solving tools

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Quantify the benefits from the Lab 03 baselines. Every benefit must trace to a metric you baselined in Lab 03. Create artifacts/05-cba-model.md. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 2 | Build the cost side. Note that the total build cost equals the SGD 480,000 ceiling exactly, and that the contingency reserve sits *inside* it - the Lab 02 factor E2 consequence. You will decompose these numbers properly in Lab 13. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 3 | Compute payback, NPV, ROI and BCR. Build the net cash flow table. Use a discount rate of 8%, Contoso's stated cost of capital. | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 4 | Stress-test against the Lab 02 downside. Lab 02 factor E1 said client L&D budgets are down 8%. Test the case with 8% lower registration volume *and* a weaker abandonment recovery - 34% down to only 22% rather than 15%. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 5 | Choose among options. The sponsor asks you to compare three options before committing. Complete the comparison and make a recommendation. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 6 | Write the business case document. Create artifacts/05-business-case.md using this structure: | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 7 | Build the benefits realisation map. Create artifacts/05-benefits-map.md. This is what Lab 23 will formally close against, so make it verifiable. | The trace is the learning, not the artifact. Ask a group to walk one line end to end aloud. |
| 8 | Answer the exam-style scenarios | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 9 min | Brief the scenario, confirm the inputs and assign roles |
| 33 min | Work the first half of the steps individually, then pool as a group |
| 34 min | Complete the remaining steps and finalise the deliverable |
| 14 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 90 minutes

Discussion & decision prompts

Build a quantified benefits model from the Lab 03 baseline metrics — how did your group decide, and what would change that decision?

Compute payback period, net present value, return on investment and benefit-cost ratio - by hand, so the exam formulas stick — how did your group decide, and what would change that decision?

Test the case against the Lab 02 downside scenario of an 8% fall in enrolment — how did your group decide, and what would change that decision?

Every benefit line traces to a Lab 03 baseline metric. A benefit with no baseline cannot be proven in Lab 23 — can every member of your group defend it?

Where would business case and cost-benefit analysis have saved you time or money on a real project you have worked on?

What good looks like

Every benefit line traces to a Lab 03 baseline metric. A benefit with no baseline cannot be proven in Lab 23.

Your discount factors decrease with time and are below 1. If any factor exceeds 1, you have inverted the formula.

Your NPV subtracts the initial investment. Forgetting the year-0 outflow is the single most common arithmetic error here.

Your BCR is above 1 and equals total benefit divided by total cost - not the inverse.

Your do-nothing option has a *negative* number attached, not a blank. Do-nothing is never free.

Your recommendation cites NPV as the deciding measure, not payback or project size.

Your downside scenario still shows a positive NPV, and you stated that conclusion explicitly.

In Scenario 2 you named the SGD 180,000 as sunk before discussing what to do next.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd