Tertiary Infotech Academy Pte Ltd

ACTIVITY 5 — LEARNER WORKSHEET

Business Case and Cost-Benefit Analysis

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO1 | TOPIC 2 - Start the Project |
| --- | --- | --- | --- |

What you are doing

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

What you will produce: business case, cba model, benefits map — submitted to artifacts/.

What you need before you start

Lab 02 factors E1 and E2

Lab 03 success metrics and baselines

Lab 04 compliance exposure figures

Your steps

Quantify the benefits from the Lab 03 baselines. Every benefit must trace to a metric you baselined in Lab 03. Create artifacts/05-cba-model.md.

Build the cost side. Note that the total build cost equals the SGD 480,000 ceiling exactly, and that the contingency reserve sits *inside* it - the Lab 02 factor E2 consequence. You will decompose these numbers properly in Lab 13.

Compute payback, NPV, ROI and BCR. Build the net cash flow table. Use a discount rate of 8%, Contoso's stated cost of capital.

Stress-test against the Lab 02 downside. Lab 02 factor E1 said client L&D budgets are down 8%. Test the case with 8% lower registration volume *and* a weaker abandonment recovery - 34% down to only 22% rather than 15%.

Choose among options. The sponsor asks you to compare three options before committing. Complete the comparison and make a recommendation.

Write the business case document. Create artifacts/05-business-case.md using this structure:

Build the benefits realisation map. Create artifacts/05-benefits-map.md. This is what Lab 23 will formally close against, so make it verifiable.

Answer the exam-style scenarios

Your working space

Complete every field. Keep this worksheet — it is your reference for the rest of the course.

Step 1 — Quantify the benefits from the Lab 03 baselines

Step 2 — Build the cost side

Step 3 — Compute payback, NPV, ROI and BCR

Step 4 — Stress-test against the Lab 02 downside

Step 5 — Choose among options

Step 6 — Write the business case document

Step 7 — Build the benefits realisation map

Step 8 — Answer the exam-style scenarios

Deliverable checklist

05-cba-model.md - the benefits quantification B1-B4 traced to Lab 03 baselines, the cost table, and the discounted cash flow table with all discount factors shown.

All four financial measures computed with working shown: payback period, NPV, ROI, BCR.

The downside sensitivity scenario with its recomputed NPV and payback.

The three-option comparison including the quantified cost of doing nothing.

05-business-case.md - all ten sections.

05-benefits-map.md - each benefit traced output -> outcome -> benefit, with baseline, target, owner and review date.

Written answers to the three scenarios.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd