Tertiary Infotech Academy Pte Ltd

ACTIVITY 9 — FACILITATOR GUIDE

Requirements Elicitation, Mind Mapping and the Traceability Matrix

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO1 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to select the right elicitation technique for each stakeholder group rather than defaulting to interviews for everything.

What learners produce

requirements mindmap, requirements register, rtm — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

The Project Management Templates pack (see the Activities folder)

Laptop with internet access for the live problem-solving tools

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Choose elicitation techniques deliberately. There is no single best technique. Each buys different information at a different cost, and the exam tests whether you can match technique to situation. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 2 | Build the requirements mind map in the live tool. Open the mind mapping tool: Mind Mapping | If the room agrees too quickly, take the quietest role aside and give them one more constraint. |
| 3 | Write the requirements register. Create artifacts/09-requirements-register.md. Priority uses MoSCoW, which Lab 10 will formalise and challenge. | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 4 | Set requirement attributes and versioning. A requirement is not just a sentence. Each one carries attributes that make it manageable. Record these for every requirement in the register. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 5 | Build the requirements traceability matrix. Create artifacts/09-rtm.md. The RTM is the single artifact that connects the business need at one end to the test evidence at the other. Build it as a table with a column for every link in that chain. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 6 | Understand what bidirectional traceability actually buys you. Compute the current compliance coverage from the matrix above and record it: | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 7 | Answer the exam-style scenarios | Keep role-holders in role; learners drift to consensus. Push for the concern behind the stated position. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 9 min | Brief the scenario, confirm the inputs and assign roles |
| 33 min | Work the first half of the steps individually, then pool as a group |
| 34 min | Complete the remaining steps and finalise the deliverable |
| 14 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 90 minutes

Discussion & decision prompts

Select the right elicitation technique for each stakeholder group rather than defaulting to interviews for everything — how did your group decide, and what would change that decision?

Use a mind map to decompose the charter's six high-level requirements into a structured requirement set — how did your group decide, and what would change that decision?

Write a requirements register in which every requirement is testable, sourced and prioritised — how did your group decide, and what would change that decision?

Every non-functional requirement in your register contains a number and a measurement method. If any NFR reads "fast", "reliable" or "user-friendly", it is not finished — can every member of your group defend it?

Where would requirements elicitation, mind mapping and the traceability matrix have saved you time or money on a real project you have worked on?

What good looks like

Every non-functional requirement in your register contains a number and a measurement method. If any NFR reads "fast", "reliable" or "user-friendly", it is not finished.

Every requirement has an acceptance criterion that could be handed to a tester who was not in the room.

You used observation rather than interviews for the admin staff, and you can state why.

Your register contains at least three transition requirements. If it has none, you have confused the product with the project.

Your RTM traces in both directions, and you can demonstrate an impact analysis by naming every downstream artifact affected by a change to REQ-018.

You computed a compliance coverage fraction as a number, found it was below 13/13, and drafted the requirements to close the gap - rather than assuming coverage.

You can state what happens to a requirement after baseline and what does not require a change request in the hybrid model.

No requirement in your register specifies a technology choice unless a named stakeholder genuinely requires that technology.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd