Tertiary Infotech Academy Pte Ltd

ACTIVITY 9 — LEARNER WORKSHEET

Requirements Elicitation, Mind Mapping and the Traceability Matrix

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO1 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

What you are doing

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

What you will produce: requirements mindmap, requirements register, rtm — submitted to artifacts/.

What you need before you start

Lab 06 charter high-level requirements R-1 to R-6 and scope boundaries

Lab 07 stakeholder register

Lab 04 compliance requirements C-01 to C-13

Your steps

Choose elicitation techniques deliberately. There is no single best technique. Each buys different information at a different cost, and the exam tests whether you can match technique to situation.

Build the requirements mind map in the live tool. Open the mind mapping tool: Mind Mapping

Write the requirements register. Create artifacts/09-requirements-register.md. Priority uses MoSCoW, which Lab 10 will formalise and challenge.

Set requirement attributes and versioning. A requirement is not just a sentence. Each one carries attributes that make it manageable. Record these for every requirement in the register.

Build the requirements traceability matrix. Create artifacts/09-rtm.md. The RTM is the single artifact that connects the business need at one end to the test evidence at the other. Build it as a table with a column for every link in that chain.

Understand what bidirectional traceability actually buys you. Compute the current compliance coverage from the matrix above and record it:

Answer the exam-style scenarios

Your working space

Complete every field. Keep this worksheet — it is your reference for the rest of the course.

Step 1 — Choose elicitation techniques deliberately

Step 2 — Build the requirements mind map in the live tool

Step 3 — Write the requirements register

Step 4 — Set requirement attributes and versioning

Step 5 — Build the requirements traceability matrix

Step 6 — Understand what bidirectional traceability actually buys you

Step 7 — Answer the exam-style scenarios

Deliverable checklist

09-requirements-mindmap.md - the exported or screenshotted mind map with the central node, all eight branches and at least four sub-branch leaves each.

09-requirements-register.md - at least 22 numbered requirements spanning business, stakeholder, functional, non-functional, transition and quality categories, each with source, priority and a testable acceptance criterion.

The requirement attribute set completed for at least five requirements, including status and version.

09-rtm.md - at least 12 populated rows tracing business need, charter requirement, requirement ID, WBS element, story, design artifact, test case and compliance requirement.

The compliance coverage fraction computed from the RTM, with the uncovered C-nn named and the closing requirements drafted.

The elicitation technique selection table with the technique chosen for each stakeholder group and the reason.

Written answers to the three scenarios.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd