Tertiary Infotech Academy Pte Ltd

ACTIVITY 10 — LEARNER WORKSHEET

MoSCoW, Kano and the Product Backlog

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO1 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

What you are doing

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

What you will produce: moscow, kano, product backlog — submitted to artifacts/.

What you need before you start

Lab 09 requirements register REQ-001 to REQ-031

Lab 05 benefits map B1-B4

Lab 07 stakeholder expectations and misalignment M-1

Your steps

Apply MoSCoW to the Lab 09 requirements. Create artifacts/10-moscow.md. Test every candidate Must against the three-part question before accepting it.

Classify the features on Kano. Create artifacts/10-kano.md. Classify by asking the Kano pair of questions for each feature: how would you feel if the feature were present, and how would you feel if it were absent.

Where MoSCoW and Kano disagree, and why that is useful. Running both models produces conflicts. The conflicts are the point; if the two models agreed everywhere, one of them would be redundant.

Write the product backlog. Create artifacts/10-product-backlog.md. Every story uses the form: As a <role>, I want <capability>, so that <benefit>. The "so that" clause is not decoration - a story whose benefit clause cannot be completed is a story with no traceable value, and Lab 09's backward traceability would flag it as gold plating.

Estimate with story points, not hours

Build the release plan against real capacity. Create artifacts/10-release-plan.md. Sequence by dependency and by gate obligation, not by preference.

Make the AI recommender trade-off numeric. Lab 07 identified misalignment M-1 and committed you to converting an argument about importance into a concrete trade-off. Here is the arithmetic that session needs.

Answer the exam-style scenarios

Your working space

Complete every field. Keep this worksheet — it is your reference for the rest of the course.

Step 1 — Apply MoSCoW to the Lab 09 requirements

Step 2 — Classify the features on Kano

Step 3 — Where MoSCoW and Kano disagree, and why that is useful

Step 4 — Write the product backlog

Step 5 — Estimate with story points, not hours

Step 6 — Build the release plan against real capacity

Step 7 — Make the AI recommender trade-off numeric

Step 8 — Answer the exam-style scenarios

Deliverable checklist

10-moscow.md - every requirement classified, with the three-part Must test shown for each Must, and the effort split arithmetic proving Musts are at or under 60%.

10-kano.md - at least 14 features classified across all five Kano categories, including at least one Reverse and one Indifferent, with the time-decay reasoning stated for at least one feature.

The MoSCoW-versus-Kano conflict table with a resolution for each conflict and the four rules that fall out of it.

10-product-backlog.md - at least 24 user stories in As a / I want / So that form, each with points from the modified Fibonacci scale, MoSCoW priority, Kano class, acceptance criteria and a trace to a Lab 09 requirement.

The reference story identified with its point value and the calibration of at least four other stories against it.

The INVEST assessment and the Definition of Ready.

10-release-plan.md - a rebalanced 12-sprint plan in which no sprint exceeds 34 points, with the dropped Coulds named, and the proof that all Must-have effort fits before gate G2.

The AI recommender trade-off arithmetic with all four options costed.

Written answers to the three scenarios.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd