Tertiary Infotech Academy Pte Ltd

ACTIVITY 11 — LEARNER WORKSHEET

Work Breakdown Structure and WBS Dictionary

| TYPE Workshop | DURATION 75 minutes | MAPS TO LO1, LO2 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

What you are doing

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

What you will produce: wbs, wbs dictionary, scope baseline — submitted to artifacts/.

What you need before you start

Lab 09 requirements register and RTM

Lab 10 product backlog

Lab 06 scope boundaries IN-1 to IN-10 and OUT-1 to OUT-7

Your steps

Confirm the inputs and the boundary. The WBS decomposes the scope statement. Before decomposing, confirm what the boundary is, because the 100% rule is meaningless without a defined 100%.

Build the WBS to three levels. Create artifacts/11-wbs.md. Render it as an indented tree with numbered codes.

Trace the compliance workstream to its origin. Branch 1.8 deserves a specific note, because it is the branch most likely to be questioned as overhead.

Write the WBS dictionary. Create artifacts/11-wbs-dictionary.md. A WBS code and a name are not enough to execute work. The dictionary entry is what a person who was not in the planning session needs.

Place control accounts and planning packages. Rolling wave: two branches are deliberately left as planning packages at baseline.

Assemble the scope baseline. Create artifacts/11-scope-baseline.md containing all three components with a version number and an approval block.

Reconcile the WBS with the product backlog. This is the real hybrid tailoring question, and it is the one most often answered badly - usually by maintaining both artifacts as duplicates and letting them drift apart.

Answer the exam-style scenarios

Your working space

Complete every field. Keep this worksheet — it is your reference for the rest of the course.

Step 1 — Confirm the inputs and the boundary

Step 2 — Build the WBS to three levels

Step 3 — Trace the compliance workstream to its origin

Step 4 — Write the WBS dictionary

Step 5 — Place control accounts and planning packages

Step 6 — Assemble the scope baseline

Step 7 — Reconcile the WBS with the product backlog

Step 8 — Answer the exam-style scenarios

Deliverable checklist

11-wbs.md - the full WBS to three levels as an indented numbered tree, covering all eleven level-2 branches, with the 100% rule verified at each level and the overlap and orphan checks recorded.

The trace showing why branch 1.8 exists, from Lab 02 factor L1 through Lab 04, Lab 06 and Lab 09 to this WBS.

11-wbs-dictionary.md - at least 8 fully populated entries, each with WBS code, name, description, deliverable, acceptance criteria, responsible role, effort estimate, cost estimate, predecessor and quality requirement.

The control account table with owners and budgets, and at least two planning packages with their decomposition dates and the reason they are not yet decomposed.

11-scope-baseline.md - scope statement plus WBS plus WBS dictionary, versioned and with an approval block.

The WBS-versus-backlog comparison, the mapping rule, and the statement of where the change control boundary sits.

Written answers to the three scenarios.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd