Tertiary Infotech Academy Pte Ltd

ACTIVITY 14 — CHECKLIST

Risk Register, RBS, EMV and Decision Tree

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO4 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

| Name |  |
| --- | --- |
| Date |  |

Self-check — Risk Register, RBS, EMV and Decision Tree

Tick each item you have completed. Any blank is a gap to close before your group presents at the debrief.

| # | Criterion | Evidences | ✓ |
| --- | --- | --- | --- |
| 1 | Every risk statement contains a cause that is a present fact, an uncertain event, and an effect on a named project objective. If any statement is a single noun phrase, it cannot be responded to or priced. | LO4 |  |
| 2 | Your register contains at least two opportunities with positive EMV. A register of threats only is half a risk register. | LO4 |  |
| 3 | Every assumption in the Lab 06 log has a corresponding risk, and you can show the conversion for A-05. | LO4 |  |
| 4 | Every risk has a trigger that someone could actually observe. "Monitor closely" is not a trigger. | LO4 |  |
| 5 | Your P/I scores are consistent with your decimal probabilities - a risk at 0.45 should not score 2 on a 1-5 probability scale. | LO4 |  |
| 6 | Your residual net EMV is approximately SGD 26,600, reconciling to the SGD 26,000 contingency with the SGD 600 variance stated rather than hidden. | LO4 |  |
| 7 | Your opportunity probabilities INCREASED after response while your threat probabilities decreased. If both moved the same way, you applied threat logic to opportunities. | LO4 |  |
| 8 | Your decision tree branch probabilities sum to exactly 1.0 at each chance node, and the decision node costs are included in the path totals. | LO4 |  |

Debrief check

Every risk statement contains a cause that is a present fact, an uncertain event, and an effect on a named project objective. If any statement is a single noun phrase, it cannot be responded to or priced.

Feedback

What did you find hardest in this activity?

What is the ONE thing you will do differently at work?

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd