Tertiary Infotech Academy Pte Ltd

ACTIVITY 14 — FACILITATOR GUIDE

Risk Register, RBS, EMV and Decision Tree

| TYPE Workshop | DURATION 90 minutes | MAPS TO LO4 | TOPIC 3 - Plan the Project |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to build a risk breakdown structure and use it to identify risks systematically rather than by brainstorm alone.

What learners produce

risk register, rbs, pi matrix — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

Flipchart or A3 sheet and markers

Laptop with internet access for the live problem-solving tools

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Build the risk breakdown structure. Create artifacts/14-rbs.md. The RBS is a hierarchy of risk SOURCES. Its purpose is systematic identification: working through categories catches risks that free brainstorming misses, because brainstorming surfaces what is memorable rather than what is likely. | Keep role-holders in role; learners drift to consensus. Push for the concern behind the stated position. |
| 2 | Trace risks from Lab 02 factors and Lab 06 assumptions. Risk identification is not invention. Most risks on a well-run project are already sitting in earlier artifacts, unlabelled. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 3 | Write risk statements in cause-event-effect form | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 4 | Build the risk register. Create artifacts/14-risk-register.md. Probability is given as a decimal and as a 1-5 score. Impact is scored 1-5, with the cost impact in SGD and the schedule impact in days. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 5 | Plot the probability/impact matrix. Create artifacts/14-pi-matrix.md. Score = probability score x impact score, both on 1-5. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 6 | Apply all ten response strategies. A real Contoso example of each of the ten: | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 7 | Compute expected monetary value. Sign convention: threat impacts are shown as positive cost figures and summed as exposure; opportunity impacts are shown as negative because they reduce exposure. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 8 | Build and solve a decision tree. Create artifacts/14-emv-analysis.md. A decision tree evaluates a choice under uncertainty by computing the EMV of each branch and selecting the best. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 9 | Qualitative versus quantitative, and when a risk becomes an issue | Ask for one item the group nearly dropped and what made them keep it. |
| 10 | Answer the exam-style scenarios | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 9 min | Brief the scenario, confirm the inputs and assign roles |
| 33 min | Work the first half of the steps individually, then pool as a group |
| 34 min | Complete the remaining steps and finalise the deliverable |
| 14 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 90 minutes

Discussion & decision prompts

Build a risk breakdown structure and use it to identify risks systematically rather than by brainstorm alone — how did your group decide, and what would change that decision?

Trace risks from the Lab 02 environment scan and the Lab 06 assumption log, since every assumption is a latent risk — how did your group decide, and what would change that decision?

Write risk statements in cause-event-effect form so that the cause can be attacked and the effect can be priced — how did your group decide, and what would change that decision?

Every risk statement contains a cause that is a present fact, an uncertain event, and an effect on a named project objective. If any statement is a single noun phrase, it cannot be responded to or priced — can every member of your group defend it?

Where would risk register, rbs, emv and decision tree have saved you time or money on a real project you have worked on?

What good looks like

Every risk statement contains a cause that is a present fact, an uncertain event, and an effect on a named project objective. If any statement is a single noun phrase, it cannot be responded to or priced.

Your register contains at least two opportunities with positive EMV. A register of threats only is half a risk register.

Every assumption in the Lab 06 log has a corresponding risk, and you can show the conversion for A-05.

Every risk has a trigger that someone could actually observe. "Monitor closely" is not a trigger.

Your P/I scores are consistent with your decimal probabilities - a risk at 0.45 should not score 2 on a 1-5 probability scale.

Your residual net EMV is approximately SGD 26,600, reconciling to the SGD 26,000 contingency with the SGD 600 variance stated rather than hidden.

Your opportunity probabilities INCREASED after response while your threat probabilities decreased. If both moved the same way, you applied threat logic to opportunities.

Your decision tree branch probabilities sum to exactly 1.0 at each chance node, and the decision node costs are included in the path totals.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd