Tertiary Infotech Academy Pte Ltd

ACTIVITY 15 — CHECKLIST

RACI Responsibility Assignment Matrix and Resource Plan

| TYPE Workshop | DURATION 45 minutes | MAPS TO LO2 | TOPIC 4 - Lead the Project Team |
| --- | --- | --- | --- |

| Name |  |
| --- | --- |
| Date |  |

Self-check — RACI Responsibility Assignment Matrix and Resource Plan

Tick each item you have completed. Any blank is a gap to close before your group presents at the debrief.

| # | Criterion | Evidences | ✓ |
| --- | --- | --- | --- |
| 1 | Every one of your 25 rows has exactly one A and at least one R. Count them; do not assume. | LO2 |  |
| 2 | You resolved the two-A defect on the compliance evidence pack by SPLITTING the task, not by demoting the DPO or the PM to C. | LO2 |  |
| 3 | You found the row with no R, and you can say why that row belonged to the dependent stakeholders from Lab 07 rather than to anyone powerful. | LO2 |  |
| 4 | Your R-per-column count identified the BA at 14 of 24 rows, and you connected that to the Lab 16 storming diagnosis as a structural cause rather than a behavioural one. | LO2 |  |
| 5 | You challenged every C with the question "would their input change the work?" and you demoted at least one C to I with a stated reason. | LO2 |  |
| 6 | Your resource histogram has an explicit capacity line and you stated the total demand (320 hours) against total capacity (288 hours) before choosing a remedy. | LO2 |  |
| 7 | You can state, without looking it up, that levelling can change the critical path and extend the end date while smoothing works within float and cannot. | LO2 |  |
| 8 | You rejected levelling for Contoso on the specific ground that it pushes the G1 design baseline and therefore the critical path past the immovable 30 June date in constraint CON-1. | LO2 |  |

Debrief check

Every one of your 25 rows has exactly one A and at least one R. Count them; do not assume.

Feedback

What did you find hardest in this activity?

What is the ONE thing you will do differently at work?

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd