Tertiary Infotech Academy Pte Ltd

ACTIVITY 15 — FACILITATOR GUIDE

RACI Responsibility Assignment Matrix and Resource Plan

| TYPE Workshop | DURATION 45 minutes | MAPS TO LO2 | TOPIC 4 - Lead the Project Team |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to assign R, A, C and I precisely, and defend every assignment against the one-accountable rule.

What learners produce

raci matrix, resource plan, raci issues — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

The Project Management Templates pack (see the Activities folder)

Flipchart or A3 sheet and markers

Laptop with internet access for the live problem-solving tools

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Assemble the inputs. A RACI is derived, not invented. Confirm you have each input before you draw a single letter. | Keep role-holders in role; learners drift to consensus. Push for the concern behind the stated position. |
| 2 | Draft the matrix (this draft contains deliberate defects). Below is the first-draft RACI as a real project team would produce it in a 40-minute workshop. It covers 20 rows drawn from the Lab 11 WBS plus four cross-cutting process rows. It contains five structural defects. Do not fix them yet - Step 3 is the audit. | Pick one entry and follow it back to its source document. Broken traces surface immediately. |
| 3 | Enter it in the live RACI tool. Open RACI Matrix and build the matrix so the tool can run the structural checks for you. | Debrief on what was conceded and why — the trade, not the outcome, is the learning. |
| 4 | Audit the matrix and find the five defects. This is the real learning in this lab. A RACI is only worth building if you then interrogate it. Run the five checks in order. | Keep role-holders in role; learners drift to consensus. Push for the concern behind the stated position. |
| 5 | Before and after, in numbers. The audit must produce a measurable change, or it was a discussion rather than an audit. | Pick one entry and follow it back to its source document. Broken traces surface immediately. |
| 6 | Build the resource plan and histogram. Create artifacts/15-resource-plan.md. The RACI says who; the resource plan says how much and when. | If a group finishes early, ask what changes at twice the scale or half the budget. |
| 7 | Level or smooth: the distinction the exam tests. Now work both remedies against the real BA over-allocation. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 8 | Connect the RACI to the communication plan. Every C and every I in the matrix is a promise to communicate. Lab 18 has to schedule and staff those promises, so count them now. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 9 | Answer the exam-style scenarios | Ask for one item the group nearly dropped and what made them keep it. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 4 min | Brief the scenario, confirm the inputs and assign roles |
| 17 min | Work the first half of the steps individually, then pool as a group |
| 17 min | Complete the remaining steps and finalise the deliverable |
| 7 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 45 minutes

Discussion & decision prompts

Assign R, A, C and I precisely, and defend every assignment against the one-accountable rule — how did your group decide, and what would change that decision?

Build a real responsibility assignment matrix from the Lab 11 WBS, using the live RACI tool — how did your group decide, and what would change that decision?

Audit a matrix for the five structural defects that make a RACI useless, and fix them — how did your group decide, and what would change that decision?

Every one of your 25 rows has exactly one A and at least one R. Count them; do not assume — can every member of your group defend it?

Where would raci responsibility assignment matrix and resource plan have saved you time or money on a real project you have worked on?

What good looks like

Every one of your 25 rows has exactly one A and at least one R. Count them; do not assume.

You resolved the two-A defect on the compliance evidence pack by SPLITTING the task, not by demoting the DPO or the PM to C.

You found the row with no R, and you can say why that row belonged to the dependent stakeholders from Lab 07 rather than to anyone powerful.

Your R-per-column count identified the BA at 14 of 24 rows, and you connected that to the Lab 16 storming diagnosis as a structural cause rather than a behavioural one.

You challenged every C with the question "would their input change the work?" and you demoted at least one C to I with a stated reason.

Your resource histogram has an explicit capacity line and you stated the total demand (320 hours) against total capacity (288 hours) before choosing a remedy.

You can state, without looking it up, that levelling can change the critical path and extend the end date while smoothing works within float and cannot.

You rejected levelling for Contoso on the specific ground that it pushes the G1 design baseline and therefore the critical path past the immovable 30 June date in constraint CON-1.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd