Tertiary Infotech Academy Pte Ltd

ACTIVITY 18 — CHECKLIST

Communication Plan, Channels and Status Reporting

| TYPE Workshop | DURATION 75 minutes | MAPS TO LO4 | TOPIC 4 - Lead the Project Team |
| --- | --- | --- | --- |

| Name |  |
| --- | --- |
| Date |  |

Self-check — Communication Plan, Channels and Status Reporting

Tick each item you have completed. Any blank is a gap to close before your group presents at the debrief.

| # | Criterion | Evidences | ✓ |
| --- | --- | --- | --- |
| 1 | Your channel figures are 36 for N=9 and 78 for N=13, and you stated the +44% versus +117% comparison explicitly. | LO4 |  |
| 2 | You derived a management implication from the formula rather than just computing it. If your notes end at "78 channels", you have done the arithmetic and missed the point. | LO4 |  |
| 3 | Every row of your communication plan has a feedback loop that would let you detect a message failing to land. Rows saying "email sent" have no feedback loop. | LO4 |  |
| 4 | Every Resistant or anxious stakeholder in your plan (S-05, S-06, S-08, S-16) receives an interactive element. | LO4 |  |
| 5 | You computed CV% = -22,000 / 249,000 = -8.8% and identified the Lab 03 threshold breach yourself, and your board report states that escalation is mandatory within 5 working days rather than treating it as a judgement call. | LO4 |  |
| 6 | Your three status reports are all traceable to the same four figures - BAC 480,000, PV 268,000, EV 249,000, AC 271,000 - and none of them softens, omits or rounds favourably. | LO4 |  |
| 7 | Your sponsor one-pager contains no acronyms, translates CPI into money, and asks for a specific decision by a specific date. | LO4 |  |
| 8 | Your team report contains blockers and WIP and does not contain EAC. Reporting a forecast at completion to a standup is altitude failure in the other direction. | LO4 |  |

Debrief check

Your channel figures are 36 for N=9 and 78 for N=13, and you stated the +44% versus +117% comparison explicitly.

Feedback

What did you find hardest in this activity?

What is the ONE thing you will do differently at work?

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd