Tertiary Infotech Academy Pte Ltd

ACTIVITY 18 — FACILITATOR GUIDE

Communication Plan, Channels and Status Reporting

| TYPE Workshop | DURATION 75 minutes | MAPS TO LO4 | TOPIC 4 - Lead the Project Team |
| --- | --- | --- | --- |

Purpose of this activity

By the end of this activity learners will be able to compute communication channels with N(N-1)/2 and derive the management implication of superlinear growth.

What learners produce

communication plan, status reports — submitted to artifacts/.

Materials required

Learner Worksheet (one per learner)

Checklist (one per group)

The Project Management Templates pack (see the Activities folder)

Flipchart or A3 sheet and markers

The course slides for the framework and worked example

Set-up

Groups of 3 to 4. Distribute one worksheet per learner and one checklist per group; each group needs one laptop for the calculations.

Scenario / briefing material

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

How to run it — step by step

| # | Instruction to learners | Facilitator note |
| --- | --- | --- |
| 1 | Compute the communication channels. The last row is the number that should change your behaviour. There are 153 potential channels across the stakeholder set. Nobody can service 153 channels. A communication plan is not administrative tidiness; it is the decision about which of the 153 you will actually maintain and at what frequency. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 2 | Choose push, pull or interactive for each stakeholder | If the room agrees too quickly, take the quietest role aside and give them one more constraint. |
| 3 | Place communications in the formal/informal by written/verbal grid | Debrief on what was conceded and why — the trade, not the outcome, is the learning. |
| 4 | Build the communication plan with feedback loops. The ECO People T8 enabler is "establish a feedback loop". A row with no feedback mechanism is a broadcast, and a broadcast tells you nothing about whether the message arrived. Complete every column. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 5 | Trace the communication model and name the noise | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 6 | The week-14 status data. Create artifacts/18-status-reports.md. One set of facts follows. All three reports in Step 7 must be traceable to it. Tailoring means changing the encoding for the audience; it does not mean changing the numbers. | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |
| 7 | Write the same status three ways. Same data, three audiences, three encodings. Write all three into artifacts/18-status-reports.md. | Check the arithmetic on one group's numbers before moving on — a wrong sign propagates into every later step. |
| 8 | Compare a bad status report with a good one. The difference between the two is not length; the good version is shorter. It is that every sentence carries a number, a threshold, a cause, a trend or a decision. Read your own draft sentence by sentence and delete anything that carries none of the five. | Make a group state the UNITS and the base date. Most errors here are unit errors, not maths errors. |
| 9 | Answer the exam-style scenarios | Ask what the number would have to be before the decision flips. That is the exam's favourite question. |

Suggested timing

| Minutes | Phase |
| --- | --- |
| 8 min | Brief the scenario, confirm the inputs and assign roles |
| 28 min | Work the first half of the steps individually, then pool as a group |
| 28 min | Complete the remaining steps and finalise the deliverable |
| 11 min | Group share-back, facilitator debrief and exam-style linkage |

Total: 75 minutes

Discussion & decision prompts

Compute communication channels with N(N-1)/2 and derive the management implication of superlinear growth — how did your group decide, and what would change that decision?

Choose push, pull or interactive communication for each stakeholder and justify the choice — how did your group decide, and what would change that decision?

Place Contoso communications correctly in the formal/informal by written/verbal grid — how did your group decide, and what would change that decision?

Your channel figures are 36 for N=9 and 78 for N=13, and you stated the +44% versus +117% comparison explicitly — can every member of your group defend it?

Where would communication plan, channels and status reporting have saved you time or money on a real project you have worked on?

What good looks like

Your channel figures are 36 for N=9 and 78 for N=13, and you stated the +44% versus +117% comparison explicitly.

You derived a management implication from the formula rather than just computing it. If your notes end at "78 channels", you have done the arithmetic and missed the point.

Every row of your communication plan has a feedback loop that would let you detect a message failing to land. Rows saying "email sent" have no feedback loop.

Every Resistant or anxious stakeholder in your plan (S-05, S-06, S-08, S-16) receives an interactive element.

You computed CV% = -22,000 / 249,000 = -8.8% and identified the Lab 03 threshold breach yourself, and your board report states that escalation is mandatory within 5 working days rather than treating it as a judgement call.

Your three status reports are all traceable to the same four figures - BAC 480,000, PV 268,000, EV 249,000, AC 271,000 - and none of them softens, omits or rounds favourably.

Your sponsor one-pager contains no acronyms, translates CPI into money, and asks for a specific decision by a specific date.

Your team report contains blockers and WIP and does not contain EAC. Reporting a forecast at completion to a standup is altitude failure in the other direction.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd