Tertiary Infotech Academy Pte Ltd

ACTIVITY 18 — LEARNER WORKSHEET

Communication Plan, Channels and Status Reporting

| TYPE Workshop | DURATION 75 minutes | MAPS TO LO4 | TOPIC 4 - Lead the Project Team |
| --- | --- | --- | --- |

What you are doing

Contoso Learning Pte Ltd is a training provider with 14,000 active learners. Its course registration portal is 9 years old. Registration takes a median of 11 minutes and 34% of attempts are abandoned. Learner communications consume 24 staff-hours per week across 3 administrators. 62% of learner traffic is mobile, against a portal that is not responsive. Legacy consent screens do not meet current PDPA requirements. The project modernises course registration and learner communications.

What you will produce: communication plan, status reports — submitted to artifacts/.

What you need before you start

Lab 07 stakeholder register, engagement matrix and engagement cadence table

Lab 03 governance model and escalation thresholds

Your steps

Compute the communication channels. The last row is the number that should change your behaviour. There are 153 potential channels across the stakeholder set. Nobody can service 153 channels. A communication plan is not administrative tidiness; it is the decision about which of the 153 you will actually maintain and at what frequency.

Choose push, pull or interactive for each stakeholder

Place communications in the formal/informal by written/verbal grid

Build the communication plan with feedback loops. The ECO People T8 enabler is "establish a feedback loop". A row with no feedback mechanism is a broadcast, and a broadcast tells you nothing about whether the message arrived. Complete every column.

Trace the communication model and name the noise

The week-14 status data. Create artifacts/18-status-reports.md. One set of facts follows. All three reports in Step 7 must be traceable to it. Tailoring means changing the encoding for the audience; it does not mean changing the numbers.

Write the same status three ways. Same data, three audiences, three encodings. Write all three into artifacts/18-status-reports.md.

Compare a bad status report with a good one. The difference between the two is not length; the good version is shorter. It is that every sentence carries a number, a threshold, a cause, a trend or a decision. Read your own draft sentence by sentence and delete anything that carries none of the five.

Answer the exam-style scenarios

Your working space

Complete every field. Keep this worksheet — it is your reference for the rest of the course.

Step 1 — Compute the communication channels

Step 2 — Choose push, pull or interactive for each stakeholder

Step 3 — Place communications in the formal/informal by written/verbal grid

Step 4 — Build the communication plan with feedback loops

Step 5 — Trace the communication model and name the noise

Step 6 — The week-14 status data

Step 7 — Write the same status three ways

Step 8 — Compare a bad status report with a good one

Step 9 — Answer the exam-style scenarios

Deliverable checklist

18-communication-plan.md - the channels table with at least eight computed cases including the 9-to-13 growth comparison showing +44% people against +117% channels; the five written management implications; the push/pull/interactive assignment for at least twelve stakeholders with a justification each; the completed formal/informal by written/verbal grid with at least two Contoso examples per cell; the full communication plan table with all seven columns populated for at least fourteen rows, every one with a named feedback loop; the communication model with at least eight Contoso noise sources, each with a stage, a consequence and a control.

18-status-reports.md - the week-14 underlying data; your own threshold test showing CV% = -8.8% against the -5% threshold and stating that escalation is mandatory within 5 working days; the three tailored status reports; the comparison table showing what changed and what did not; the bad-versus-good report comparison with at least six named defects.

Written answers to the three scenarios.

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd