Tertiary Infotech Academy Pte Ltd

ACTIVITY 20 — CHECKLIST

Earned Value Management and Schedule Compression

| TYPE Workshop | DURATION 60 minutes | MAPS TO LO5 | TOPIC 5 - Monitor and Control the Project |
| --- | --- | --- | --- |

| Name |  |
| --- | --- |
| Date |  |

Self-check — Earned Value Management and Schedule Compression

Tick each item you have completed. Any blank is a gap to close before your group presents at the debrief.

| # | Criterion | Evidences | ✓ |
| --- | --- | --- | --- |
| 1 | Your cumulative PV at period 12 equals SGD 480,000 exactly. If it does not, stop - every forecast downstream is invalid. | LO5 |  |
| 2 | CV = -22,000 and SV = -19,000, both negative, and you described SV in dollars rather than days. | LO5 |  |
| 3 | CPI = 0.919 and SPI = 0.929, and you carried CPI to at least four decimal places before computing EAC. | LO5 |  |
| 4 | You computed all three EAC variants and *chose* one with a stated reason drawn from the trend, rather than defaulting to the first formula you remembered. | LO5 |  |
| 5 | Your TCPI of 1.105 is compared against your CPI of 0.919, and you concluded in writing that recovery to the original budget is not credible. | LO5 |  |
| 6 | You identified the seven-period monotonic CPI decline as systemic, not noise. | LO5 |  |
| 7 | Your crash decision selected J and O for SGD 15,500, and you explicitly rejected activity F despite it being the cheapest per day - because it is not on the critical path. | LO5 |  |
| 8 | You rejected fast-tracking the compliance review and cited both the mandatory dependency and the SGD 26,000 historical rework cost. | LO5 |  |

Debrief check

Your cumulative PV at period 12 equals SGD 480,000 exactly. If it does not, stop - every forecast downstream is invalid.

Feedback

What did you find hardest in this activity?

What is the ONE thing you will do differently at work?

Project Management Masterclass · C523 · Version v3.0 · © 2026 Tertiary Infotech Academy Pte Ltd