## Slide 1
COURSE SLIDES
Project Management Professional (PMP) Exam Prep
Course Code: C523
Conducted by Tertiary Infotech Academy Pte Ltd · UEN 201200696W
Version v1.0 · 20 July 2026
© 2026 Tertiary Infotech Academy Pte Ltd. All rights reserved. · www.tertiarycourses.com.sg

## Slide 2
COURSE ADMINISTRATION
Welcome & Housekeeping
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
1

## Slide 3
YOUR TRAINER · GENERAL
About the Trainer
?
Your Trainer
General Trainer template — to be completed by the trainer
NAME
____________________________________________
TITLE / DESIGNATION
____________________________________________
QUALIFICATIONS
____________________________________________
AREAS OF EXPERTISE
____________________________________________
TRAINING & INDUSTRY EXPERIENCE
____________________________________________
CONTACT
____________________________________________
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
2

## Slide 4
YOUR TRAINER
About the Trainer
AA
Dr. Alfred Ang
Principal Trainer Tertiary Infotech Academy Pte. Ltd.
ROLE
Principal Trainer, Tertiary Infotech Academy Pte. Ltd.
CERTIFICATION
Industry certified in the subject area of this course.
DELIVERS
Professional short courses for Tertiary Infotech Academy.
FOUNDER
Founder and lead instructor at Tertiary Infotech / Tertiary Courses.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
3

## Slide 5
ICE-BREAKER
Let's Know Each Other
1
Your name and organisation / role.
2
Your experience with this subject (if any).
3
What you want to be able to do after this course.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
4

## Slide 6
HOUSEKEEPING
Ground Rules
1
Set your mobile phone to silent mode.
2
Participate actively — no question is too small.
3
Mutual respect: agree to disagree.
4
One conversation at a time.
5
Be punctual; return from breaks on time.
6
Learn by doing — try every hands-on lab.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
5

## Slide 7
COURSE PORTAL
Download Course Material
1
Sign in at the LMS-TMS portal
▶
2
Open this course from your dashboard
▶
3
Go to the Courseware tab
▶
4
Download the Slides (PPT/PDF), Learner Guide and Lesson Plan
▶
5
Keep them open alongside the labs as you work
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
6
Portal: https://lms-tms.tertiaryinfotech.com

## Slide 8
SCHEDULE
Lesson Plan — 4 Days, 8 hours/day
Day 1
Day 2
• Day 1 — Business Environment & Starting the Project
– Topic 1: Business Environment (Labs 1–4)
– Topic 2: Start the Project (Labs 5–8)
• Day 2 — Planning the Project
– Topic 3: Plan the Project (Labs 9–14)
• Daily timing
– 9:30am–6:30pm · 1-hour lunch · tea breaks within training time
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
7

## Slide 9
WHAT YOU'LL ACHIEVE
Learning Outcomes
1
Scope & Authorise
Scope project requirements and build a business case, charter and traceable scope baseline that authorise delivery.
2
Plan & Baseline
Develop an integrated project plan with realistic schedule, cost and resource baselines using PERT, critical path and reserve analysis.
3
Lead the Team
Lead a project team through its development stages, applying leadership style, motivation theory and structured conflict resolution.
4
Risk & Stakeholders
Analyse project risk quantitatively and engage stakeholders through a planned communication and escalation cadence.
5
Control & Close
Control delivery against baselines with earned value, flow metrics and statistical process control, then close the project and realise benefits.
6
Exam Readiness
Apply the PMI PMP Examination Content Outline (ECO 2026) across all three domains and sit a full-format mock exam with domain score analysis.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
8

## Slide 10
LEARNING APPROACH
How You'll Learn
1
Trainer demonstrates the concept
▶
2
You build it yourself in the hands-on lab
▶
3
Verify with the lab's 'Test it' step
▶
4
Discuss and troubleshoot together
▶
5
Recap against the learning outcomes
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
9

## Slide 11
CORE CONCEPTS
Course Fundamentals
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
10

## Slide 12
OVERVIEW
The PMP Exam at a Glance
1
180 questions, 230 minutes
170 scored plus 10 unscored pretest items, with two 10-minute breaks.
2
Three domains
People 33%, Process 41%, Business Environment 26% — weighted by the ECO 2026.
3
Predictive, agile and hybrid
About 40% predictive; the other 60% splits between adaptive/agile and hybrid.
4
Six question formats
Multiple choice and response, matching, enhanced matching, graphic-based and case study.
5
Scenario-driven, not recall
Almost every item is a situation asking what you do next, not a definition.
6
35 contact hours
This course delivers the 35 hours of project management education PMI requires.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
11

## Slide 13
THE BUILDING BLOCKS
The ECO 2026 Domains
1
People — 33%
Lead, align and communicate with the humans on and around the project.
2
Process — 41%
Plan, deliver, measure and close the work itself.
3
Business Environment — 26%
Connect the project to governance, compliance, risk and change.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
12

## Slide 14
HOW THIS COURSE WORKS
The exam does not ask what you know. It asks what you would do.
Every lab in this course puts you in a scenario, makes you choose, and then shows you why the exam would score that choice the way it does.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
13

## Slide 15
COURSE ROADMAP
What You'll Build
An authorised project
• Environment scan and governance model
• Compliance register
• Business case with NPV and BCR
• Project charter and stakeholder analysis
An integrated plan
• Requirements traceability matrix
• Prioritised backlog and WBS
• Critical path with PERT estimates
• Cost baseline with reserves and a risk register
A controlled delivery
• RACI and communication plan
• Kanban flow metrics
• Earned value analysis and forecasts
• Root cause analysis and control charts
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
14

## Slide 16
THE LEARNING ARC
How Every Lab Progresses
1
Read the scenario and identify which development approach is in play.
2
Work the technique by hand — the exam gives you no spreadsheet.
3
Produce the artifact the next lab will consume.
4
Verify your result against the stated success test.
5
Connect it to the exam: what would the item stem look like, and what is the tell?
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
15

## Slide 17
TOPIC 01
Business Environment
Foundations · governance · compliance · change · development approaches
01
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
16

## Slide 18
KEY CONCEPTS
Key Concepts — Business Environment
1
A project is a temporary endeavour creating a unique product, service or result — it is bounded in time and delivers change, unlike operations.
2
The 12 PMI principles and the triple constraint frame every tailoring decision you make on the exam and on the job.
3
Two life cycles, five approaches: the project life cycle is the phases; the development life cycle is predictive, iterative, incremental, agile or hybrid.
4
EEFs constrain you and OPAs are reusable assets — you conform to EEFs, you apply and then update OPAs.
5
Governance sets escalation thresholds: escalate outside tolerance with options, resolve inside tolerance with the team; phase gates decide go, change, hold or kill.
6
Compliance, sustainability and the responsible use of AI are the project manager's own obligations, not someone else's department.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
17

## Slide 19
WHAT YOU'LL DO
Hands-On Labs — Business Environment
Labs 1–2
• PMP Exam Orientation and 35 PDU Study Plan
• PESTLE and TECOP External Environment Scan
Labs 3–4
• EEF/OPA Inventory, Governance and Escalation Thresholds
• Compliance, Sustainability and AI-Governance Register
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
18

## Slide 20
TOPIC 01 · HANDS-ON
PMP Exam Orientation and 35 PDU Study Plan
LAB 1
Reconstruct the ECO (July 2026) blueprint from its totals - 180 questions, 170 scored, 240 minutes - deriving the per-domain scored counts and the 80-second pacing rule by hand. Catalogue all six question types including graphic-based items, record the 35 contact-hour evidence, and build a six-week study plan weighted to the domain percentages. Test answer-selection heuristics on three Contoso case scenarios.
You'll build
An exam blueprint with derived question counts and pacing figure (artifacts/01-exam-blueprint.md), a 35 contact-hour record (artifacts/01-pdu-log.md), a six-week weighted study plan (artifacts/01-study-plan.md), answer-selection heuristics and a baseline score.
Tools: Spreadsheet, Markdown editor
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
19

## Slide 21
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
1
STEP 1 OF 7
Build the exam blueprint from the ECO 2026 numbers and derive the per-domain scored-question counts
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
20

## Slide 22
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
2
STEP 2 OF 7
Log the six question types and write an approach for each under time pressure
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
21

## Slide 23
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
3
STEP 3 OF 7
Record your 35 contact-hour evidence against the PMP eligibility rule
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
22

## Slide 24
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
4
STEP 4 OF 7
Build a six-week study plan weighted to the blueprint domain percentages
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
23

## Slide 25
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
5
STEP 5 OF 7
Write your answer-selection heuristics: what to eliminate and what to prefer
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
24

## Slide 26
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
6
STEP 6 OF 7
Apply the heuristics to three scenarios, naming the heuristic that decided each
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
25

## Slide 27
LAB 1
PMP Exam Orientation and 35 PDU Study Plan
7
STEP 7 OF 7
Set your baseline score over 20 timed practice questions
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
26

## Slide 28
LAB 1 · VERIFY
PMP Exam Orientation and 35 PDU Study Plan
✅ Test it
The per-domain counts read 56 / 70 / 44 and sum to exactly 170; the pacing figure is 80 seconds per question derived from 240 / 180; the study plan gives Process the largest single hour allocation and contains two full-length timed mocks in the final week; and each scenario answer names a heuristic rather than only a letter.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
27

## Slide 29
TOPIC 01 · HANDS-ON
PESTLE and TECOP External Environment Scan
LAB 2
From the Contoso briefing pack, run a PESTLE scan across all six categories, scoring every factor for impact and likelihood. Run a TECOP scan over the five risk dimensions to surface the operational and political exposure PESTLE misses. Combine and rank both tables, take the vital few scoring 16 or above, and translate each into a scope, backlog or cost consequence with a named destination artifact.
You'll build
A scored six-category PESTLE scan (artifacts/02-pestle-scan.md), a scored five-dimension TECOP scan (artifacts/02-tecop-scan.md), a combined ranked factor table, and a backlog-impact table mapping each top factor to its destination artifact (artifacts/02-backlog-impacts.md).
Tools: PESTLE, TECOP, Mind Mapping
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
28

## Slide 30
LAB 2
PESTLE and TECOP External Environment Scan
1
STEP 1 OF 7
Read the Contoso operating-environment briefing pack
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
29

## Slide 31
LAB 2
PESTLE and TECOP External Environment Scan
2
STEP 2 OF 7
Build and score the PESTLE table, adding at least two factors of your own
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
30

## Slide 32
LAB 2
PESTLE and TECOP External Environment Scan
3
STEP 3 OF 7
Run the TECOP scan across the technical, environmental, commercial, operational and political dimensions
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
31

## Slide 33
LAB 2
PESTLE and TECOP External Environment Scan
4
STEP 4 OF 7
Rank the combined factors and take the vital few scoring 16 or above
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
32

## Slide 34
LAB 2
PESTLE and TECOP External Environment Scan
5
STEP 5 OF 7
Translate each ranked factor into a scope and backlog consequence with a destination artifact
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
33

## Slide 35
LAB 2
PESTLE and TECOP External Environment Scan
6
STEP 6 OF 7
Set the review cadence, owner and out-of-cycle triggers
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
34

## Slide 36
LAB 2
PESTLE and TECOP External Environment Scan
7
STEP 7 OF 7
Answer the exam-style scenarios on responding to external change
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
35

## Slide 37
LAB 2 · VERIFY
PESTLE and TECOP External Environment Scan
✅ Test it
Every PESTLE letter carries at least one factor, every score is the product of a stated impact and likelihood, the TECOP table surfaced at least one factor absent from the PESTLE table, and every factor scoring 16 or above has a named destination artifact in a later lab rather than a vague instruction to monitor.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
36

## Slide 38
TOPIC 01 · HANDS-ON
EEF/OPA Inventory, Governance and Escalation Thresholds
LAB 3
Separate Enterprise Environmental Factors - conditions the project must live with - from Organizational Process Assets, the templates and standards it reuses. Design the Contoso governance model: which body decides what, at which cadence, with what rights. Set numeric escalation thresholds for cost, schedule, risk and issue severity, and separate the change control path from the issue resolution path.
You'll build
A classified EEF/OPA inventory (artifacts/03-eef-opa-inventory.md), a governance model naming decision bodies, rights, cadence and success metrics (artifacts/03-governance-model.md), and a numeric escalation threshold table separating change and issue paths (artifacts/03-escalation-thresholds.md).
Tools: Spreadsheet, Markdown editor
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
37

## Slide 39
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
1
STEP 1 OF 7
Inventory the Contoso Enterprise Environmental Factors
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
38

## Slide 40
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
2
STEP 2 OF 7
Inventory the Contoso Organizational Process Assets
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
39

## Slide 41
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
3
STEP 3 OF 7
Design the governance model: bodies, decision rights and cadence
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
40

## Slide 42
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
4
STEP 4 OF 7
Define the project success metrics and their measurement baselines
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
41

## Slide 43
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
5
STEP 5 OF 7
Set numeric escalation thresholds for cost, schedule, risk and issues
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
42

## Slide 44
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
6
STEP 6 OF 7
Separate the change control path from the issue resolution path
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
43

## Slide 45
LAB 3
EEF/OPA Inventory, Governance and Escalation Thresholds
7
STEP 7 OF 7
Answer the exam-style scenarios on governance and escalation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
44

## Slide 46
LAB 3 · VERIFY
EEF/OPA Inventory, Governance and Escalation Thresholds
✅ Test it
Every item in the inventory is classified as an EEF or an OPA and the learner can justify each classification; each governance body has a named decision right and cadence; every escalation threshold carries a number rather than a word such as significant; and the change path and the issue path are visibly different routes with different owners.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
45

## Slide 47
TOPIC 01 · HANDS-ON
Compliance, Sustainability and AI-Governance Register
LAB 4
Classify Contoso's compliance requirements - PDPA personal-data protection, the statutory seven-year attendance retention obligation and the pre-go-live review - then identify the threats to each and quantify the consequences of noncompliance. Decide the actions and how compliance is measured. Add the two areas the July 2026 ECO expects: net-zero hosting, and AI governance for the deferred AI recommender.
You'll build
A compliance register with threats, consequences, actions and measures (artifacts/04-compliance-register.md), a sustainability plan covering the net-zero hosting obligation (artifacts/04-sustainability-plan.md), and an AI-governance register (artifacts/04-ai-governance.md).
Tools: Spreadsheet, Markdown editor
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
46

## Slide 48
LAB 4
Compliance, Sustainability and AI-Governance Register
1
STEP 1 OF 8
Confirm the compliance requirements and classify them by category
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
47

## Slide 49
LAB 4
Compliance, Sustainability and AI-Governance Register
2
STEP 2 OF 8
Identify the threats to each compliance requirement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
48

## Slide 50
LAB 4
Compliance, Sustainability and AI-Governance Register
3
STEP 3 OF 8
Analyse and quantify the consequences of noncompliance
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
49

## Slide 51
LAB 4
Compliance, Sustainability and AI-Governance Register
4
STEP 4 OF 8
Decide the approach and the specific actions for each requirement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
50

## Slide 52
LAB 4
Compliance, Sustainability and AI-Governance Register
5
STEP 5 OF 8
Define how compliance is measured, with evidence and a measurement owner
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
51

## Slide 53
LAB 4
Compliance, Sustainability and AI-Governance Register
6
STEP 6 OF 8
Build the sustainability section against the group net-zero obligation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
52

## Slide 54
LAB 4
Compliance, Sustainability and AI-Governance Register
7
STEP 7 OF 8
Build the AI-governance register for the deferred AI recommender
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
53

## Slide 55
LAB 4
Compliance, Sustainability and AI-Governance Register
8
STEP 8 OF 8
Answer the exam-style scenarios on compliance decisions
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
54

## Slide 56
LAB 4 · VERIFY
Compliance, Sustainability and AI-Governance Register
✅ Test it
Every compliance requirement has a named threat, a quantified consequence, an action and a measurement method with an owner; the sustainability section ties to a reportable hosting carbon figure; and the AI-governance register records data use, human oversight and an accountable owner rather than a general statement of intent.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
55

## Slide 57
TOPIC RECAP
Recap — Business Environment
1
You can now: Business Env T1 - Define and establish project governance (success metrics)
2
You can now: Business Env T8 - Evaluate external business environment changes; Business Env T7 - Support organizational change
3
You can now: Business Env T1 - Define and establish project governance; Business Env T4 - Remove impediments and manage issues
4
You can now: Business Env T2 - Plan and manage project compliance; Process T7 - Plan and optimize quality (regulatory compliance, sustainability)
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
56

## Slide 58
TOPIC 02
Start the Project
Business case · charter · stakeholders · team formation
02
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
57

## Slide 59
KEY CONCEPTS
Key Concepts — Start the Project
1
The business case justifies the project; the charter authorises it. The business case can exist without a project — the charter cannot.
2
Cost-benefit analysis with NPV, payback and BCR turns a proposal into a defensible investment decision.
3
The charter is issued by the sponsor, names the project manager and states their authority level — it is high level and rarely changed.
4
Stakeholder identification, power/interest analysis and the salience model determine who gets what engagement and how often.
5
The team charter establishes ground rules and a shared vision before the first conflict, not after it.
6
The development approach is a documented tailoring decision justified by project context — never a personal preference.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
58

## Slide 60
WHAT YOU'LL DO
Hands-On Labs — Start the Project
Labs 5–6
• Business Case and Cost-Benefit Analysis
• Project Charter
Labs 7–8
• Stakeholder Register, Power/Interest Grid and Salience Model
• Team Charter, Ground Rules and Shared Vision
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
59

## Slide 61
TOPIC 02 · HANDS-ON
Business Case and Cost-Benefit Analysis
LAB 5
Turn the Contoso baseline metrics into a quantified benefits model, then build the cost side against the board-approved SGD 480,000 ceiling. Compute payback, NPV, ROI and benefit-cost ratio by hand, including the year-zero outflow most commonly dropped from NPV. Stress-test against the Lab 02 downside of an 8% fall in enrolment, then choose among options including a costed do-nothing.
You'll build
A quantified cost-benefit model with payback, NPV, ROI and BCR plus a downside sensitivity run (artifacts/05-cba-model.md), a written business case with a recommendation and its deciding measure (artifacts/05-business-case.md), and a benefits realisation map (artifacts/05-benefits-map.md).
Tools: Statistics, Spreadsheet
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
60

## Slide 62
LAB 5
Business Case and Cost-Benefit Analysis
1
STEP 1 OF 8
Quantify the benefits from the Lab 03 baseline metrics
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
61

## Slide 63
LAB 5
Business Case and Cost-Benefit Analysis
2
STEP 2 OF 8
Build the cost side against the board-approved budget ceiling
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
62

## Slide 64
LAB 5
Business Case and Cost-Benefit Analysis
3
STEP 3 OF 8
Compute payback period, NPV, ROI and benefit-cost ratio by hand
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
63

## Slide 65
LAB 5
Business Case and Cost-Benefit Analysis
4
STEP 4 OF 8
Stress-test the case against the Lab 02 downside enrolment scenario
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
64

## Slide 66
LAB 5
Business Case and Cost-Benefit Analysis
5
STEP 5 OF 8
Choose among the project options, including a costed do-nothing option
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
65

## Slide 67
LAB 5
Business Case and Cost-Benefit Analysis
6
STEP 6 OF 8
Write the business case document with a recommendation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
66

## Slide 68
LAB 5
Business Case and Cost-Benefit Analysis
7
STEP 7 OF 8
Build the benefits realisation map for later closure measurement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
67

## Slide 69
LAB 5
Business Case and Cost-Benefit Analysis
8
STEP 8 OF 8
Answer the exam-style scenarios on value and sunk cost
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
68

## Slide 70
LAB 5 · VERIFY
Business Case and Cost-Benefit Analysis
✅ Test it
Every benefit line traces to a Lab 03 baseline metric; all discount factors fall below 1 and decrease with time; the NPV subtracts the year-zero investment; the BCR is total benefit over total cost and exceeds 1; the do-nothing option carries a negative number rather than a blank; and the recommendation cites NPV as the deciding measure.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
69

## Slide 71
TOPIC 02 · HANDS-ON
Project Charter
LAB 6
Assemble the governance model, compliance requirements and business-case financials into a charter that authorises the project. State success criteria each carrying a numeric baseline and target, and define scope boundaries including exclusions with traceable rationales. Name the PM's procurement and change-approval authority in figures matching the Lab 03 thresholds, and open the assumption log.
You'll build
A project charter with measurable success criteria, scope boundaries, exclusions, milestones, budget and PM authority (artifacts/06-project-charter.md), a development-approach decision (artifacts/06-approach-decision.md) and an assumption log with validation dates (artifacts/06-assumption-log.md).
Tools: Markdown editor, Spreadsheet
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
70

## Slide 72
LAB 6
Project Charter
1
STEP 1 OF 9
Assemble the charter inputs from the governance, compliance and business-case artifacts
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
71

## Slide 73
LAB 6
Project Charter
2
STEP 2 OF 9
Write the charter header and the purpose statement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
72

## Slide 74
LAB 6
Project Charter
3
STEP 3 OF 9
State measurable success criteria with numeric baselines and targets
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
73

## Slide 75
LAB 6
Project Charter
4
STEP 4 OF 9
Define scope boundaries, including exclusions and their rationale
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
74

## Slide 76
LAB 6
Project Charter
5
STEP 5 OF 9
Record the high-level requirements, milestones and budget
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
75

## Slide 77
LAB 6
Project Charter
6
STEP 6 OF 9
Name the project manager's authority in specific procurement and change-approval figures
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
76

## Slide 78
LAB 6
Project Charter
7
STEP 7 OF 9
Document the hybrid development approach as a tailoring decision
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
77

## Slide 79
LAB 6
Project Charter
8
STEP 8 OF 9
Build the assumption and constraint log with validation dates
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
78

## Slide 80
LAB 6
Project Charter
9
STEP 9 OF 9
Answer the exam-style scenarios on charter authority and scope
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
79

## Slide 81
LAB 6 · VERIFY
Project Charter
✅ Test it
Every success criterion carries a numeric baseline and target; the charter has a sponsor signature block; every exclusion has a traceable rationale; the milestone list contains milestones only and no durations; the approach decision names what is predictive, what is adaptive and the interface between them; and every assumption has a validation date before being wrong becomes unrecoverable.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
80

## Slide 82
TOPIC 02 · HANDS-ON
Stakeholder Register, Power/Interest Grid and Salience Model
LAB 7
Identify the full Contoso stakeholder set, including forgotten groups such as the three admin staff who are also subject matter experts. Analyse each on power, interest, attitude and impact, plot the power/interest grid and derive the strategy per quadrant. Where the grid fails, apply the salience model of power, legitimacy and urgency. Build the current-versus-desired engagement matrix and close each gap.
You'll build
A stakeholder register scored on power, interest, attitude and impact (artifacts/07-stakeholder-register.md), a power/interest grid (artifacts/07-power-interest-grid.md), a salience analysis (artifacts/07-salience-model.md) and an engagement matrix (artifacts/07-engagement-matrix.md).
Tools: Power/Interest Grid, Salience Model, Spreadsheet
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
81

## Slide 83
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
1
STEP 1 OF 8
Identify the full stakeholder set, including the groups projects habitually forget
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
82

## Slide 84
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
2
STEP 2 OF 8
Build the stakeholder register with power, interest, attitude and impact
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
83

## Slide 85
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
3
STEP 3 OF 8
Plot the power/interest grid and derive the strategy each quadrant demands
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
84

## Slide 86
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
4
STEP 4 OF 8
Apply the salience model where the grid fails to give a usable answer
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
85

## Slide 87
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
5
STEP 5 OF 8
Build the current-versus-desired engagement matrix
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
86

## Slide 88
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
6
STEP 6 OF 8
Surface and plan to resolve the misaligned stakeholder expectations
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
87

## Slide 89
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
7
STEP 7 OF 8
Set a tailored engagement cadence per stakeholder group
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
88

## Slide 90
LAB 7
Stakeholder Register, Power/Interest Grid and Salience Model
8
STEP 8 OF 8
Answer the exam-style scenarios on stakeholder engagement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
89

## Slide 91
LAB 7 · VERIFY
Stakeholder Register, Power/Interest Grid and Salience Model
✅ Test it
The register includes the three admin staff; every stakeholder has numeric power and interest scores matching their grid position; the salience analysis produced at least one insight the grid did not; every current-to-desired gap has an action with an owner and date; the expectation-conflict plan attaches a trade-off number; and the cadence differs by stakeholder rather than one fortnightly email for everyone.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
90

## Slide 92
TOPIC 02 · HANDS-ON
Team Charter, Ground Rules and Shared Vision
LAB 8
Draft a shared vision short enough to recall without reading it, traced to the Lab 06 success criteria. Build the team charter: name all nine members, write the working agreement on core hours and time zones, and set ground rules across six categories, each with an observable violation test. Agree a definition of done separating done from released, and set the decision rule - consent, consensus or command.
You'll build
A vision statement traced to the charter success criteria (artifacts/08-vision-statement.md), a team charter with the working agreement, definition of done, decision-rule table and skills matrix (artifacts/08-team-charter.md), and six ground-rule categories (artifacts/08-ground-rules.md).
Tools: Team Charter, Definition of Done, Skills Matrix
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
91

## Slide 93
LAB 8
Team Charter, Ground Rules and Shared Vision
1
STEP 1 OF 10
Draft the shared vision statement and test it against the criteria
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
92

## Slide 94
LAB 8
Team Charter, Ground Rules and Shared Vision
2
STEP 2 OF 10
Name the team and record each member's role
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
93

## Slide 95
LAB 8
Team Charter, Ground Rules and Shared Vision
3
STEP 3 OF 10
Write the working agreement on core hours, time zones and availability
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
94

## Slide 96
LAB 8
Team Charter, Ground Rules and Shared Vision
4
STEP 4 OF 10
Set ground rules across the six categories, each with an observable standard
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
95

## Slide 97
LAB 8
Team Charter, Ground Rules and Shared Vision
5
STEP 5 OF 10
Agree the definition of done that QA and the developers will both accept
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
96

## Slide 98
LAB 8
Team Charter, Ground Rules and Shared Vision
6
STEP 6 OF 10
Choose the decision-making rule for each class of decision and name the decider
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
97

## Slide 99
LAB 8
Team Charter, Ground Rules and Shared Vision
7
STEP 7 OF 10
Build the skills and capacity matrix and expose the single points of failure
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
98

## Slide 100
LAB 8
Team Charter, Ground Rules and Shared Vision
8
STEP 8 OF 10
Design the graduated response to ground-rule violations
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
99

## Slide 101
LAB 8
Team Charter, Ground Rules and Shared Vision
9
STEP 9 OF 10
Forward-reference the responsibility assignment matrix and set the vision review cadence
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
100

## Slide 102
LAB 8
Team Charter, Ground Rules and Shared Vision
10
STEP 10 OF 10
Answer the exam-style scenarios on team leadership and ground rules
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
101

## Slide 103
LAB 8 · VERIFY
Team Charter, Ground Rules and Shared Vision
✅ Test it
The vision is under 30 words and traces to at least two numbered charter success criteria; every ground rule has a violation test; the definition of done separates done from released; the decision table uses at least two rules and names a decider for every command-rule row; and the skills matrix identifies at least three single points of failure, each with a named owner and dated mitigation.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
102

## Slide 104
TOPIC RECAP
Recap — Start the Project
1
You can now: Process T3 - Help ensure value-based delivery; Process T6 - Plan and manage finance
2
You can now: Process T1 - Develop an integrated project management plan and plan delivery; Process T2 - Develop and manage project scope
3
You can now: People T4 - Engage stakeholders; People T5 - Align stakeholder expectations; People T6 - Manage stakeholder expectations
4
You can now: People T1 - Develop a common vision; People T3 - Lead the project team
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
103

## Slide 105
TOPIC 03
Plan the Project
Scope · schedule · cost · quality · resources · communications · risk
03
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
104

## Slide 106
KEY CONCEPTS
Key Concepts — Plan the Project
1
The integrated project management plan is the sum of subsidiary plans plus the scope, schedule and cost baselines.
2
Requirements elicitation feeds a requirements traceability matrix so every deliverable traces back to a business need.
3
MoSCoW and Kano prioritise the backlog by value; the WBS decomposes scope to work packages with a WBS dictionary.
4
PERT three-point estimating and critical path analysis expose which activities actually drive the finish date and where float exists.
5
Cost estimating produces a budget with contingency reserve for known unknowns and management reserve for unknown unknowns.
6
Risk identification, qualitative and quantitative analysis with EMV and decision trees produce a risk register with owned responses.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
105

## Slide 107
WHAT YOU'LL DO
Hands-On Labs — Plan the Project
Labs 9–10
• Requirements Elicitation, Mind Mapping and the Traceability Matrix
• MoSCoW, Kano and the Product Backlog
Labs 11–12
• Work Breakdown Structure and WBS Dictionary
• Network Diagram, PERT and the Critical Path
Labs 13–14
• Cost Estimating, Budget and Reserves
• Risk Register, RBS, EMV and Decision Tree
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
106

## Slide 108
TOPIC 03 · HANDS-ON
Requirements Elicitation, Mind Mapping and the Traceability Matrix
LAB 9
Turn the six charter requirements into a testable requirement set. Match elicitation techniques to stakeholder groups rather than defaulting to interviews, then expand them into a mind map. From the map write a 31-line register (REQ-001 to REQ-031) across the business, stakeholder, functional, non-functional, transition and quality categories. Build a bidirectional RTM from source to deliverable and test.
You'll build
A requirements mind map, a 31-requirement register with sourced, prioritised and testable entries, and a bidirectional RTM carrying the 13 compliance requirements to the governance gate - artifacts/09-requirements-mindmap.md, artifacts/09-requirements-register.md and artifacts/09-rtm.md.
Tools: Mind Mapping, Design Thinking (optional)
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
107

## Slide 109
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
1
STEP 1 OF 7
Choose elicitation techniques deliberately, matching each technique to the stakeholder group and noting its weakness
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
108

## Slide 110
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
2
STEP 2 OF 7
Build the requirements mind map in the live Mind Mapping tool from the six charter requirements
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
109

## Slide 111
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
3
STEP 3 OF 7
Write the requirements register across all six categories, with a source, priority and acceptance criterion per line
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
110

## Slide 112
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
4
STEP 4 OF 7
Set requirement attributes and versioning, and define the route by which a baselined requirement changes
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
111

## Slide 113
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
5
STEP 5 OF 7
Build the bidirectional requirements traceability matrix from source through deliverable to test
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
112

## Slide 114
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
6
STEP 6 OF 7
Work through what bidirectional traceability buys you when a requirement is challenged or dropped
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
113

## Slide 115
LAB 9
Requirements Elicitation, Mind Mapping and the Traceability Matrix
7
STEP 7 OF 7
Answer the exam-style scenarios on elicitation choice, requirement quality and traceability
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
114

## Slide 116
LAB 9 · VERIFY
Requirements Elicitation, Mind Mapping and the Traceability Matrix
✅ Test it
Every requirement in the register has a unique ID, a named source, a MoSCoW priority and an acceptance criterion stated as a number or a pass/fail condition; no non-functional requirement is left unmeasurable. Each of the 13 compliance requirements C-01 to C-13 can be traced forward from the RTM to a deliverable and a test, and every requirement traces backward to a charter item or stakeholder.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
115

## Slide 117
TOPIC 03 · HANDS-ON
MoSCoW, Kano and the Product Backlog
LAB 10
Prioritise the Lab 09 requirements with two models that deliberately disagree. Apply MoSCoW under discipline rules - legally required, contractually required, or non-viable without it - to separate Musts from wishes. Classify the same features on Kano as basic, performance, excitement, indifferent or reverse, and resolve each conflict. Write a story backlog in points and a capacity-based release plan.
You'll build
A MoSCoW classification, a Kano classification of 14 features, a 21-plus story backlog with points and traces to REQ IDs, and a capacity-based release plan - artifacts/10-moscow.md, artifacts/10-kano.md, artifacts/10-product-backlog.md and artifacts/10-release-plan.md.
Tools: Scrum Simulator
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
116

## Slide 118
LAB 10
MoSCoW, Kano and the Product Backlog
1
STEP 1 OF 8
Apply MoSCoW to the Lab 09 requirements using the legal, contractual and viability discipline tests
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
117

## Slide 119
LAB 10
MoSCoW, Kano and the Product Backlog
2
STEP 2 OF 8
Classify the features on Kano as basic, performance, excitement, indifferent or reverse
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
118

## Slide 120
LAB 10
MoSCoW, Kano and the Product Backlog
3
STEP 3 OF 8
Examine where MoSCoW and Kano disagree, and resolve each conflict with a stated rule
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
119

## Slide 121
LAB 10
MoSCoW, Kano and the Product Backlog
4
STEP 4 OF 8
Write the product backlog as user stories with acceptance criteria and traces to requirement IDs
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
120

## Slide 122
LAB 10
MoSCoW, Kano and the Product Backlog
5
STEP 5 OF 8
Estimate with story points rather than hours, and justify relative sizing
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
121

## Slide 123
LAB 10
MoSCoW, Kano and the Product Backlog
6
STEP 6 OF 8
Build the release plan against real team capacity and verify the Must-haves land before the gate
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
122

## Slide 124
LAB 10
MoSCoW, Kano and the Product Backlog
7
STEP 7 OF 8
Make the AI recommender trade-off numeric using story points against benefit value
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
123

## Slide 125
LAB 10
MoSCoW, Kano and the Product Backlog
8
STEP 8 OF 8
Answer the exam-style scenarios on prioritisation, value delivery and backlog management
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
124

## Slide 126
LAB 10 · VERIFY
MoSCoW, Kano and the Product Backlog
✅ Test it
Every Must in the MoSCoW list survives the three discipline tests, and no more than the agreed share of total story points sits in Must. The release plan arithmetic reconciles: summed Must-have points divided by measured team velocity fits inside the sprints available before the gate, with the shortfall or slack stated explicitly. Each Kano basic is also a MoSCoW Must.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
125

## Slide 127
TOPIC 03 · HANDS-ON
Work Breakdown Structure and WBS Dictionary
LAB 11
Decompose the Contoso scope into a deliverable-oriented WBS to three levels under the 100% rule, using the 8/80 rule and the estimate-and-assign test to decide when to stop. Every charter in-scope item must appear in the tree, no out-of-scope item anywhere. Write dictionary entries carrying effort in person-days, cost, predecessors, acceptance criteria and a control account, then assemble the scope baseline.
You'll build
A three-level deliverable-oriented WBS, a WBS dictionary with costed and estimated work-package entries, and the assembled scope baseline - artifacts/11-wbs.md, artifacts/11-wbs-dictionary.md and artifacts/11-scope-baseline.md.
Tools: WBS decomposition, 8/80 rule, Rolling wave planning
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
126

## Slide 128
LAB 11
Work Breakdown Structure and WBS Dictionary
1
STEP 1 OF 8
Confirm the inputs and the scope boundary from the charter, register and backlog
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
127

## Slide 129
LAB 11
Work Breakdown Structure and WBS Dictionary
2
STEP 2 OF 8
Build the WBS to three levels, deliverable-oriented, under the 100% rule
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
128

## Slide 130
LAB 11
Work Breakdown Structure and WBS Dictionary
3
STEP 3 OF 8
Trace the compliance workstream back to the environmental factor that created it
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
129

## Slide 131
LAB 11
Work Breakdown Structure and WBS Dictionary
4
STEP 4 OF 8
Write the WBS dictionary entries with effort, cost, predecessors and acceptance criteria
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
130

## Slide 132
LAB 11
Work Breakdown Structure and WBS Dictionary
5
STEP 5 OF 8
Place control accounts and planning packages for the work not yet knowable
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
131

## Slide 133
LAB 11
Work Breakdown Structure and WBS Dictionary
6
STEP 6 OF 8
Assemble the scope baseline and state exactly what it contains
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
132

## Slide 134
LAB 11
Work Breakdown Structure and WBS Dictionary
7
STEP 7 OF 8
Reconcile the WBS with the product backlog so the two do not duplicate each other
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
133

## Slide 135
LAB 11
Work Breakdown Structure and WBS Dictionary
8
STEP 8 OF 8
Answer the exam-style scenarios on decomposition, the 100% rule and baseline control
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
134

## Slide 136
LAB 11 · VERIFY
Work Breakdown Structure and WBS Dictionary
✅ Test it
Roll the work-package effort and cost estimates up each branch and confirm they sum to the level-2 and level-1 totals with no orphan work and no double counting - this is the 100% rule proved arithmetically. Check every charter in-scope item appears exactly once in the tree, that no out-of-scope item appears at all, and that each work package sits inside the 8/80 hour band and can be assigned to one owner.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
135

## Slide 137
TOPIC 03 · HANDS-ON
Network Diagram, PERT and the Critical Path
LAB 12
Convert the Lab 11 work packages into an activity list, sequence them with the four dependency types, and draw the precedence network. Compute the forward and backward pass by hand for early/late start and finish, total and free float, taking the critical path as the zero-float chain. Apply three-point estimating with the triangular and PERT beta formulas, then compare crashing against fast-tracking on cost per day.
You'll build
An activity list, a precedence network, a critical path with float per activity, PERT durations with variance, a costed compression analysis and the schedule baseline - artifacts/12-activity-list.md, artifacts/12-network-diagram.md, artifacts/12-critical-path.md, artifacts/12-schedule-baseline.md.
Tools: PERT, Critical Path Method, Forward and backward pass, Crashing and fast-tracking
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
136

## Slide 138
LAB 12
Network Diagram, PERT and the Critical Path
1
STEP 1 OF 9
Derive the activity list from the WBS work packages, converting deliverables into activities
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
137

## Slide 139
LAB 12
Network Diagram, PERT and the Critical Path
2
STEP 2 OF 9
Understand the dependencies just declared, separating mandatory from discretionary logic
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
138

## Slide 140
LAB 12
Network Diagram, PERT and the Critical Path
3
STEP 3 OF 9
Draw the precedence network diagram with the four dependency types
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
139

## Slide 141
LAB 12
Network Diagram, PERT and the Critical Path
4
STEP 4 OF 9
Compute the forward and backward pass, then total float and free float per activity
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
140

## Slide 142
LAB 12
Network Diagram, PERT and the Critical Path
5
STEP 5 OF 9
Apply three-point estimating with both formulas and compute the project confidence range from variance
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
141

## Slide 143
LAB 12
Network Diagram, PERT and the Critical Path
6
STEP 6 OF 9
Compress the schedule by comparing crashing and fast-tracking on cost per day saved
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
142

## Slide 144
LAB 12
Network Diagram, PERT and the Critical Path
7
STEP 7 OF 9
Apply the lessons-learned constraint that compliance review precedes UAT, and price the parallel alternative
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
143

## Slide 145
LAB 12
Network Diagram, PERT and the Critical Path
8
STEP 8 OF 9
Build the schedule baseline from the accepted network and durations
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
144

## Slide 146
LAB 12
Network Diagram, PERT and the Critical Path
9
STEP 9 OF 9
Answer the exam-style scenarios on float, critical path and compression
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
145

## Slide 147
LAB 12 · VERIFY
Network Diagram, PERT and the Critical Path
✅ Test it
The backward pass must reproduce the forward pass: project late finish equals early finish, and every critical-path activity shows zero total float. Confirm the PERT roll-up - expected duration near 123 days, standard deviation about 4.73 days, a 95.45% range of roughly 113.5 to 132.5 days - by summing critical-path variances. The compression must shorten the critical path, not a float-bearing chain.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
146

## Slide 148
TOPIC 03 · HANDS-ON
Cost Estimating, Budget and Reserves
LAB 13
Select estimating techniques against the information available and state each one's accuracy range, then build a bottom-up estimate from the Lab 11 work packages and reconcile it to the charter budget. Separate contingency from management reserve - who authorises release, which sits in the cost baseline - and size contingency by expected monetary value. Time-phase into a cost baseline S-curve.
You'll build
A bottom-up cost estimate reconciled to the charter, an EMV-sized contingency reserve, a time-phased cost baseline S-curve with the funding requirement above it, and a cost-of-quality analysis - artifacts/13-cost-estimates.md, artifacts/13-cost-baseline.md and artifacts/13-reserve-analysis.md.
Tools: Statistics, Bottom-up estimating, Expected Monetary Value
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
147

## Slide 149
LAB 13
Cost Estimating, Budget and Reserves
1
STEP 1 OF 7
Build the bottom-up estimate from the WBS work packages and reconcile it to the charter budget
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
148

## Slide 150
LAB 13
Cost Estimating, Budget and Reserves
2
STEP 2 OF 7
Distinguish contingency reserve from management reserve, including authority and baseline placement
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
149

## Slide 151
LAB 13
Cost Estimating, Budget and Reserves
3
STEP 3 OF 7
Size the contingency reserve by expected monetary value rather than by percentage
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
150

## Slide 152
LAB 13
Cost Estimating, Budget and Reserves
4
STEP 4 OF 7
Build the time-phased cost baseline as an S-curve
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
151

## Slide 153
LAB 13
Cost Estimating, Budget and Reserves
5
STEP 5 OF 7
Perform funding limit reconciliation against the cash-flow profile
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
152

## Slide 154
LAB 13
Cost Estimating, Budget and Reserves
6
STEP 6 OF 7
Analyse the cost of quality across prevention, appraisal, internal failure and external failure
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
153

## Slide 155
LAB 13
Cost Estimating, Budget and Reserves
7
STEP 7 OF 7
Answer the exam-style scenarios on estimating accuracy, reserves and baseline versus budget
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
154

## Slide 156
LAB 13 · VERIFY
Cost Estimating, Budget and Reserves
✅ Test it
The money must add up both ways: work-package estimates plus contingency equals the cost baseline, and cost baseline plus management reserve equals the total budget. Confirm the EMV sizing by recomputing probability times impact per priced risk. The cumulative S-curve must end at the cost baseline total, and funding limit reconciliation must show no period where planned spend exceeds the authorised tranche.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
155

## Slide 157
TOPIC 03 · HANDS-ON
Risk Register, RBS, EMV and Decision Tree
LAB 14
Build a risk breakdown structure and use it to identify risks systematically, tracing them from the Lab 02 environment scan and the Lab 06 assumption log - every assumption is a latent risk. Write each in cause-event-effect form, then assess the register on a probability/impact matrix and by expected monetary value. Give each a response from the ten strategies and solve a decision tree on EMV.
You'll build
A risk breakdown structure, a risk register with cause-event-effect statements and owners, a plotted probability/impact matrix, a full EMV analysis and a solved decision tree - artifacts/14-risk-register.md, artifacts/14-rbs.md, artifacts/14-pi-matrix.md and artifacts/14-emv-analysis.md.
Tools: System Thinking, EMV, Decision Tree, Probability/Impact Matrix
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
156

## Slide 158
LAB 14
Risk Register, RBS, EMV and Decision Tree
1
STEP 1 OF 10
Build the risk breakdown structure and use it to drive systematic identification
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
157

## Slide 159
LAB 14
Risk Register, RBS, EMV and Decision Tree
2
STEP 2 OF 10
Trace risks from the Lab 02 PESTLE/TECOP factors and the Lab 06 assumption log
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
158

## Slide 160
LAB 14
Risk Register, RBS, EMV and Decision Tree
3
STEP 3 OF 10
Write risk statements in cause-event-effect form
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
159

## Slide 161
LAB 14
Risk Register, RBS, EMV and Decision Tree
4
STEP 4 OF 10
Build the risk register with probability, impact, owner and trigger per risk
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
160

## Slide 162
LAB 14
Risk Register, RBS, EMV and Decision Tree
5
STEP 5 OF 10
Plot the probability/impact matrix and rank the risks by score
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
161

## Slide 163
LAB 14
Risk Register, RBS, EMV and Decision Tree
6
STEP 6 OF 10
Apply all ten response strategies - five for threats and five for opportunities
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
162

## Slide 164
LAB 14
Risk Register, RBS, EMV and Decision Tree
7
STEP 7 OF 10
Compute expected monetary value for each priced risk and for the portfolio
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
163

## Slide 165
LAB 14
Risk Register, RBS, EMV and Decision Tree
8
STEP 8 OF 10
Build and solve a decision tree for a real Contoso decision and defend the recommendation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
164

## Slide 166
LAB 14
Risk Register, RBS, EMV and Decision Tree
9
STEP 9 OF 10
Distinguish qualitative from quantitative analysis, and a risk from an issue
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
165

## Slide 167
LAB 14
Risk Register, RBS, EMV and Decision Tree
10
STEP 10 OF 10
Answer the exam-style scenarios on response strategy selection, EMV and secondary risk
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
166

## Slide 168
LAB 14 · VERIFY
Risk Register, RBS, EMV and Decision Tree
✅ Test it
Recompute each risk's EMV as probability times impact, summing threats and opportunities separately - the net portfolio EMV must reconcile with the contingency reserve sized in Lab 13. Solve the decision tree by rolling values back from the leaves; the recommended branch must have the highest expected value net of cost. Every register row carries an owner, a trigger and one of the ten strategies.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
167

## Slide 169
TOPIC RECAP
Recap — Plan the Project
1
You can now: Process T2 - Develop and manage project scope; Process T1 - Develop an integrated project management plan.
2
You can now: Process T3 - Help ensure value-based delivery; Process T2 - Develop and manage project scope.
3
You can now: Process T2 - Develop and manage project scope (break down scope); Process T1 - Develop an integrated project management plan.
4
You can now: Process T8 - Plan and manage schedule.
5
You can now: Process T6 - Plan and manage finance; Process T1 - Develop an integrated project management plan.
6
You can now: Business Environment T5 - Plan and manage risk; Business Environment T4 - Support organisational change.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
168

## Slide 170
TOPIC 04
Lead the Project Team
Leadership · motivation · conflict · coaching · communication
04
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
169

## Slide 171
KEY CONCEPTS
Key Concepts — Lead the Project Team
1
Tuckman's forming, storming, norming, performing and adjourning gives you a diagnosis, and each stage calls for a different leadership response.
2
Situational leadership, servant leadership and motivation theory (Maslow, Herzberg, McClelland, Theory X/Y) drive team performance.
3
RACI removes ambiguity: exactly one Accountable per work package, Responsible parties who do the work.
4
The five conflict modes — collaborate, compromise, smooth, force, withdraw — are chosen by context; collaborate/problem-solve is preferred.
5
The channels formula n(n-1)/2 shows why communication complexity grows faster than team size.
6
A communication plan defines who needs what information, in what format, how often, and through which channel.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
170

## Slide 172
WHAT YOU'LL DO
Hands-On Labs — Lead the Project Team
Labs 15–16
• RACI Responsibility Assignment Matrix and Resource Plan
• Tuckman Diagnosis, Motivation Theory and Leadership Style
Labs 17–18
• Conflict Resolution: Five Modes, Leas' Levels and Negotiation
• Communication Plan, Channels and Status Reporting
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
171

## Slide 173
TOPIC 04 · HANDS-ON
RACI Responsibility Assignment Matrix and Resource Plan
LAB 15
Build a RACI matrix from the Lab 11 WBS work packages, defending every assignment against the one-accountable rule. The supplied draft carries five deliberate defects - missing accountability, two accountables on a row, over-consultation, an unassigned role and an unowned work package - which you audit out and fix. Build the resource histogram and distinguish levelling from smoothing.
You'll build
A defect-free RACI matrix over the WBS work packages, a documented audit of the five structural defects with fixes, and a resource plan with a levelled histogram - artifacts/15-raci-matrix.md, artifacts/15-resource-plan.md and artifacts/15-raci-issues.md.
Tools: RACI Matrix
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
172

## Slide 174
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
1
STEP 1 OF 9
Assemble the inputs from the WBS dictionary, team charter and stakeholder register
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
173

## Slide 175
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
2
STEP 2 OF 9
Draft the matrix, accepting that the supplied draft contains deliberate defects
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
174

## Slide 176
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
3
STEP 3 OF 9
Enter the matrix in the live RACI Matrix tool
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
175

## Slide 177
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
4
STEP 4 OF 9
Audit the matrix and find the five structural defects
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
176

## Slide 178
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
5
STEP 5 OF 9
Compare before and after in numbers, counting assignments per row and per role
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
177

## Slide 179
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
6
STEP 6 OF 9
Build the resource plan and the resource histogram
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
178

## Slide 180
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
7
STEP 7 OF 9
Level or smooth the over-allocation, and state which technique can move the critical path
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
179

## Slide 181
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
8
STEP 8 OF 9
Connect the RACI to the communication plan so the C and I entries drive the distribution list
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
180

## Slide 182
LAB 15
RACI Responsibility Assignment Matrix and Resource Plan
9
STEP 9 OF 9
Answer the exam-style scenarios on accountability, over-consultation and levelling versus smoothing
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
181

## Slide 183
LAB 15 · VERIFY
RACI Responsibility Assignment Matrix and Resource Plan
✅ Test it
Audit the corrected matrix row by row and column by column: every work-package row shows exactly one A and at least one R, no row is empty, and no role column is empty. Compare the histogram before and after: levelling must remove every allocation above 100%, and the learner must state whether the end date moved (levelling) or held (smoothing).
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
182

## Slide 184
TOPIC 04 · HANDS-ON
Tuckman Diagnosis, Motivation Theory and Leadership Style
LAB 16
Diagnose the team's Tuckman stage from the sprint 3 behavioural evidence rather than elapsed time, naming structural causes not personalities, then select the leader actions that move a team out of storming. Apply six motivation theories - Maslow, Herzberg, McGregor, McClelland, Vroom and Self-Determination - for one action each. Compute a Vroom score as expectancy times instrumentality times valence.
You'll build
A Tuckman diagnosis with structural causes and leader actions, per-member motivation profiles with one action from each of the six theories, and a leadership style map - artifacts/16-tuckman-diagnosis.md, artifacts/16-motivation-plan.md and artifacts/16-leadership-style-plan.md.
Tools: Tuckman model, Situational Leadership, Vroom Expectancy calculation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
183

## Slide 185
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
1
STEP 1 OF 8
Read the sprint 3 evidence and record the observed behaviours without interpreting them yet
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
184

## Slide 186
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
2
STEP 2 OF 8
Diagnose the Tuckman stage and name the structural causes behind it
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
185

## Slide 187
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
3
STEP 3 OF 8
Choose the leader actions that move a team out of storming
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
186

## Slide 188
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
4
STEP 4 OF 8
Apply the six motivation theories, producing one specific action from each
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
187

## Slide 189
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
5
STEP 5 OF 8
Build per-member motivation profiles, computing the Vroom expectancy score numerically
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
188

## Slide 190
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
6
STEP 6 OF 8
Map a situational leadership style to each member's competence and commitment
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
189

## Slide 191
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
7
STEP 7 OF 8
Distinguish servant leadership from laissez-faire behaviourally and by outcome
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
190

## Slide 192
LAB 16
Tuckman Diagnosis, Motivation Theory and Leadership Style
8
STEP 8 OF 8
Answer the exam-style scenarios on stage diagnosis, Herzberg and style selection
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
191

## Slide 193
LAB 16 · VERIFY
Tuckman Diagnosis, Motivation Theory and Leadership Style
✅ Test it
The diagnosis cites at least three observed sprint 3 behaviours and does not rest on how long the team has existed. Each Vroom score is computed as expectancy times instrumentality times valence, with the lowest factor identified as the one to fix - a low score with high valence and instrumentality points at expectancy - and the action must target that factor. Every member carries a different style justification.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
192

## Slide 194
TOPIC 04 · HANDS-ON
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
LAB 17
Place the five conflict-handling modes on the assertiveness and cooperativeness axes, state each one's legitimate use, and identify the cases where collaborate - usually the keyed answer - is wrong. Diagnose intensity on Leas' five levels from the language people use. Run four Contoso role-plays, recording each in a conflict log. Close on negotiation: positions versus interests, BATNA and ZOPA.
You'll build
A conflict log recording level, mode, intervention and outcome per incident, observer notes and debriefs for the four role-plays, and a resolution plan with a BATNA and ZOPA analysis - artifacts/17-conflict-log.md, artifacts/17-roleplay-notes.md and artifacts/17-resolution-plan.md.
Tools: Thomas-Kilmann five modes, Leas' Levels, BATNA and ZOPA analysis
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
193

## Slide 195
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
1
STEP 1 OF 8
Build the conflict log with columns for level, mode, intervention and outcome
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
194

## Slide 196
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
2
STEP 2 OF 8
Run role-play 1: two developers on architecture at Leas' level 1 to 2
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
195

## Slide 197
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
3
STEP 3 OF 8
Run role-play 2: Head of Sales versus product owner on scope at level 3
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
196

## Slide 198
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
4
STEP 4 OF 8
Run role-play 3: QA lead versus dev lead on the definition of done at level 2 to 3
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
197

## Slide 199
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
5
STEP 5 OF 8
Run role-play 4: admin staff versus Ops Manager on redundancy, escalating and high emotion
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
198

## Slide 200
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
6
STEP 6 OF 8
Build the resolution plan from the four logged conflicts
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
199

## Slide 201
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
7
STEP 7 OF 8
Apply negotiation: separate positions from interests, and compute BATNA and ZOPA
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
200

## Slide 202
LAB 17
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
8
STEP 8 OF 8
Answer the exam-style scenarios on mode selection and escalation thresholds
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
201

## Slide 203
LAB 17 · VERIFY
Conflict Resolution: Five Modes, Leas' Levels and Negotiation
✅ Test it
Every conflict log row names a Leas' level, the mode chosen, and why that mode beat collaborate - a level 4 or 5 entry that still selects collaborate is a failed diagnosis. The negotiation analysis states each party's BATNA explicitly and shows the ZOPA as a numeric range between the two reservation points, or states that no ZOPA exists and no deal is available.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
202

## Slide 204
TOPIC 04 · HANDS-ON
Communication Plan, Channels and Status Reporting
LAB 18
Compute the communication channels with N(N-1)/2 and derive the implication of its superlinear growth. Select push, pull or interactive per stakeholder, place communications in the formal/informal by written/verbal grid, and build a plan where every row carries a feedback loop. Write the week-14 status three ways for three audiences, noticing that a CPI of 0.919 breaches the governance threshold.
You'll build
A communication plan with computed channel counts, a push/pull/interactive assignment and a named feedback loop per stakeholder row, plus three audience-specific week-14 status reports written from one set of numbers - artifacts/18-communication-plan.md and artifacts/18-status-reports.md.
Tools: N(N-1)/2 channels formula, Sender-receiver model, Status reporting
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
203

## Slide 205
LAB 18
Communication Plan, Channels and Status Reporting
1
STEP 1 OF 9
Compute the communication channels with N(N-1)/2 and derive the growth implication
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
204

## Slide 206
LAB 18
Communication Plan, Channels and Status Reporting
2
STEP 2 OF 9
Choose push, pull or interactive for each stakeholder and justify the choice
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
205

## Slide 207
LAB 18
Communication Plan, Channels and Status Reporting
3
STEP 3 OF 9
Place communications in the formal/informal by written/verbal grid
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
206

## Slide 208
LAB 18
Communication Plan, Channels and Status Reporting
4
STEP 4 OF 9
Build the communication plan with a named feedback loop on every row
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
207

## Slide 209
LAB 18
Communication Plan, Channels and Status Reporting
5
STEP 5 OF 9
Trace a message through the sender-receiver model and name the real noise sources
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
208

## Slide 210
LAB 18
Communication Plan, Channels and Status Reporting
6
STEP 6 OF 9
Work through the week-14 status data and compute the performance indices
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
209

## Slide 211
LAB 18
Communication Plan, Channels and Status Reporting
7
STEP 7 OF 9
Write the same status three ways for three different audiences from one set of numbers
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
210

## Slide 212
LAB 18
Communication Plan, Channels and Status Reporting
8
STEP 8 OF 9
Compare a bad status report with a good one and name what makes the difference
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
211

## Slide 213
LAB 18
Communication Plan, Channels and Status Reporting
9
STEP 9 OF 9
Answer the exam-style scenarios on channels, communication method and escalation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
212

## Slide 214
LAB 18 · VERIFY
Communication Plan, Channels and Status Reporting
✅ Test it
Recompute N(N-1)/2 before and after the proposed additions and confirm the channel count grows superlinearly - state the delta, not just the totals. Every plan row names a sender, audience, method, frequency and feedback loop. The three status reports reconcile to identical figures despite differing in emphasis, and the CPI of 0.919 is flagged against the governance cost variance threshold with the escalation named.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
213

## Slide 215
TOPIC RECAP
Recap — Lead the Project Team
1
You can now: People T3 - Lead the project team (establish clear roles and responsibilities within the team); Process T4 - Plan and manage resources.
2
You can now: People T3 - Lead the project team; People T1 - Develop a common vision.
3
You can now: People T2 - Manage conflicts.
4
You can now: People T8 - Plan and manage communication; People T4 - Engage stakeholders.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
214

## Slide 216
TOPIC 05
Monitor and Control the Project
Earned value · flow metrics · quality control · change control · issues
05
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
215

## Slide 217
KEY CONCEPTS
Key Concepts — Monitor and Control the Project
1
Earned value management combines scope, schedule and cost into CPI, SPI, EAC and VAC — it tells you THAT something is wrong, not why.
2
Schedule compression is a choice between crashing (adds cost) and fast-tracking (adds risk); both must be justified against the baseline.
3
Kanban flow metrics — WIP limits, lead time and cycle time — expose bottlenecks that a Gantt chart hides.
4
Root cause analysis with 5 Whys, fishbone and Pareto finds the vital few causes behind most of the pain.
5
Statistical process control separates assignable causes from common-cause noise, and a stable process can still fail its specification.
6
Integrated change control evaluates every change against all baselines before approval — the change control board decides, the PM does not.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
216

## Slide 218
WHAT YOU'LL DO
Hands-On Labs — Monitor and Control the Project
Labs 19–20
• Kanban Board with WIP Limits and Lead/Cycle Time
• Earned Value Management and Schedule Compression
Labs 21–22
• Root Cause Analysis with 5 Whys, Fishbone and Pareto
• SPC Control Chart and Statistical Process Analysis
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
217

## Slide 219
TOPIC 05 · HANDS-ON
Kanban Board with WIP Limits and Lead/Cycle Time
LAB 19
Build a nine-column Kanban board mirroring Contoso's workflow, separating active from queue columns so waiting time becomes visible. Set a justified WIP limit per column, load 18 story cards with backlog-entry, work-start and acceptance dates, and compute lead time, cycle time, throughput and flow efficiency. Apply Little's Law, then find the bottleneck and apply the five Theory of Constraints steps.
You'll build
artifacts/19-kanban-board.md with the nine-column workflow and WIP limits; artifacts/19-flow-metrics.md with lead and cycle time, throughput, flow efficiency and the Little's Law verification; artifacts/19-bottleneck-analysis.md with the utilisation table and Theory of Constraints response.
Tools: Kanban Board
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
218

## Slide 220
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
1
STEP 1 OF 8
Design the workflow columns, separating active stages from queue stages
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
219

## Slide 221
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
2
STEP 2 OF 8
Set and justify a WIP limit for every column against the team composition
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
220

## Slide 222
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
3
STEP 3 OF 8
Load the 18 real cards with backlog-entry, work-start and acceptance dates
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
221

## Slide 223
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
4
STEP 4 OF 8
Compute the flow metrics - lead time, cycle time, throughput and flow efficiency
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
222

## Slide 224
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
5
STEP 5 OF 8
Apply Little's Law to verify stability and forecast the remaining release
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
223

## Slide 225
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
6
STEP 6 OF 8
Find the bottleneck from column utilisation and apply the Theory of Constraints steps
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
224

## Slide 226
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
7
STEP 7 OF 8
Read the cumulative flow diagram and interpret band width, slope and convergence
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
225

## Slide 227
LAB 19
Kanban Board with WIP Limits and Lead/Cycle Time
8
STEP 8 OF 8
Answer the exam-style scenarios on Little's Law, WIP limits and lead versus cycle time
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
226

## Slide 228
LAB 19 · VERIFY
Kanban Board with WIP Limits and Lead/Cycle Time
✅ Test it
Mean lead time comes to 13.11 days against a mean cycle time of 6.94 days, a flow efficiency of 52.9%; Little's Law implies a WIP of about 6.25 against an observed 6 on day 12; Test is the bottleneck on its 100% utilisation, the 97% queue in front of it and the collapse to 33% downstream; and the learner rejects raising the In Test WIP limit, explaining why it would lengthen cycle time.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
227

## Slide 229
TOPIC 05 · HANDS-ON
Earned Value Management and Schedule Compression
LAB 20
From the SGD 480,000 Contoso cost baseline, validate that cumulative planned value at the final period equals BAC, then compute CV, SV, CPI and SPI at the week-14 status date. Calculate all three EAC variants, choose the defensible one on evidence, and derive ETC, VAC and both TCPI figures. Analyse the seven-period CPI/SPI trend and choose between crashing and fast-tracking from the crash-cost table.
You'll build
artifacts/20-evm-calculations.md with CV, SV, CPI and SPI plus the seven-period trend table; artifacts/20-forecast.md with all three EAC variants, ETC, VAC and both TCPI figures; artifacts/20-compression-decision.md with the five-day crash recovery, its cost and the rejection of fast-tracking.
Tools: Statistics
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
228

## Slide 230
LAB 20
Earned Value Management and Schedule Compression
1
STEP 1 OF 8
Take the cost baseline and actuals, and validate that cumulative PV equals BAC
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
229

## Slide 231
LAB 20
Earned Value Management and Schedule Compression
2
STEP 2 OF 8
Compute the variances and indices at week 14 - CV, SV, CPI and SPI
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
230

## Slide 232
LAB 20
Earned Value Management and Schedule Compression
3
STEP 3 OF 8
Forecast the outcome with all three EAC variants, plus ETC, VAC and TCPI
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
231

## Slide 233
LAB 20
Earned Value Management and Schedule Compression
4
STEP 4 OF 8
Analyse the seven-period CPI/SPI trend rather than the single snapshot
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
232

## Slide 234
LAB 20
Earned Value Management and Schedule Compression
5
STEP 5 OF 8
Check the result against the escalation thresholds and decide whether to escalate
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
233

## Slide 235
LAB 20
Earned Value Management and Schedule Compression
6
STEP 6 OF 8
Decide between crashing and fast-tracking using the crash-cost table
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
234

## Slide 236
LAB 20
Earned Value Management and Schedule Compression
7
STEP 7 OF 8
Write the variance report in sponsor format with three costed options and a recommendation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
235

## Slide 237
LAB 20
Earned Value Management and Schedule Compression
8
STEP 8 OF 8
Answer the exam-style scenarios on EAC selection, EVM reading and trend interpretation
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
236

## Slide 238
LAB 20 · VERIFY
Earned Value Management and Schedule Compression
✅ Test it
Cumulative PV at period 12 equals SGD 480,000; CV = -22,000 and SV = -19,000 are in dollars not days; CPI = 0.919 and SPI = 0.929, CPI carried to four decimals into EAC = SGD 522,420 and VAC = -SGD 42,420; the TCPI of 1.105 against CPI 0.919 makes recovery not credible; the crash selects J and O for SGD 15,500, rejecting non-critical F; and escalation is raised on the forecast, not the actual variance.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
237

## Slide 239
TOPIC 05 · HANDS-ON
Root Cause Analysis with 5 Whys, Fishbone and Pareto
LAB 21
Take the defect log for sprints 1 to 7 - the period over which CPI declined monotonically - and run the three root cause tools in sequence. Pareto on defect frequency isolates the vital few inside the 80% cut; a second Pareto by rework hours reveals where frequency and cost disagree. A fishbone generates causes across the six categories, and 5 Whys drives from symptom to root cause, verified with the removal test.
You'll build
artifacts/21-pareto-analysis.md with the frequency and cost rankings and cumulative percentages; artifacts/21-fishbone.md with two causes per category; artifacts/21-5whys.md with the causal chain; artifacts/21-corrective-actions.md separating corrective from preventive action.
Tools: Pareto Chart, Fishbone Diagram, 5 Whys
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
238

## Slide 240
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
1
STEP 1 OF 8
Take the defect data covering sprints 1 to 7 with counts, rework hours and cost
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
239

## Slide 241
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
2
STEP 2 OF 8
Build the Pareto chart on defect frequency and locate the 80% cut
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
240

## Slide 242
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
3
STEP 3 OF 8
Re-run Pareto by rework cost and notice where the two rankings disagree
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
241

## Slide 243
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
4
STEP 4 OF 8
Fishbone the top category across all six cause categories
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
242

## Slide 244
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
5
STEP 5 OF 8
Drive from symptom to root cause with 5 Whys
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
243

## Slide 245
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
6
STEP 6 OF 8
Verify the root cause with the therefore test and the removal test before acting
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
244

## Slide 246
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
7
STEP 7 OF 8
Design corrective, preventive and defect-repair actions and assign owners
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
245

## Slide 247
LAB 21
Root Cause Analysis with 5 Whys, Fishbone and Pareto
8
STEP 8 OF 8
Answer the exam-style scenarios on root cause versus symptom and action type
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
246

## Slide 248
LAB 21 · VERIFY
Root Cause Analysis with 5 Whys, Fishbone and Pareto
✅ Test it
Cumulative percentages reach 100% with the 80% cut at rank 5 on 81.55%; both Pareto runs rank acceptance criteria and browser compatibility first and second; every fishbone category carries two causes; the root cause is a system or process failure rather than an individual's shortcoming and passes the removal test; and the causal chain connects it back to the CPI decline found by earned value analysis.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
247

## Slide 249
TOPIC 05 · HANDS-ON
SPC Control Chart and Statistical Process Analysis
LAB 22
Plot 20 daily measurements of median registration completion time and compute the centre line and control limits from the data itself, using the moving-range method rather than the sample standard deviation. Apply the out-of-control rules including the rule of seven and identify where the process shifts. Separate common from assignable cause, then assess capability - the process is in control yet fails specification.
You'll build
artifacts/22-control-chart.md with the individuals chart, centre line and control limits; artifacts/22-stability-verdict.md with the rule-by-rule out-of-control analysis and the named assignable cause; artifacts/22-capability-summary.md with the capability indices against the charter target.
Tools: SPC / Control Chart, Statistics
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
248

## Slide 250
LAB 22
SPC Control Chart and Statistical Process Analysis
1
STEP 1 OF 8
Take the 20 daily measurements of median registration completion time
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
249

## Slide 251
LAB 22
SPC Control Chart and Statistical Process Analysis
2
STEP 2 OF 8
Compute the centre line and control limits from the moving ranges
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
250

## Slide 252
LAB 22
SPC Control Chart and Statistical Process Analysis
3
STEP 3 OF 8
Plot the individuals chart against the computed limits
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
251

## Slide 253
LAB 22
SPC Control Chart and Statistical Process Analysis
4
STEP 4 OF 8
Apply the out-of-control rules, including the rule of seven, run by run
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
252

## Slide 254
LAB 22
SPC Control Chart and Statistical Process Analysis
5
STEP 5 OF 8
Separate common cause from assignable cause and decide the response to each
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
253

## Slide 255
LAB 22
SPC Control Chart and Statistical Process Analysis
6
STEP 6 OF 8
Assess capability against the charter success criterion and distinguish control from specification limits
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
254

## Slide 256
LAB 22
SPC Control Chart and Statistical Process Analysis
7
STEP 7 OF 8
Write the quality verdict and the corrective actions
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
255

## Slide 257
LAB 22
SPC Control Chart and Statistical Process Analysis
8
STEP 8 OF 8
Answer the exam-style scenarios on tampering, signals and capability
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
256

## Slide 258
LAB 22 · VERIFY
SPC Control Chart and Statistical Process Analysis
✅ Test it
The centre line comes to 4.053 with MR-bar 0.3286, sigma 0.2913 and limits of 3.179 and 4.927, computed from the stable period not all 20 points; sigma is MR-bar divided by 1.128; the rule of seven is checked on days 1 to 15, longest run 2; days 16 to 20 are assignable cause with a dated explanation matching the shift; and the negative Cpk leads to re-centring rather than tightening.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
257

## Slide 259
TOPIC RECAP
Recap — Monitor and Control the Project
1
You can now: Process T9 - Evaluate project status; Business Environment T4 - Remove impediments and manage issues.
2
You can now: Process T9 - Evaluate project status; Process T6 - Plan and manage budget and resources.
3
You can now: Business Environment T4 - Remove impediments and manage issues; Process T7 - Plan and manage quality of products and deliverables; Business Environment T6 - Support continuous improvement.
4
You can now: Process T7 - Plan and manage quality of products and deliverables; Process T9 - Evaluate project status.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
258

## Slide 260
TOPIC 06
Close the Project
Acceptance · transition · benefits realisation · lessons learned · exam strategy
06
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
259

## Slide 261
KEY CONCEPTS
Key Concepts — Close the Project
1
Closure requires formal stakeholder acceptance against documented criteria, not merely the end of the work.
2
Transition readiness moves the deliverable to operations with the support, documentation and training that make it sustainable.
3
Benefits realisation is measured after go-live against the business case — the project ends, the benefits do not.
4
Lessons learned only count when they update an organisational process asset that the next project inherits.
5
Knowledge transfer protects the organisation from the loss of the team that built the thing.
6
Exam strategy: read the last sentence first, identify the development approach in play, and eliminate answers that bypass the process.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
260

## Slide 262
WHAT YOU'LL DO
Hands-On Labs — Close the Project
Lab 23
• Project Closure, Benefits Realisation and Lessons Learned
Lab 24
• Capstone - Integrated Project Management Plan and Mock Exam
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
261

## Slide 263
TOPIC 06 · HANDS-ON
Project Closure, Benefits Realisation and Lessons Learned
LAB 23
Close the Contoso project against the four closure enablers. Define closure criteria first, run Control Quality against specification before seeking acceptance through Validate Scope, then validate operational readiness. Write the final report against all eight charter success criteria - including the one missed - and reconcile the final cost. Hand every benefit to a named owner with a post-closure review date.
You'll build
artifacts/23-closure-checklist.md separating procurement from administrative closure; artifacts/23-final-report.md with the eight criteria and cost reconciliation; artifacts/23-lessons-learned.md; artifacts/23-benefits-realisation.md handing B1 to B4 to named owners; artifacts/23-transition-plan.md.
Tools: Closure checklist, Benefits realisation register, Lessons learned register
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
262

## Slide 264
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
1
STEP 1 OF 9
Define the closure criteria before closing anything
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
263

## Slide 265
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
2
STEP 2 OF 9
Verify scope with Control Quality before seeking acceptance
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
264

## Slide 266
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
3
STEP 3 OF 9
Obtain formal acceptance from the customer through Validate Scope
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
265

## Slide 267
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
4
STEP 4 OF 9
Validate readiness for transition to operations
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
266

## Slide 268
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
5
STEP 5 OF 9
Write the final report against all eight charter success criteria
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
267

## Slide 269
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
6
STEP 6 OF 9
Hand over the benefits to named owners with review dates beyond project end
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
268

## Slide 270
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
7
STEP 7 OF 9
Capture lessons learned that each update a named organisational process asset
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
269

## Slide 271
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
8
STEP 8 OF 9
Plan the knowledge transfer and release the team
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
270

## Slide 272
LAB 23
Project Closure, Benefits Realisation and Lessons Learned
9
STEP 9 OF 9
Answer the exam-style scenarios on closure sequence, acceptance and benefits ownership
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
271

## Slide 273
LAB 23 · VERIFY
Project Closure, Benefits Realisation and Lessons Learned
✅ Test it
Control Quality verifies against specification first, Validate Scope obtains acceptance second; the checklist separates procurement from administrative closure; SC-2 is reported NOT MET with its consequence quantified as a SGD 42,529 annual benefit shortfall; the final cost reconciles to SGD 478,900 with contingency closing at zero exposure; and every benefit B1 to B4 has a named owner who is not the project manager.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
272

## Slide 274
TOPIC 06 · HANDS-ON
Capstone - Integrated Project Management Plan and Mock Exam
LAB 24
Part A assembles twenty-three labs of artifacts into one integrated project management plan: a component index mapping all 25 components to the lab that produced each, the three baselines and the PMB accounted separately, and a twenty-assertion consistency audit. Part B is a 30-question mock practice exam in ECO 2026 format under a 40-minute timer, scored by domain against the published weights.
You'll build
artifacts/24-project-management-plan.md with the component index and twenty-assertion audit; artifacts/24-mock-exam-answers.md with all 30 answers recorded before the key was read; artifacts/24-score-analysis.md; artifacts/24-exam-readiness-plan.md with a dated plan for every domain below 70%.
Tools: Project management plan index, Consistency audit, Mock practice exam, Score analysis
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
273

## Slide 275
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
1
STEP 1 OF 9
Build the plan index mapping all 25 components to the lab and artifact that produced each
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
274

## Slide 276
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
2
STEP 2 OF 9
Account for the three baselines and the performance measurement baseline separately
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
275

## Slide 277
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
3
STEP 3 OF 9
Run the twenty-assertion consistency audit and record every discrepancy found
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
276

## Slide 278
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
4
STEP 4 OF 9
Prepare the five-minute executive presentation outline with timings per slide
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
277

## Slide 279
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
5
STEP 5 OF 9
Sit the 30-question mock practice exam in ECO 2026 format under a 40-minute timer
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
278

## Slide 280
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
6
STEP 6 OF 9
Score the mock practice exam by domain against the 33/41/26 weights
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
279

## Slide 281
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
7
STEP 7 OF 9
Separate confident correct answers from flagged guesses and identify the weakest domain
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
280

## Slide 282
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
8
STEP 8 OF 9
Write the remediation plan naming specific labs, ECO tasks, a dated action and a re-test date
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
281

## Slide 283
LAB 24
Capstone - Integrated Project Management Plan and Mock Exam
9
STEP 9 OF 9
Complete the exam-day readiness checklist covering eligibility, pacing and answer selection
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
282

## Slide 284
LAB 24 · VERIFY
Capstone - Integrated Project Management Plan and Mock Exam
✅ Test it
The plan index accounts for the three baselines plus the PMB, and the learner explains why management reserve requires a baseline change while contingency does not; the audit PV sum comes to SGD 480,000 with at least one genuine discrepancy recorded; the mock exam was taken in 40 minutes without looking at the key; and per-domain scores are compared against 33%, 41% and 26%.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
283

## Slide 285
TOPIC RECAP
Recap — Close the Project
1
You can now: Process T10 - Manage project closure and transitions; Business Environment T6 - Support organizational change and continuous improvement; People T7 - Help ensure knowledge transfer.
2
You can now: All domains - People, Process and Business Environment across the full ECO 2026 task list.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
284

## Slide 286
WRAP-UP
Course Summary & Next Steps
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
285

## Slide 287
LEARNING OUTCOMES
What You Achieved
1
Scope & Authorise
Scope project requirements and build a business case, charter and traceable scope baseline that authorise delivery.
2
Plan & Baseline
Develop an integrated project plan with realistic schedule, cost and resource baselines using PERT, critical path and reserve analysis.
3
Lead the Team
Lead a project team through its development stages, applying leadership style, motivation theory and structured conflict resolution.
4
Risk & Stakeholders
Analyse project risk quantitatively and engage stakeholders through a planned communication and escalation cadence.
5
Control & Close
Control delivery against baselines with earned value, flow metrics and statistical process control, then close the project and realise benefits.
6
Exam Readiness
Apply the PMI PMP Examination Content Outline (ECO 2026) across all three domains and sit a full-format mock exam with domain score analysis.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
286

## Slide 288
WRAP-UP
Keep Practising After the Course
1
Re-run the labs on your own machine — repetition is what makes the skills stick.
2
Apply the techniques to a real process or project in your own organisation.
3
Your course material stays available at https://lms-tms.tertiaryinfotech.com/.
4
Explore the follow-on courses at www.tertiarycourses.com.sg.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
287

## Slide 289
THANK YOU FOR ATTENDING
Thank You!
You now have the practical skills from every lab in this course — keep applying them to your own work.
PMP-Exam-Prep · C523
© 2026 Tertiary Infotech Academy Pte Ltd
288