## Slide 1
Project Management Professional (PMP) 35 PDU Training
4-Day Instructor-Led Programme · 35 PDUs
Version: 16.0 Trainer: Dr. Alfred Ang
Course Code: TGS-2024045797 TSC: ICT-PMT-4026-1.1
Tertiary Infotech Academy Pte Ltd · UEN 201200696W
Aligned to the PMI PMP Examination Content Outline — July 2026
© 2026 Tertiary Infotech Academy Pte Ltd

## Slide 2
COURSE ADMINISTRATION
Digital Attendance
1
Scan AM and PM, every day
Digital attendance is taken twice daily. Both scans are required for each of the four days.
2
Assessment attendance is separate
Take attendance again for the assessment session on Day 4 — it is a distinct record.
3
75% minimum for funding
SSG funding is conditional on the attendance rate recorded in the digital attendance system.
4
Scan with your own identity
Proxy attendance voids funding for both the absent learner and the person who scanned.
5
TRAQOM quality survey
Mandatory at course end. Your certificate is released only after the survey is submitted.
6
Where to go
Both the attendance QR code and the TRAQOM link are issued by the trainer at lms-tms.tertiaryinfotech.com.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
2

## Slide 3
GENERAL TRAINER PROFILE
About the Trainer
—
<Trainer Name>
<Designation>
<Organisation>
<UEN>
<Email>
Qualifications
<Degree / professional certifications relevant to the course domain, including certifying body and year.>
Industry experience
<Years of relevant practice, sectors worked in, and the scale of projects or teams led.>
Training experience
<ACTA/ACLP status, years of adult training delivery, and the programmes previously facilitated.>
Areas of specialisation
<Specific technical or domain areas the trainer is engaged to deliver within this course.>
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
3

## Slide 4
YOUR FACILITATOR
About the Trainer
AA
Dr. Alfred Ang
Principal Trainer
Tertiary Infotech Academy Pte Ltd
UEN 201200696W
enquiry@tertiaryinfotech.com
Qualifications
Doctorate-level research background with deep grounding in the quantitative techniques this course applies — estimation, risk analysis and statistical quality control.
Industry experience
Two decades leading technology projects across predictive, agile and hybrid delivery in both industry and the public sector.
Training experience
Delivers WSQ programmes in project management, data and AI, and mentors candidates through PMP and Lean Six Sigma pathways.
Areas of specialisation
Project governance, earned value management, agile transformation, and the applied problem-solving toolset used in this course's labs.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
4

## Slide 5
LMS / TMS PORTAL
Download Your Course Material
lms-tms.tertiaryinfotech.com
Project Management Professional (PMP) 35 PDU
TGS-2024045797 · Course materials
Trainer Slides
PPTX
Learner Slides
PDF
Learner Guide
PDF
Lesson Plan
PDF
Lab worksheets
ZIP
1
Sign in
Use the account created with your registration email.
2
Open this course
Find it under My Courses using code TGS-2024045797.
3
Download everything
Slides, Learner Guide, Lesson Plan and labs.
4
Keep your record
Your completion record and certificate live here too.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
5

## Slide 6
HOW WE WORK TOGETHER
Ground Rules
1
Phones on silent
Take calls outside the room so the session is not disrupted for others.
2
Participate actively
This course is built around labs and discussion — the more you contribute, the more you take away.
3
No question is too basic
If something is unclear, ask. Others in the room almost certainly share the same question.
4
Punctuality after breaks
Return on time so we can cover the full ECO syllabus within the four days.
5
Respect differing views
Project management is contextual — disagreement is useful when handled with professional respect.
6
Confidentiality
Workplace examples shared in class stay in the class; anonymise sensitive client or employer detail.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
6

## Slide 7
WSQ / SSG
Skills Framework Alignment
1
TSC Title
Project Management — the technical skill and competency this course is accredited against.
2
TSC Code
ICT-PMT-4026-1.1 — quote this reference in funding and HR records.
3
Course Code
TGS-2024045797 — the SSG course reference for this programme.
4
Proficiency level
Level 4 — able to scope, plan and control medium-scale projects with limited supervision.
5
PDU value
35 contact hours, satisfying the PMI education prerequisite for the PMP application.
6
Assessment
Written Assessment, 1 hour, plus a Case Study, 2 hours — both conducted on Day 4.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
7

## Slide 8
BY THE END OF THIS COURSE YOU WILL BE ABLE TO
Learning Outcomes
1
LO1
Scope medium-scale project requirements to drive timely completions.
2
LO2
Develop project plans based on realistic timelines and resource allocations.
3
LO3
Implement methodologies effectively to address project exigencies and derive solutions from identified root causes.
4
LO4
Analyze program risks and engage stakeholders through scheduled touchpoints to discuss potential issues.
5
LO5
Coordinate project deliverables against set objectives, costs, and timelines, and implement corrective actions.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
8

## Slide 9
WHAT THE EXAM ACTUALLY TESTS
The PMP Exam Content Outline — July 2026
Chart: 
| People 33% | Process 41% | Business Environment 26%
Weighting | 33 | 41 | 26
WHAT IT TELLS YOU
People 33% — leading, aligning and communicating with the team and stakeholders.
Process 41% — planning, delivering, measuring and closing the work.
Business Environment 26% — governance, compliance, risk and change. Up sharply from the old 8%.
Approach mix: ~40% predictive, 60% adaptive/agile and hybrid.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
9

## Slide 10
EXAM UPDATE
What Changed in the July 2026 Exam Update
1
Business Environment tripled
Weighting rises from 8% to 26% — governance, compliance and external change are now central, not peripheral.
2
People eased slightly
From 42% to 33%, but the tasks are sharper: vision, conflict, expectations and knowledge transfer.
3
Process rebalanced
From 50% to 41%, with new emphasis on value-based delivery and financial management.
4
Sustainability is examinable
Named explicitly in compliance, quality (cost of quality) and risk response enablers.
5
Artificial intelligence enters scope
The JTA validated AI as a trend affecting practice — expect it in estimation, reporting and governance items.
6
Graphic-based questions are new
You will be asked to read charts, control charts and diagrams and answer from them — practise interpretation.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
10

## Slide 11
EXAM MECHANICS
PMP Exam Format at a Glance
Element | Detail | What it means for you
Questions | 180 total (170 scored + 10 pretest) | Unscored pretest items are indistinguishable — answer everything seriously.
Time | 240 minutes (4 hours) | About 80 seconds per question — pace, do not linger.
Breaks | Two 10-minute breaks | First after the case-study section, second midway through the rest.
Section lock | No return after a break | Review your answers BEFORE you start a break.
Approach mix | About 40% predictive; the remaining 60% split between adaptive/agile and hybrid. | You cannot pass on waterfall knowledge alone.
Delivery | Test centre or online proctored | Case study questions are available on all modalities.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
11

## Slide 12
SIX FORMATS YOU WILL MEET
PMP Exam Question Types
1
Multiple choice
One best answer from four options — the bulk of the exam.
2
Multiple response
More than one correct answer; the item tells you how many.
3
Matching
Drag items from one column to match a second column.
4
Enhanced matching
Matching that includes an image or diagram for context.
5
Graphic-based (NEW)
Read a chart, graph, diagram or image, then answer from it.
6
Case study
A scenario with supporting visuals, then a series of linked questions.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
12

## Slide 13
WHERE WE ARE GOING
Course Outline — Topics 1 to 3
1
Topic 1. Business Environment
Where projects come from, why they are funded, and the governance, compliance and change context they must survive in.
Foundation and project fundamentals · Strategic alignment and business value · Development approaches: predictive, agile, hybrid
2
Topic 2. Start the Project
Turning an idea into an authorised project: the business case, the charter, the stakeholders and the team.
Project integration and the charter · Business case, cost-benefit and benefits management · Identify, analyse and prioritise stakeholders
3
Topic 3. Plan the Project
Building the integrated plan — scope, schedule, cost, quality, resources, communications, risk and procurement.
The integrated project management plan · Scope: requirements, WBS and baselines · Schedule: activities, dependencies, critical path
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
13

## Slide 14
WHERE WE ARE GOING
Course Outline — Topics 4 to 6
1
Topic 4. Lead the Project Team
The People domain in practice — leadership style, motivation, conflict, coaching and communication.
Direct and manage project work · Craft your leadership skills · Build a collaborative team environment
2
Topic 5. Monitor and Control the Project
Measuring truth against plan: earned value, quality control, change control, issues and impediments.
Monitor and control project work · Evaluate project progress and earned value · Control quality with statistical tools
3
Topic 6. Close the Project
Landing the project: acceptance, transition, benefits realisation and the knowledge that outlives the team.
Project and phase closure · Benefits realisation and value confirmation · Knowledge transfer and lessons learned
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
14

## Slide 15
LESSON PLAN
The Four Days
1
Day 1
Business Environment & Starting the Project Labs 01-08
2
Day 2
Planning the Project Labs 09-14
3
Day 3
Leading the Team & Controlling Delivery Labs 15-22
4
Day 4
Closing, Exam Strategy & Practice Labs 23-24 + practice exam
Each day runs 9:30am–6:30pm with a one-hour lunch break and two tea breaks. Roughly half of each day is hands-on lab work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
15

## Slide 16
DAY 1 SCHEDULE
Lesson Plan — Day 1: Business Environment & Starting the Project
Time | Session | Activity
9:30 – 10:00 | Registration & Digital Attendance (AM) | Course introduction, trainer and learner introductions, ground rules, learning outcomes, ECO 2026 orientation
10:00 – 11:15 | Topic 1. Business Environment | Concept delivery, worked examples and discussion
11:15 – 11:30 | Tea Break | —
11:30 – 13:00 | Topic 2. Start the Project | Concept delivery, worked examples and discussion
13:00 – 14:00 | Lunch Break | —
14:00 – 14:15 | Digital Attendance (PM) | Afternoon attendance scan
14:15 – 15:45 | Hands-on Labs | Lab 01, Lab 02, Lab 03, Lab 04 (LO1, LO3, LO4)
15:45 – 16:00 | Tea Break | —
16:00 – 17:30 | Hands-on Labs (continued) | Lab 05, Lab 06, Lab 07, Lab 08 — group share-back
17:30 – 18:30 | Consolidation | Exam-style question drill on the day's material, recap and Q&A
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
16

## Slide 17
DAY 2 SCHEDULE
Lesson Plan — Day 2: Planning the Project
Time | Session | Activity
9:30 – 10:00 | Registration & Digital Attendance (AM) | Digital attendance (AM); recap of Day 1 and Q&A
10:00 – 11:15 | Topic 3. Plan the Project | Concept delivery, worked examples and discussion
11:15 – 11:30 | Tea Break | —
11:30 – 13:00 | Topic 3. Plan the Project | Concept delivery, worked examples and discussion
13:00 – 14:00 | Lunch Break | —
14:00 – 14:15 | Digital Attendance (PM) | Afternoon attendance scan
14:15 – 15:45 | Hands-on Labs | Lab 09, Lab 10, Lab 11 (LO1, LO2, LO4)
15:45 – 16:00 | Tea Break | —
16:00 – 17:30 | Hands-on Labs (continued) | Lab 12, Lab 13, Lab 14 — group share-back
17:30 – 18:30 | Consolidation | Exam-style question drill on the day's material, recap and Q&A
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
17

## Slide 18
DAY 3 SCHEDULE
Lesson Plan — Day 3: Leading the Team & Controlling Delivery
Time | Session | Activity
9:30 – 10:00 | Registration & Digital Attendance (AM) | Digital attendance (AM); recap of Day 2 and Q&A
10:00 – 11:15 | Topic 4. Lead the Project Team | Concept delivery, worked examples and discussion
11:15 – 11:30 | Tea Break | —
11:30 – 13:00 | Topic 5. Monitor and Control the Project | Concept delivery, worked examples and discussion
13:00 – 14:00 | Lunch Break | —
14:00 – 14:15 | Digital Attendance (PM) | Afternoon attendance scan
14:15 – 15:45 | Hands-on Labs | Lab 15, Lab 16, Lab 17, Lab 18 (LO2, LO3, LO4, LO5)
15:45 – 16:00 | Tea Break | —
16:00 – 17:30 | Hands-on Labs (continued) | Lab 19, Lab 20, Lab 21, Lab 22 — group share-back
17:30 – 18:30 | Consolidation | Exam-style question drill on the day's material, recap and Q&A
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
18

## Slide 19
DAY 4 SCHEDULE
Lesson Plan — Day 4: Closing, Exam Strategy & Practice
Time | Session | Activity
9:30 – 9:45 | Digital Attendance (AM) | Digital attendance (AM); recap of Day 3 and Q&A
9:45 – 11:00 | Topic 6. Close the Project | Concept delivery: closure, benefits realisation, knowledge transfer
11:00 – 11:15 | Tea Break | —
11:15 – 13:00 | Hands-on Labs | Lab 23 (LO1, LO2, LO3, LO4, LO5)
13:00 – 14:00 | Lunch Break | —
14:00 – 14:15 | Digital Attendance (PM) | Afternoon attendance scan
14:15 – 15:15 | Hands-on Labs (continued) | Lab 24 — capstone consolidation and mock exam review
15:15 – 15:30 | Briefing for Assessment | Assessment rules, timing, materials and submission
15:30 – 16:30 | Written Assessment (WA) | Open-ended short-answer questions, K1–K5 (1 hour)
16:30 – 18:30 | Case Study Assessment (CS) | Applied project scenario, A1–A8 (2 hours); digital attendance for the assessment session
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
19

## Slide 20
ASSESSMENT RULES
Briefing for Assessment
1
Open book
Course slides, your Learner Guide and your lab artifacts may be used. Phones and bags go under the table.
2
No recording
Photographs and recordings of assessment papers are strictly prohibited.
3
No collaboration
The assessment is individual work; talking during the assessment ends your attempt.
4
Time allocation
Written Assessment 1 hour (3:30–4:30pm), then the Case Study 2 hours (4:30–6:30pm).
5
Ask before you start
Clarify any instruction with the assessor before beginning — not midway through.
6
Submit everything
Hand in all question papers and answer scripts, including any rough working.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
20

## Slide 21
HOW YOU WILL BE ASSESSED
Assessment
1
Written Assessment — 1 hour
Five open-ended short-answer questions (K1–K5) on the ECO domains, processes, formulas and terminology.
Day 4, 3:30pm–4:30pm. Open book, individual.
2
Case Study — 2 hours
One project scenario with five linked questions (A1–A8) requiring applied judgement rather than recall.
Day 4, 4:30pm–6:30pm. Open book, individual.
3
Competency standard
You are assessed Competent (C) or Not Yet Competent (NYC) against the five learning outcomes.
4
Re-assessment
Learners assessed NYC are offered one re-assessment opportunity per the academy's assessment policy.
5
What to bring
Photo identification, a non-programmable calculator, and your course materials — both papers are open book.
6
Funding condition
Completing the assessment is a mandatory condition of SSG funding, alongside the 75% attendance rate.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
21

## Slide 22
SSG REQUIREMENTS
Criteria for Funding
1
75% minimum attendance
Based on the SSG digital attendance record — both AM and PM scans, every day.
2
Complete the assessment
You must attempt the Written Assessment and the Case Study on Day 4.
3
Achieve Competent
A Competent outcome across all learning outcomes is required for certification.
4
Complete TRAQOM
The mandatory quality survey must be submitted to release your certificate.
5
Employer-sponsored claims
Absentee payroll and course-fee claims follow your organisation's SkillsFuture submission process.
6
Keep your records
Retain your certificate and course code for the PMI application — this course supplies the 35 contact hours.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
22

## Slide 23
01
TOPIC
Business Environment
Where projects come from, why they are funded, and the governance, compliance and change context every project must survive in. This topic sets the vocabulary used for the rest of the course.
1
What a project is, and what project management actually delivers
2
The 12 PMI principles and what project success really depends on
3
Life cycles and development approaches: predictive, agile and hybrid
4
Organisational culture, EEFs, OPAs and structured change management
5
Project governance, escalation thresholds and phase gates
6
Compliance, sustainability and the responsible use of AI in projects
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
23

## Slide 24
DEFINITION OF A PROJECT
The foundation of everything that follows
A project is a temporary endeavour undertaken to create a unique product, service or result.
TEMPORARY
It has a definite start and a definite end — ending when objectives are met, or when it is clear they cannot be.
UNIQUE
The output has never been produced in exactly this form before, so some degree of uncertainty is always present.
DELIVERS CHANGE
A project moves the organisation from a current state to a future state that carries business value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
24

## Slide 25
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Projects versus operations — why the distinction matters
PROJECT WORK
Temporary, unique, change-driven
Has a defined start and end date fixed by the charter
Produces a unique deliverable that did not previously exist
Staffed by a team that is assembled and later released
Success is measured against scope, schedule, cost and benefits
Progressively elaborated as more information becomes known
Funded from a capital or change budget with a business case
OPERATIONAL WORK
Ongoing, repetitive, efficiency-driven
Continues indefinitely as long as the business needs the output
Produces the same product or service repeatedly to a standard
Staffed by a permanent functional team reporting to a line manager
Success is measured against throughput, cost per unit and quality
Optimised for stability and predictable repetition, not novelty
Funded from a recurring operating expense budget
Exam cue: if the scenario describes work that never ends or simply repeats, it is operations — the correct answer usually involves transitioning the deliverable to operations, not extending the project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
25

## Slide 26
ECO BUSINESS ENV T8 · EVALUATE EXTERNAL BUSINESS ENVIRONMENT CHANGES
What counts as a project? Recognising project work in the wild
1
Developing a software product
Building a new mobile banking app from concept to launch — unique code, a fixed release date, and a team disbanded after go-live.
2
Constructing a new office
Design, permits, build and fit-out of a physical asset, with heavy regulatory compliance and irreversible, expensive change late on.
3
Filming a motion picture
Highly creative, schedule-driven work with named talent constraints and a single big-bang delivery to distribution.
4
An advertising campaign
Short, iterative, market-sensitive delivery where the external environment can invalidate the concept mid-flight.
5
Redesigning a business process
An internal change project whose real deliverable is adoption by people, not a document — heavy change management content.
6
Migrating to a cloud platform
Technical transformation with security, data-residency and compliance obligations plus a hard decommission deadline.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
26

## Slide 27
PROJECT MANAGEMENT DEFINED
What is project management?
The application of knowledge, skills, tools and techniques to project activities to meet the project requirements.
A DISCIPLINE
It spans initiating, planning, executing, monitoring and controlling, and closing — performed with intent, not by accident.
A VALUE ENGINE
Projects are how strategy actually happens; without them an organisation's strategic plan stays a slide deck.
A RISK REDUCER
Structured management makes uncertainty visible early, when responding to it is still cheap.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
27

## Slide 28
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
The role of the project manager — six jobs you are actually paid for
1
Integrator
Holds the whole picture together, making sure scope, schedule, cost, quality and risk decisions are consistent with one another.
2
Communicator
Spends roughly 90% of the working day communicating — translating between technical teams, sponsors and customers.
3
Decision maker
Makes calls within delegated authority and escalates cleanly and quickly when a threshold is breached.
4
Servant leader
Removes impediments, protects the team from noise, and creates the conditions in which skilled people can do good work.
5
Risk owner
Continuously scans internally and externally for threats and opportunities, and drives agreed responses to closure.
6
Business steward
Keeps the project honest about business value, stopping or reshaping work that no longer justifies its investment.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
28

## Slide 29
TRIPLE CONSTRAINT
The triple constraint — the physics of every project
Scope, time and cost are joined; move one and at least one other must move, or quality silently absorbs the difference.
SCOPE
The work required and the features delivered. Uncontrolled growth here is scope creep and is the single most common project failure.
TIME
The schedule and its milestones. Compressing time without adding cost or cutting scope only borrows quality from the future.
COST
The approved budget including reserves. Cutting cost mid-flight usually means fewer people, which extends time.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
29

## Slide 30
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Which constraint is fixed? Choosing your development approach from it
Fixed date, vague scope
Use agile with a fixed timebox and a variable backlog. Deliver the highest-value slice by the date.
Fixed date, clear scope
Predictive delivery with a firm baseline and strong change control is the natural fit.
Flexible date, vague scope
Exploratory or iterative work — prototype, learn, then commit once the problem is understood.
Flexible date, clear scope
Incremental delivery lets the customer take value early while the remaining work continues.
REQUIREMENTS CERTAINTY → high
DELIVERY DATE → fixed
In agile the triple constraint inverts: cost and time are fixed by the sprint, and scope is the variable that flexes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
30

## Slide 31
PMI TALENT TRIANGLE
The PMI Talent Triangle — three competency areas the PMP tests
1
Ways of Working
Technical mastery of the many methods available — predictive, agile, hybrid — and the judgement to tailor the method to the environment.
2
Power Skills
Collaborative leadership, effective communication, empathy, conflict resolution and the influence needed without formal authority.
3
Business Acumen
Understanding priority, cost versus benefit, industry context and how to make decisions that hold up commercially, not just technically.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
31

## Slide 32
PMI PRINCIPLES
The 12 PMI project management principles (1 of 2)
1
Be a diligent, respectful, caring steward
Act with integrity and in the organisation's and society's interest, honouring both internal and external obligations.
2
Create a collaborative team environment
Teams that share agreements, structures and processes deliver more than individuals working in parallel silos.
3
Effectively engage with stakeholders
Engage proactively and to the degree needed to contribute to project success and customer satisfaction.
4
Focus on value
Continually evaluate and adjust project alignment to business objectives and the intended benefits and value.
5
Recognize and respond to system interactions
See the project as a system of interacting parts; a change in one area has consequences elsewhere in the organisation.
6
Demonstrate leadership behaviours
Leadership is a behaviour anyone on the team can show, not a position on an organisation chart.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
32

## Slide 33
PMI PRINCIPLES
The 12 PMI project management principles (2 of 2)
1
Tailor based on context
Design the delivery approach around the project's context, objectives, stakeholders, governance and environment.
2
Build quality into processes and deliverables
Quality is designed in and inspected continuously, not bolted on by testing at the end of the schedule.
3
Navigate complexity
Continually evaluate and address complexity arising from human behaviour, system interactions, ambiguity and uncertainty.
4
Optimize risk responses
Consistently evaluate exposure to both threats and opportunities, seeking responses proportional to the impact.
5
Embrace adaptability and resilience
Build capacity to absorb impacts and recover quickly, so setbacks do not become project failures.
6
Enable change to achieve the future state
Prepare those affected for adoption; a delivered output that nobody uses has produced zero value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
33

## Slide 34
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
What project success actually depends on
Chart: 
| Understanding of the core problem | Collaboration & communication | PM effectiveness | Team member skill levels | Funding & resource availability | Organisational project maturity
Relative influence on outcome | 95 | 88 | 82 | 76 | 70 | 64
WHAT IT TELLS YOU
Most failures trace back to solving the wrong problem well, not to weak execution of the right one.
Communication quality outranks tooling — no tool rescues a team that does not talk to its stakeholders.
Organisational maturity sets the ceiling; a strong PM in an immature organisation still fights the system.
Funding matters, but adequate funding on the wrong scope simply buys a faster failure.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
34

## Slide 35
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Two different life cycles — do not confuse them on the exam
PROJECT LIFE CYCLE
The phases the project passes through
The series of phases a project moves through from start to close
Typical phases: feasibility, design, build, test, deploy, close
Phases usually end in a phase gate or stage-gate review
At each gate the sponsor decides go, go-with-change, hold or kill
Defined by the organisation's methodology and governance
Answers the question: where are we in the journey?
DEVELOPMENT LIFE CYCLE
How the deliverable is actually produced
The approach used to create the product inside those phases
Options: predictive, iterative, incremental, adaptive/agile, hybrid
Chosen from requirements certainty, risk and delivery cadence
Can differ per deliverable within one and the same project
Defined by the team with the sponsor, and can be tailored
Answers the question: how are we building the thing?
A single project can have a predictive project life cycle for governance while using an agile development life cycle inside the build phase — that combination is a hybrid.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
35

## Slide 36
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
The generic project life cycle and its effort profile
1
Starting the project
Charter approved, sponsor named, high-level scope and stakeholders identified. Cost and staffing are low.
2
Organising & preparing
The integrated plan is built. Effort ramps up and the ability to influence outcome is still high.
3
Carrying out the work
The bulk of cost and staffing. Changes here are expensive; risk decreases as work is completed.
4
Ending the project
Acceptance, transition, procurement and financial closure, lessons learned, release of the team.
Risk and stakeholder influence are highest at the start; the cost of change is highest at the end. That single relationship explains most of PMI's guidance on planning and early engagement.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
36

## Slide 37
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Why early decisions dominate: risk, influence and the cost of change
Chart: 
| Initiation | Planning | Early execution | Mid execution | Late execution | Closing
Stakeholder influence & risk | 95 | 80 | 58 | 38 | 18 | 5
Cost of making a change | 5 | 15 | 35 | 60 | 88 | 98
WHAT IT TELLS YOU
The two curves cross early — after that point, changes cost more than the influence they buy.
This is the mathematical argument for investing in requirements and stakeholder engagement up front.
Agile flattens the cost-of-change curve by keeping increments small and reversible rather than by planning harder.
Exam cue: 'the change was requested late in execution' signals a formal impact analysis, not immediate action.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
37

## Slide 38
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Common life cycle definitions — the vocabulary PMI uses
Life cycle | Requirements | Delivery | Goal / when to use
Predictive | Fixed and baselined up front | One delivery at the end | Manage cost — best when the solution is well understood and change is expensive
Iterative | Dynamic; refined each cycle | One final delivery, repeated refinement | Correctness of the solution — prototype until the right thing is understood
Incremental | Dynamic; decomposed into slices | Frequent smaller usable deliveries | Speed to value — customer gets working capability before the whole is finished
Adaptive / agile | Dynamic, in a prioritised backlog | Frequent delivery via short timeboxes | Customer value through fast feedback — best under high uncertainty
Hybrid | Mixed by component or phase | Mixed cadence across the project | Fit the approach to each part — the most common shape in real organisations
Memory hook: iterative improves the same thing repeatedly; incremental adds new usable pieces. Agile deliberately does both at once.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
38

## Slide 39
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
The development approach continuum, from most to least predictive
STEP 1
Predictive
Full scope defined up front, single delivery at the end, change controlled formally through a change board.
STEP 2
Iterative
Repeated cycles refine one solution until it is right; the delivery to the customer still happens once.
STEP 3
Incremental
Successive usable slices are handed over, each adding functionality to what the customer already has.
STEP 4
Adaptive / Agile
Short timeboxes deliver working increments while the backlog is continuously reprioritised on feedback.
STEP 5
Hybrid
Deliberately combines approaches — for example predictive infrastructure alongside an agile application build.
The approach is a tailoring decision, not an identity. PMI expects you to justify it from requirements certainty, risk, regulatory constraint and how quickly value can be delivered.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
39

## Slide 40
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Project cadence — the timing and frequency of delivery
1
Single delivery
One handover at the very end of the project. Typical of construction, regulated pharmaceuticals and large infrastructure.
2
Multiple deliveries
Work is separated into parts released as they complete, not necessarily in a fixed sequence or on a fixed calendar.
3
Periodic delivery
Multiple deliveries released on a fixed drumbeat — monthly, bi-monthly or every sprint — which makes planning predictable.
4
Continuous delivery
Every accepted change flows to production as it is ready, supported by automated testing and deployment pipelines.
5
Cadence versus approach
Cadence is about when the customer receives value; the development approach is about how the work is produced.
6
Why it matters
Cadence drives the release plan, the funding profile, and how often the benefits measurement system must be read.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
40

## Slide 41
AGILE FUNDAMENTALS
The definition you must be able to state cold
Agile is both incremental — small, regular releases of value — and iterative — reflecting and improving regularly.
INCREMENTAL
Each sprint hands over a potentially releasable increment, so the customer accrues real value long before the end.
ITERATIVE
Each sprint also revisits and refines what exists, and the retrospective refines how the team works.
THE COMBINATION
Doing only one of the two is not agile: increments without reflection stagnate; reflection without increments stalls.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
41

## Slide 42
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Predictive (waterfall) versus adaptive (agile) delivery
PREDICTIVE / WATERFALL
Plan the work, then work the plan
Requirements are gathered once, then baselined and frozen
Design, build and test are performed once, in sequence
Success is conformance to the approved scope, schedule and budget
Change is a formal event requiring a change request and CCB approval
Detailed documentation is produced and is itself a deliverable
Customer sees the working product late, usually at UAT
ADAPTIVE / AGILE
Inspect and adapt, every timebox
Requirements live in a backlog and are refined continuously
Design, build and test are performed once per increment
Success is working product and realised customer value
Change is expected and absorbed by reprioritising the backlog
Working software is favoured over comprehensive documentation
Customer sees working product at the end of every sprint
Predictive performs the full life cycle once; adaptive performs it once per increment. That single sentence answers a surprising number of exam questions.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
42

## Slide 43
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
The Stacey model — matching approach to complexity and uncertainty
Complicated
Requirements are unclear but technology is known. Use iterative or incremental cycles to converge on the right scope.
Complex
Both what and how are uncertain. Agile with short feedback loops and small safe-to-fail experiments is the fit.
Simple
Both what and how are well understood. Predictive delivery is efficient and the cheapest option to govern.
Complicated (technical)
The what is clear but the how is not. Use spikes, prototypes and iterative technical proving.
TECHNOLOGY / HOW → uncertain
REQUIREMENTS / WHAT → uncertain
Agile is suited to high-uncertainty work. Using agile on genuinely simple, well-understood work adds ceremony without buying any information.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
43

## Slide 44
AGILE MANIFESTO
The Agile Manifesto (2001) — four values, stated as preferences
WE VALUE MORE
The left-hand side of each pairing
Individuals and interactions
Working software (working product)
Customer collaboration
Responding to change
Seventeen practitioners agreed these in Snowbird, Utah in 2001
The values sit above the 12 principles and all frameworks
OVER
The right-hand side still has value
… over processes and tools
… over comprehensive documentation
… over contract negotiation
… over following a plan
'While there is value in the items on the right, we value the items on the left more'
Agile never says documentation or plans are worthless
Exam trap: an option saying agile teams do not plan or do not document is always wrong. Agile teams plan more often, in smaller pieces, and document what is genuinely useful.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
44

## Slide 45
AGILE PRINCIPLES
The 12 Agile Principles (1 of 2)
1
Satisfy the customer early
Highest priority is satisfying the customer through early and continuous delivery of valuable software.
2
Welcome changing requirements
Even late in development; agile processes harness change for the customer's competitive advantage.
3
Deliver frequently
Deliver working product from a couple of weeks to a couple of months, with a preference for the shorter timescale.
4
Business and developers together
Business people and developers must work together daily throughout the project, not meet at handover points.
5
Build around motivated individuals
Give them the environment and support they need, and trust them to get the job done.
6
Face-to-face conversation
The most efficient and effective method of conveying information within a development team.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
45

## Slide 46
AGILE PRINCIPLES
The 12 Agile Principles (2 of 2)
1
Working product is the measure
Working software is the primary measure of progress — not percentage complete, not documents produced.
2
Sustainable pace
Sponsors, developers and users should be able to maintain a constant pace indefinitely; heroics are a warning sign.
3
Technical excellence
Continuous attention to technical excellence and good design enhances agility and keeps future change cheap.
4
Simplicity
The art of maximising the amount of work not done — building only what is needed is essential.
5
Self-organising teams
The best architectures, requirements and designs emerge from self-organising teams, not from imposed plans.
6
Reflect and adjust
At regular intervals the team reflects on how to become more effective, then tunes and adjusts its behaviour.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
46

## Slide 47
SCRUM ROLES AND ARTIFACTS
Scrum — the most widely used agile framework
1
Product Owner
Owns and prioritises the product backlog, represents the business, and is accountable for maximising the value the team delivers.
2
Scrum Master
Facilitates the events, coaches the team on Scrum, removes impediments, and shields the team from outside interference.
3
Development Team
Three to nine cross-functional people who self-organise to turn backlog items into a done increment each sprint.
4
Product Backlog
The single ordered list of everything that might be needed, continuously refined and re-ordered by the Product Owner.
5
Sprint Backlog
The subset the team commits to this sprint, plus the plan for delivering it; owned entirely by the development team.
6
Increment
The sum of all completed backlog items this sprint plus all prior sprints, in a potentially releasable state.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
47

## Slide 48
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
The sprint — Scrum events in the order they occur
STEP 1
Sprint Planning
The team pulls backlog items into the sprint and agrees the sprint goal. Timeboxed to 8 hours for a month sprint.
STEP 2
Daily Scrum
A 15-minute timeboxed sync where the team inspects progress toward the sprint goal and replans the next 24 hours.
STEP 3
Development Work
The team builds the increment, refining the backlog for future sprints as it goes.
STEP 4
Sprint Review
The team demonstrates the increment to stakeholders and the backlog is adapted based on their feedback.
STEP 5
Sprint Retrospective
The team inspects how it worked and commits to specific improvements for the next sprint.
A sprint is a timebox of one month or less. Its length is fixed, its scope is not — the sprint end date never moves to accommodate unfinished work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
48

## Slide 49
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Agile ceremonies beyond the core Scrum events
1
Product strategy meeting
The Product Owner shares the product vision and roadmap so the team understands why the backlog is ordered the way it is.
2
Backlog refinement (grooming)
An ongoing session where items are clarified, split, estimated and re-ordered so the top of the backlog is always ready.
3
Daily standup
Five to fifteen minutes, timeboxed, and not necessarily daily on every team — the purpose is coordination, not status reporting.
4
Release planning
Maps multiple sprints to a release date so stakeholders outside the team can plan marketing, training and operations.
5
Project retrospective
Held at the end of the project to review both the work and the process — the agile equivalent of lessons learned.
6
Demo or showcase
An informal review with wider stakeholders, used to gather feedback before committing to the next block of work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
49

## Slide 50
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Running a retrospective that actually changes behaviour
STEP 1
Set the stage
Establish psychological safety and remind everyone the aim is improvement of the system, not blame of individuals.
STEP 2
Gather data
Collect facts about the sprint — metrics, events, incidents — so opinions can be anchored to evidence.
STEP 3
Generate insights
Ask why the data looks as it does; use root cause tools such as 5 Whys or a fishbone diagram.
STEP 4
Decide what to do
Choose one or two improvements the team can genuinely complete in the next sprint.
STEP 5
Close the retrospective
Confirm the actions, name owners, and put them into the next sprint backlog so they are real work.
A retrospective with no action items in the next sprint backlog is theatre. Track improvement actions with the same rigour as feature work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
50

## Slide 51
PEOPLE AND TEAMS
The project team — makeup, sourcing and skills
1
Team composition
Refers to the team's makeup and how members are brought together; it varies with organisational culture, location and project scope.
2
Full-time and part-time
Members may be dedicated or shared. Shared members multitask, which reduces throughput and increases handover risk.
3
Generalists and specialists
Specialists bring depth for hard problems; generalists give the team the flexibility to redistribute work when plans change.
4
Avoid single points of failure
If only one person holds a required skill, their absence stops the project — cross-train deliberately.
5
Cross-functional teams
A team that contains every skill needed to take an item from idea to done removes waiting on external groups.
6
T-shaped people
Generalising specialists with one deep specialty plus broad general skills — the most valuable shape for agile teams.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
51

## Slide 52
AGILE TEAMS
Agile team characteristics and the agile team space
1
Small
Typically three to twelve members. Communication paths grow quadratically, so large teams spend their capacity coordinating.
2
Co-located or well-connected
Physical or virtual co-location creates an osmotic environment where useful information is absorbed without a meeting.
3
Dedicated
100% allocated to one team to avoid multitasking, which is the single largest source of hidden delay in knowledge work.
4
Information radiators
Burndown charts, Kanban boards and impediment lists on display, so status is visible at a glance without a report.
5
Pairing
Two people work on one item together, checking each other's thinking and spreading knowledge as a side effect.
6
Swarming
Multiple team members converge on one blocked or high-value item to finish it fast rather than starting new work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
52

## Slide 53
AGILE ROLES
Agile team roles and their traditional equivalents
Agile role | What they do | Closest predictive equivalent
Product Owner | Represents the customer and business, owns and prioritises the product backlog, accepts or rejects each increment | Business analyst plus sponsor's delegate
Team Facilitator | Also called Scrum Master, agile lead, team coach or servant leader; runs ceremonies, removes blockers, grows the team | Project manager (facilitation half of the role)
Cross-functional member | Generalising specialists — T-shaped people who self-organise to deliver the increment end to end | Team member from a functional department
Agile Coach | Works across several teams on practice maturity and organisational impediments beyond a single team | PMO methodology lead
Stakeholder / customer | Attends reviews, supplies the feedback that re-orders the backlog, and confirms value is real | Steering committee member or end user
Note what is missing: agile has no role that assigns tasks to individuals. Work is pulled by the team, not pushed by a manager.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
53

## Slide 54
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Tailoring — the principle that makes everything else practical
We can, and should, tailor anything on our project so it meets the outcomes and delivers business value.
PROCESS
The development approach, the number of phases, the depth of planning and the frequency of governance reviews.
ARTIFACTS
Which plans, registers and reports genuinely help — and which exist only because a template said so.
METHODS & TOOLS
The estimating techniques, meeting formats, tooling and metrics that fit this team and this context.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
54

## Slide 55
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
The four-step tailoring approach
STEP 1
Select the initial approach
Choose predictive, adaptive or hybrid based on requirements certainty, risk and delivery cadence.
STEP 2
Tailor for the organisation
Adjust for the organisation's methodology, PMO requirements, governance and regulatory obligations.
STEP 3
Tailor for the project
Adjust for product type, culture, team size and criticality — a safety-critical build needs more rigour.
STEP 4
Implement ongoing improvement
Inspect the tailored process at retrospectives and adjust it as the project and team mature.
Tailoring is not permission to skip work you find inconvenient. Every removal should be a reasoned decision you could defend to the sponsor or an auditor.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
55

## Slide 56
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Types of managers — who owns what in the organisation
1
Project Manager
Assigned by the performing organisation to lead the team responsible for achieving the project objectives and delivering business value.
2
Functional Manager
Manages a functional or business unit and provides the people, skills and physical resources the project consumes.
3
Operations Manager
Responsible for ensuring ongoing business operations run efficiently, and receives the project's output at transition.
4
Program Manager
Coordinates related projects to obtain benefits not available from managing them individually, and resolves cross-project conflicts.
5
Portfolio Manager
Selects and balances the mix of programs and projects so the investment aligns with organisational strategy.
6
Product Manager
Owns a product across its whole life — well before a project starts and long after it closes — driving the roadmap and value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
56

## Slide 57
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Product management versus project management
PRODUCT MANAGEMENT
Continuous, value-and-market driven
Spans the entire product life cycle, potentially for years
Owns the vision, roadmap and the ordered backlog of value
Measures success by adoption, revenue, retention and outcomes
Funding is often a standing capacity, not a one-off approval
Ends only when the product is retired from the market
Asks: are we building the right thing?
PROJECT MANAGEMENT
Temporary, delivery-and-constraint driven
Spans one temporary endeavour with a defined start and end
Owns the plan, the baselines and the delivery of agreed scope
Measures success by scope, schedule, cost, quality and benefits
Funding is approved against a specific business case
Ends at acceptance, transition and administrative closure
Asks: are we building the thing right?
Organisations increasingly fund persistent product teams rather than discrete projects — the PMP now expects you to operate comfortably in both models.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
57

## Slide 58
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Organisational structure and project manager authority
Structure | PM authority | PM role | Resource control
Functional | Little or none | Part-time coordinator | Functional manager controls the budget and the people
Weak matrix | Low | Part-time expediter or coordinator | Functional manager still controls the budget
Balanced matrix | Low to moderate | Full-time project manager | Budget is shared between PM and functional manager
Strong matrix | Moderate to high | Full-time project manager | Project manager controls the budget
Projectised | High to almost total | Full-time project manager | Project manager controls budget and staff entirely
Hybrid / composite | Varies by project | Varies | Mixed — the most common real-world arrangement
If an exam scenario says the PM has no authority over resources, you are in a functional or weak matrix — the correct action is almost always to negotiate with the functional manager.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
58

## Slide 59
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Project Management Office types and their degree of control
PMO type | Authority and control | What it provides
Supportive | Low degree of control — consultative | Serves as a project repository; supplies templates, best practices, training and information from other projects
Controlling | Moderate degree of control — compliance | Provides support and ensures compliance through adoption of methods, frameworks, specific templates, forms and tools
Directive | High degree of control — direct management | Takes control by directly managing the projects; project managers are assigned by and report into the PMO
Agile / value delivery office | Enabling rather than controlling | Coaches teams, removes organisational impediments and reports on flow and benefits rather than on plan conformance
Memory hook: Supportive suggests, Controlling checks, Directive directs. The exam tests which one owns the project manager.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
59

## Slide 60
ECO BUSINESS ENV T8 · EVALUATE EXTERNAL BUSINESS ENVIRONMENT CHANGES
Reading the external business environment: PESTLE, TECOP and VUCA
1
PESTLE
Political, Economic, Socio-cultural, Technological, Legal and Environmental forces — the standard scan of the macro environment.
2
TECOP
Technical, Environmental, Commercial, Operational and Political — a risk-oriented scan used heavily in engineering and construction.
3
VUCA
Volatility, Uncertainty, Complexity and Ambiguity — describes the character of the environment rather than listing its factors.
4
Why the PM does this
External change can invalidate the business case mid-project; scanning turns an ambush into a managed risk with a response.
5
How often
Not once at initiation. ECO T8 requires the PM to continually review the external environment for impacts to scope and backlog.
6
What you do with it
Feed findings into the risk register, reprioritise the backlog, and escalate anything that threatens the business case.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
60

## Slide 61
ECO BUSINESS ENV T8 · EVALUATE EXTERNAL BUSINESS ENVIRONMENT CHANGES
Responding to a change in the external business environment
STEP 1
Survey
Continuously scan regulations, technology, geopolitics, competitors and market conditions relevant to the project.
STEP 2
Assess impact
Determine what the change does to scope, backlog, business case, benefits, risk exposure and compliance obligations.
STEP 3
Prioritise
Rank the impact against other demands; not every external change deserves a response this quarter.
STEP 4
Act or escalate
Reprioritise the backlog within your authority, or raise a change request and escalate beyond your threshold.
STEP 5
Review continually
Re-check the environment on a defined cadence and update the risk register and the plan accordingly.
Classic exam scenario: a new regulation is announced mid-project. The best first action is to assess the impact on the project — not to stop work, and not to immediately change scope.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
61

## Slide 62
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Enterprise Environmental Factors versus Organizational Process Assets
EEF — conditions you must live with
Usually inputs; largely outside your control
Internal: resource capabilities, organisational culture, IT systems, distribution of facilities, employee capability
External: marketplace conditions, laws, regulations and standards
External: operating conditions, social and cultural influences
Government or industry standards you cannot negotiate away
Risk tolerances and the organisation's appetite for change
You adapt the project to EEFs; you rarely change them
OPA — knowledge you can reuse
Inputs and outputs; you can and should update them
Processes, policies and procedures: organisational charts, procurement rules, hiring and onboarding procedures
Templates, checklists, standardised WBS structures and forms
Organisational knowledge bases: engineering wikis, libraries, archives
Lessons learned repositories and historical estimating databases
Configuration management and financial control procedures
ECO T6 requires you to update OPAs — they are an output too
Fastest test: can the project change it? If yes it is usually an OPA. If the project must simply conform to it, it is an EEF.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
62

## Slide 63
EEF VS OPA
Exam drill: classify these as EEF or OPA
IF THE QUESTION SAYS
Economic demand for a new shopping area; local neighbourhood demand for a better town centre
THE BEST ANSWER IS
EEF — external marketplace and social conditions the project must respond to but cannot change.
IF THE QUESTION SAYS
Historical society conservation building regulations affecting the site
THE BEST ANSWER IS
EEF — a legal and regulatory constraint from outside the organisation; it becomes a compliance requirement.
IF THE QUESTION SAYS
An archive of past large infrastructure projects held by your company
THE BEST ANSWER IS
OPA — a knowledge base and historical information repository you can mine for estimates and lessons.
IF THE QUESTION SAYS
The approved vendor and contractor list, and the tenant selection process
THE BEST ANSWER IS
OPA — internal processes, policies and procedures the organisation maintains and the project must apply.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
63

## Slide 64
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
Assessing organisational culture — what to actually look at
1
Leadership, hierarchy and authority
How decisions get made and how far they must travel. This directly sets your realistic escalation lead time.
2
Shared vision, beliefs and expectations
What people believe the organisation is for. A project that contradicts this will meet quiet, persistent resistance.
3
Diversity, equity and inclusion practices
Whether varied perspectives are genuinely sought; this shapes team formation and the quality of risk identification.
4
Risk tolerance and appetite
How much uncertainty the organisation will accept determines your reserve levels and your response strategies.
5
Regulations, policies and code of conduct
The formal rules of the road, including the ethical standards the team is expected to uphold without supervision.
6
Motivation and reward systems
What behaviour actually gets rewarded. If individuals are rewarded, a team incentive scheme will not stick.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
64

## Slide 65
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
Why change management belongs to the project manager
Organisational change requires individual change — a delivered output that nobody adopts has produced exactly zero value.
YOU ARE A CHANGEMAKER
Whether or not your organisation has a PMO, the project manager is the person driving change into the business.
TAILOR THE STRATEGY
Change approach must fit the circumstances, the people affected and the timing — there is no universal script.
USE A ROBUST APPROACH
Structured models such as ADKAR give you a checklist you can measure adoption against, not just good intentions.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
65

## Slide 66
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
The ADKAR model — five milestones an individual must reach
STEP 1
Awareness
The person understands why the change is needed. Address this with communication from a credible, senior sponsor.
STEP 2
Desire
The person chooses to support the change. Address this by making the personal 'what's in it for me' explicit and honest.
STEP 3
Knowledge
The person knows how to change. Address this with training, documentation and worked examples.
STEP 4
Ability
The person can demonstrate the new skills and behaviours. Address this with coaching, practice time and hands-on support.
STEP 5
Reinforcement
The change sticks. Address this with recognition, metrics and removal of the old way of working.
Diagnostic power: if adoption is failing, find the first milestone the person has not reached. More training will never fix a Desire problem.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
66

## Slide 67
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
Plan for change — the practical activities to build into your plan
1
Define readiness activities
Specify the knowledge transfer, training and readiness work required to implement the change the project brings.
2
Run an attitudinal survey
Find out how affected people actually feel before go-live, so resistance is measured rather than assumed away.
3
Create an information campaign
Familiarise people with the coming change over time; a single announcement email is not a communication plan.
4
Be open about effects
Transparent about the potential negative effects too — hidden bad news destroys the trust the change depends on.
5
Create a rollout plan
Sequence adoption by group, region or business unit so support capacity matches the number of people changing at once.
6
Measure adoption
Define adoption metrics up front and track them after go-live; benefits realisation depends on them, not on delivery.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
67

## Slide 68
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
When the organisation changes around your project
1
Reorganisations
A new reporting structure can remove your sponsor or reassign your team mid-flight; re-confirm authority immediately.
2
Strategy or priority shifts
A change in strategic direction can reprioritise value, including removing deliverables you have already built.
3
New deliverables demanded
Internal business changes frequently create a need for deliverables that were never in the approved baseline.
4
Process changes
New internal processes may change how you must procure, hire, report or release — check them before you are blocked.
5
Stay informed
The PM, sponsor or product owner must be familiar with business plans, reorganisations and other internal activity.
6
Recommend options
Assess the impact, then recommend options for changes to the project rather than presenting a single fait accompli.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
68

## Slide 69
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Project governance
The framework of structures, rules, procedures, reporting and ethics within which project decisions are legitimately made.
SINGLE ACCOUNTABILITY
Governance offers one clear point of accountability for the project, so decisions do not orbit unowned.
SPANS THE LIFE CYCLE
It encompasses the whole project life cycle, from authorisation through phase gates to closure.
ALREADY EXISTS
Governance is typically already in place — established by a PMO or aligned to organisational policy; you inherit it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
69

## Slide 70
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
The governance board and what it is responsible for
1
Who sits on it
Typically the project sponsor, senior managers from affected business units, and PMO resources; sometimes customer representatives.
2
Provides oversight
Independent oversight of whether the project remains viable, compliant and aligned to the strategy that funded it.
3
Reviews key deliverables
Formally reviews and accepts major deliverables at defined checkpoints rather than only at the very end.
4
Guides project decisions
Provides direction on decisions that exceed the project manager's delegated authority or cross business unit boundaries.
5
Approves changes above threshold
Acts as, or feeds into, the change control board for changes larger than the PM can approve alone.
6
Governance varies
Its type and intensity depend on the project's strategic importance, constraints and external oversight requirements.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
70

## Slide 71
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Governance defines escalation — the thresholds decision path
STEP 1
Detect the deviation
An issue, risk or change is identified that may push the project outside its agreed tolerance.
STEP 2
Test against threshold
Compare the impact to the documented tolerance for cost, schedule, scope, quality and risk.
STEP 3
Within threshold
Work with the team to find a resolution and record the decision; do not consume sponsor attention unnecessarily.
STEP 4
Outside threshold
Escalate to the stakeholder who is authorised to act, with options and a recommendation, not just a problem.
STEP 5
Record and communicate
Log the decision, update the plan and registers, and inform everyone affected by the outcome.
Escalating everything makes you look incapable; escalating nothing makes you look reckless. The written threshold is what makes the difference defensible.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
71

## Slide 72
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Defining project success metrics that governance can act on
Schedule performance
SPI = EV ÷ PV
Below 1.00 means the project is earning value more slowly than planned; a common governance threshold is SPI below 0.90.
Cost performance
CPI = EV ÷ AC
Below 1.00 means each dollar spent is buying less value than planned; often escalated when CPI falls below 0.90.
Benefit realisation
BRR = Actual ÷ Planned benefit
Measured after transition to operations; it is the metric that proves the business case was real, not merely persuasive.
Return on investment
ROI = (Benefit − Cost) ÷ Cost
The financial justification governance used to fund the project; re-check it whenever scope or cost changes materially.
Compliance level
% requirements evidenced
The share of identified compliance requirements with current, auditable evidence — the measure ECO T2 asks for.
ECO Business Environment T1 explicitly requires you to define success metrics and escalation thresholds. Vague metrics make governance ceremonial.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
72

## Slide 73
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Governance checkpoints: phase gates in a predictive project
1
Concept gate
Is the idea worth investigating? The business case is outline only and the estimate is order-of-magnitude.
2
Planning gate
Is the plan credible and funded? Baselines are approved and the estimate tightens to a definitive range.
3
Build gate
Is the solution being produced to spec? Design is frozen and major deliverables are formally reviewed.
4
Readiness gate
Is the organisation ready to receive it? Testing, training and compliance evidence are confirmed.
5
Closure gate
Have benefits started and is everything transitioned? Contracts, finances and lessons learned are closed out.
At every gate the decision is one of four: continue, continue with modification, hold and re-plan, or terminate. 'Continue because we have already spent the money' is the sunk cost fallacy.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
73

## Slide 74
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Project phase relationships — sequential versus overlapping
SEQUENTIAL PHASES
One phase completes before the next begins
Each phase ends at a gate that must be passed to continue
Lowest risk of rework because each stage is confirmed before build
Longest overall duration — no phase runs in parallel
Preferred where safety, regulation or irreversibility dominates
Clearest governance because decisions are discrete events
Change late in the sequence is the most expensive kind
OVERLAPPING PHASES
The next phase starts before the prior one ends
Known as fast tracking; used to compress the total schedule
Increases risk of rework because assumptions may prove wrong
Requires far more communication between the overlapping teams
Governance gates become partial or conditional approvals
Common in construction and product development under time pressure
The PM must explicitly accept and reserve for the rework risk
In adaptive delivery, the equivalent checkpoint is the sprint review — governance moves from a rare heavyweight gate to a frequent lightweight inspection of a working increment.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
74

## Slide 75
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Applying governance in predictive versus adaptive projects
PREDICTIVE GOVERNANCE
Few, heavy, document-based checkpoints
Phase gate reviews at defined milestones in the schedule
Evidence is documentation: plans, designs, test reports, sign-offs
Change control board approves deviations from the baseline
Status reported against percentage complete and earned value
Escalation follows a documented threshold and hierarchy
Benefits are typically confirmed after the whole project closes
ADAPTIVE GOVERNANCE
Many, light, product-based checkpoints
Sprint review at the end of every timebox, with stakeholders present
Evidence is a working increment that can be inspected directly
The Product Owner reprioritises the backlog instead of raising CRs
Status reported through burndown, velocity and cumulative flow
Impediments escalated immediately by the team facilitator
Benefits can be measured from the first released increment
The governance obligation is identical in both; only the frequency, the artefacts and the evidence change. Regulated industries still require agile teams to produce audit trails.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
75

## Slide 76
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Value-based delivery — the reason the project exists
Value is the worth, importance or usefulness of the output to the organisation and its stakeholders — not the volume of work completed.
IDENTIFY VALUE
Agree the value components with key stakeholders early, in measurable terms, so 'success' is not decided retrospectively.
PRIORITISE BY VALUE
Order the work by value and stakeholder feedback so the most valuable capability is delivered first.
VERIFY MEASUREMENT
Confirm a measurement system is in place to track benefits — you cannot claim value you never measured.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
76

## Slide 77
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Delivering and evaluating project value
STEP 1
Identify components
Work with key stakeholders to name the value components and how each will be recognised.
STEP 2
Prioritise the work
Order the backlog or scope by value and stakeholder feedback rather than by ease or by who shouted loudest.
STEP 3
Deliver incrementally
Assess every opportunity to release value earlier in smaller pieces rather than banking it all to the end.
STEP 4
Measure benefits
Verify the measurement system is live and read it; track actual benefit against the business case forecast.
STEP 5
Re-examine value
Continually examine whether the business value still justifies the remaining investment, and re-plan if not.
A project that is on time and on budget but delivers no measured benefit has failed. PMI's value-delivery view treats the business case as a live document, not an entry ticket.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
77

## Slide 78
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Project compliance — who is responsible for what
1
External standards
Government regulations, industry standards, privacy law and any licensing the product or the organisation requires.
2
Internal standards
Corporate policies, the quality management system, the code of conduct and the organisation's own methodology.
3
The PMO's role
Monitors compliance at organisational level, maintains the standards and audits projects against them.
4
The project team's role
Responsible for compliance in project activity — quality of processes and deliverables, and the work done by vendors.
5
Procurement compliance
Vendor work must meet the same obligations; contracts must pass the requirement down and give you audit rights.
6
The PM's stewardship
Compliance stewardship is your personal responsibility — it is an ethical obligation under the PMI Code of Conduct.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
78

## Slide 79
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Classifying compliance categories
Category | Typical requirements | Consequence of failure
Environmental | Emissions limits, waste handling, environmental impact assessment, site remediation | Fines, forced remediation, loss of operating licence, reputational damage
Workplace health and safety | Risk assessments, permits to work, protective equipment, incident reporting | Injury, prosecution of individuals, stop-work orders, insurance loss
Ethical and anti-corruption | Anti-bribery policy, conflict of interest declarations, gift registers, procurement fairness | Criminal liability, contract voiding, blacklisting from public tenders
Data protection and security | Consent, data residency, encryption, breach notification, access control | Regulatory fines, breach notification cost, customer attrition
Social responsibility | Labour standards in the supply chain, accessibility, inclusion, community obligations | Reputational harm, activist and investor pressure, contract loss
Quality and process | Standards conformance, documented process rigour, traceability of test evidence | Rework, product recall, refused acceptance, warranty exposure
Categories vary with industry, solution scope and the organisation's unique legal and regulatory exposure — classify them for your project, not from a template.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
79

## Slide 80
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Confirming compliance requirements for your project
1
Legal and regulatory constraints
Requirements for specific practices, mandatory standards, privacy laws and rules for handling sensitive information.
2
Where compliance is owned
Identify who in the organisation handles compliance — legal, quality, security, or an external regulator's inspector.
3
The quality policy
Understand the organisation's quality policy and how much process rigour and quality control it demands of this project.
4
Tailor the rigour
How much control is genuinely relevant here? A safety-critical system and an internal reporting tool do not need the same rigour.
5
Awareness across the team
Confirm the team and stakeholders actually know the compliance matters that apply — assumed knowledge is a common failure.
6
Evidence, not intention
Every requirement needs a named owner, a control and auditable evidence that the control is actually operating.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
80

## Slide 81
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Prioritising threats to compliance
Monitor closely
Severe but unlikely — for example a major data breach. Maintain preventive controls and a tested response plan.
Act immediately
Severe and likely — for example missing a known regulatory deadline. Escalate and fund a response now.
Accept and log
Minor and unlikely — record in the register, review periodically, and do not spend scarce control effort here.
Fix the process
Minor but frequent — for example repeated missing sign-offs. Correct the underlying process, not each instance.
LIKELIHOOD OF OCCURRING → high
SEVERITY OF CONSEQUENCE → high
Analyse the consequences of non-compliance before choosing the response, and measure the extent to which the project is compliant on a defined cadence.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
81

## Slide 82
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Methods that support compliance through the project
STEP 1
Documentation
Maintain a compliance register of requirements, owners, controls and evidence, updated as obligations change.
STEP 2
Risk planning
Prioritise compliance risks explicitly in the risk register with named responses, not as generic assumptions.
STEP 3
Compliance council
Convene quality and audit specialists plus relevant legal and technical experts to rule on grey areas.
STEP 4
Compliance audit
Run a formal audit at defined checkpoints to test that controls actually operate as designed.
STEP 5
Stewardship
Model and enforce compliance behaviour in the team every day — it is ultimately your personal responsibility.
Measure compliance the way you measure schedule: the percentage of identified requirements with current evidence, trended over time and reported to governance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
82

## Slide 83
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Sustainability is now a compliance and a value dimension
The 2026 ECO makes sustainability an explicit information requirement, a quality obligation and a category of project risk.
ENVIRONMENTAL
Carbon footprint of the solution, energy and water use, materials, waste and end-of-life disposal of what you build.
SOCIAL
Labour conditions across the supply chain, accessibility of the deliverable, and impact on the surrounding community.
GOVERNANCE
Transparent reporting of sustainability claims, ethical procurement, and avoidance of greenwashing in benefit claims.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
83

## Slide 84
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Where sustainability appears in the 2026 ECO
ECO reference | What it requires | What you actually do
Process T1 — integrated plan | Determine critical information requirements, explicitly including sustainability | Add sustainability criteria to the plan and to the definition of done
Process T7 — quality | Manage cost of quality and sustainability together | Cost sustainable options in the business case rather than as an afterthought
Business Env T2 — compliance | Confirm sustainability among the compliance requirement categories | Register environmental and social obligations with owners and evidence
Business Env T5 — risk | Execute risk responses for security and sustainability risks | Log sustainability risks in the register with real, funded responses
Business Env T8 — external change | Survey regulatory change in the external environment | Track emerging disclosure and reporting regulation affecting the deliverable
Exam framing: sustainability is treated as a legitimate constraint and benefit, so 'ignore it because it is not in scope' is never the best answer.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
84

## Slide 85
ECO BUSINESS ENV T8 · EVALUATE EXTERNAL BUSINESS ENVIRONMENT CHANGES
AI in project management — where it genuinely helps
1
Estimation
Models trained on historical project data produce range estimates and flag where your estimate diverges from comparable past work.
2
Risk detection
Pattern analysis across schedule, issue logs and communications surfaces emerging risks earlier than a monthly review would.
3
Status reporting
Automated generation of status narratives from tool data, freeing PM time for stakeholder work rather than slide assembly.
4
Schedule optimisation
Scenario simulation across thousands of resource and sequence permutations to test compression options before committing.
5
Requirements analysis
Clustering and de-duplicating large volumes of stakeholder input, and flagging ambiguous or untestable requirements.
6
Meeting and knowledge capture
Transcription, action extraction and searchable project memory that makes lessons learned findable rather than archived.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
85

## Slide 86
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Governing AI use on your project — the risks you own
1
Data confidentiality
Client data, contracts and personal information pasted into external tools may leave your control and breach your obligations.
2
Accuracy and hallucination
Generated estimates, text and analysis can be confidently wrong; a human must own and verify anything that reaches a stakeholder.
3
Bias in the training data
A model trained on past projects reproduces past bias — in vendor selection, in estimating, and in performance judgement.
4
Transparency and disclosure
Stakeholders should know when analysis or reporting they rely on was machine-generated; concealment is an ethics failure.
5
Accountability stays human
Delegating a task to AI never delegates the accountability; the project manager remains answerable for the decision.
6
Regulatory exposure
AI-specific regulation is emerging quickly — treat it as an external environment change to survey under ECO T8.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
86

## Slide 87
ECO BUSINESS ENV T7 · SUPPORT ORGANIZATIONAL CHANGE
Introducing AI into your project practice responsibly
STEP 1
Define the use case
Name the specific decision or task AI will support, and the measurable improvement you expect from it.
STEP 2
Check policy and law
Confirm what your organisation's AI policy, contracts and applicable regulation permit before any data moves.
STEP 3
Classify the data
Determine what data may be used, where it may be processed, and what must never leave your environment.
STEP 4
Pilot with a human in the loop
Run the AI output alongside the existing method and compare; never switch over blind.
STEP 5
Measure and govern
Track accuracy and benefit, disclose usage to stakeholders, and review at the governance checkpoint.
AI adoption is itself an organisational change project. Everything you learned about ADKAR applies to getting your own team to use it well.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
87

## Slide 88
EXAM FOCUS
Exam focus: Business Environment traps
IF THE QUESTION SAYS
A new law is announced that affects your project mid-execution
THE BEST ANSWER IS
Assess the impact on the project first, then raise a change request through the defined governance path.
IF THE QUESTION SAYS
An issue arises that exceeds your documented tolerance level
THE BEST ANSWER IS
Escalate to the stakeholder authorised to act, presenting options and a recommendation — do not decide alone.
IF THE QUESTION SAYS
A stakeholder asks you to skip a compliance step to hit the date
THE BEST ANSWER IS
Refuse and escalate. Compliance stewardship is non-negotiable and is an ethical obligation under the Code of Conduct.
IF THE QUESTION SAYS
The organisation reorganises and your sponsor is replaced
THE BEST ANSWER IS
Assess the impact on the project, then re-confirm the charter, authority and priorities with the new sponsor.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
88

## Slide 89
EXAM FOCUS
Exam focus: approach, governance and value traps
IF THE QUESTION SAYS
Requirements are unclear and are expected to keep evolving
THE BEST ANSWER IS
Recommend an adaptive or hybrid approach with short feedback loops — not a longer, more detailed requirements phase.
IF THE QUESTION SAYS
The sponsor asks why the project should continue after a market shift
THE BEST ANSWER IS
Re-examine the business value against the remaining investment and present the options, including terminating.
IF THE QUESTION SAYS
A team wants to drop retrospectives because they feel unproductive
THE BEST ANSWER IS
Fix the retrospective, do not remove it — check whether actions are actually reaching the next sprint backlog.
IF THE QUESTION SAYS
You are told 'we are agile so we do not need documentation'
THE BEST ANSWER IS
Wrong. Agile values working product over comprehensive documentation; regulated projects still require compliance evidence.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
89

## Slide 90
ECO BUSINESS ENV T1 · DEFINE AND ESTABLISH PROJECT GOVERNANCE
Where Business Environment sits in the July 2026 exam
Chart: 
| People (33%) | Process (41%) | Business Environment (26%)
Share of scored questions | 33 | 41 | 26
WHAT IT TELLS YOU
Business Environment is roughly 44 of the 170 scored questions — too many to treat as a side topic.
Its eight tasks cover governance, compliance, change control, impediments, risk, improvement, org change and external change.
This topic delivers T1, T2, T7 and T8; the remaining tasks appear in Topics 5 and 6 of this course.
About 40% of the exam is predictive and 60% adaptive or hybrid, so answer in the context each scenario states.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
90

## Slide 91
RECAP
Topic 1 recap — Business Environment
1
A project is temporary and unique
It delivers change and business value, and ends when objectives are met or are shown to be unachievable.
2
Triple constraint and tailoring
Scope, time and cost are joined; tailor process, artifacts and methods to the context rather than applying a template.
3
Two life cycles, five approaches
The project life cycle is the phases; the development life cycle is predictive, iterative, incremental, agile or hybrid.
4
Agile is incremental plus iterative
Four Manifesto values and twelve principles; Scrum supplies the roles, events and artifacts most teams actually use.
5
EEFs constrain, OPAs are reusable
You conform to EEFs; you apply and then update OPAs — updating them is an explicit ECO obligation.
6
Change needs individuals to change
ADKAR gives five milestones — awareness, desire, knowledge, ability and reinforcement — to diagnose adoption failure.
7
Governance sets thresholds
Escalate outside tolerance with options; resolve inside tolerance with the team. Phase gates decide go, change, hold or kill.
8
Compliance and sustainability are owned by you
Classify requirements, analyse threats, evidence controls, and treat sustainability as both constraint and benefit.
9
Value, not activity, defines success
Prioritise by value, deliver incrementally, verify a benefits measurement system exists and read it.
10
AI helps but never takes accountability
Use it for estimation, risk detection and reporting under an explicit policy, with a human verifying every output.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
91

## Slide 92
WHAT YOU WILL BUILD
Hands-on Labs — Topic 1
1
Lab 01. PMP Exam Orientation and 35-PDU Study Plan
All domains · LO1 · 20 min in class + 25 min self-study
Produces: Personal study plan, Domain self-assessment
2
Lab 02. PESTLE and TECOP External Environment Scan
BE T8 · LO1 · 20 min in class + 25 min self-study
Produces: PESTLE scan, TECOP risk themes
3
Lab 03. EEF/OPA Inventory with Governance and Escalation Thresholds
BE T1 · LO1 · 20 min in class + 25 min self-study
Produces: EEF/OPA inventory, Escalation threshold table
4
Lab 04. Compliance, Sustainability and AI Governance Register
BE T2 · LO4 · 20 min in class + 25 min self-study
Produces: Compliance register, AI governance controls
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
92

## Slide 93
HANDS-ON ACTIVITY
Lab 01. PMP Exam Orientation and 35-PDU Study Plan
Case study: Contoso Training Portal Upgrade. All domains · LO1. Produces Personal study plan, Domain self-assessment.
20 min in class
1
Record your PMP eligibility route: degree plus 36 months leading projects, or diploma plus 60 months, and confirm the 35 contact hours this course supplies.
2
Score yourself 1-5 on each of the three ECO domains — People, Process and Business Environment — to expose where your knowledge is thinnest.
3
Weight your available study hours by the exam percentages: Process 41%, People 33%, Business Environment 26%.
4
Block an eight-week study calendar with named topics per week, not vague 'revision' entries.
5
Schedule three full 180-question mock exams into that calendar, spaced at weeks 4, 6 and 8.
6
Write down your target exam date and work backwards to confirm the plan is actually achievable.
DELIVERABLE
Personal study plan, Domain self-assessment
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
93

## Slide 94
HANDS-ON ACTIVITY
Lab 02. PESTLE and TECOP External Environment Scan
Case study: Contoso Training Portal Upgrade. BE T8 · LO1. Produces PESTLE scan, TECOP risk themes.
20 min in class
1
List the Contoso project's external drivers under each PESTLE heading: political, economic, socio-cultural, technological, legal, environmental.
2
Open the Mind Mapping tool and branch each PESTLE factor into the specific effect it has on the training portal project.
3
Repeat the scan using TECOP — technical, environmental, commercial, operational, political — and note which factors only TECOP surfaced.
4
Rate every factor for likelihood and impact on a 1-5 scale, then rank them.
5
Identify the three factors most likely to force a scope or schedule change.
6
Write a one-paragraph environmental summary suitable for the project charter's assumptions and constraints section.
DELIVERABLE
PESTLE scan, TECOP risk themes
TOOL
Mind Mapping
alfredang.github.io/mindmapping/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
94

## Slide 95
HANDS-ON ACTIVITY
Lab 03. EEF/OPA Inventory with Governance and Escalation Thresholds
Case study: Contoso Training Portal Upgrade. BE T1 · LO1. Produces EEF/OPA inventory, Escalation threshold table.
20 min in class
1
Inventory the enterprise environmental factors constraining Contoso: existing systems, culture, staff capability, market and regulation.
2
Inventory the organisational process assets available to reuse: templates, historical data, procurement rules, lessons learned.
3
Classify each item explicitly as EEF or OPA and justify the classification in one line — this is a heavily examined distinction.
4
Define the governance structure: who sponsors, who sits on the steering committee, and what the project manager may decide alone.
5
Set numeric escalation thresholds for cost variance, schedule slip and risk severity, stating what triggers escalation to whom.
6
Define the phase gates and the go / no-go criteria applied at each.
DELIVERABLE
EEF/OPA inventory, Escalation threshold table
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
95

## Slide 96
HANDS-ON ACTIVITY
Lab 04. Compliance, Sustainability and AI Governance Register
Case study: Contoso Training Portal Upgrade. BE T2 · LO4. Produces Compliance register, AI governance controls.
20 min in class
1
Identify every compliance requirement touching the portal: data protection, accessibility, financial audit, and workplace health and safety.
2
Classify each requirement into a compliance category and name its owner inside the organisation.
3
Assess the consequence of non-compliance for each — financial penalty, reputational damage, or inability to launch.
4
Add sustainability requirements: energy use of the hosting platform, e-waste from decommissioned hardware, and supplier sustainability criteria.
5
Register the AI governance controls: where AI is used in the project, what data it consumes, and how its output is reviewed before acting on it.
6
Define how compliance will be MEASURED, not merely asserted — the 2026 outline expects a metric.
DELIVERABLE
Compliance register, AI governance controls
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
96

## Slide 97
02
TOPIC
Start the Project
Turning an idea into an authorised project: the business case that justifies it, the charter that authorises it, the stakeholders who judge it, and the team that will build it.
1
Project integration and the Develop Project Charter process
2
Business value, business case, cost-benefit and benefits management
3
Identify, analyse and prioritise stakeholders
4
Align and manage stakeholder expectations (ECO 2026 People T5/T6)
5
Form the team, agree the team charter and kick off
6
Recommend the development approach for the integrated plan
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
97

## Slide 98
TOPIC 2 LEARNING OUTCOMES
What You Will Be Able To Do After Topic 2
1
Draft a project charter
Write a charter that names the sponsor and PM, states measurable objectives, and authorises the PM to apply organisational resources.
2
Justify a project financially
Build a cost-benefit analysis and read payback, NPV, IRR, ROI and BCR well enough to defend the selection decision to a steering committee.
3
Identify every stakeholder
Work an organisation breakdown structure and document analysis to find who is affected, then record them properly in a stakeholder register.
4
Analyse and prioritise
Apply power/interest and power/influence grids, the stakeholder cube and the salience model to decide who gets how much of your attention.
5
Align expectations
Facilitate discussions that surface conflicting expectations early and converge them onto one agreed set of project objectives.
6
Start the team well
Co-create a team charter, set ground rules and run a kick-off that leaves everyone sharing the same vision of success.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
98

## Slide 99
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Why initiation deserves this much time
Projects are not lost at the end. They are lost at the start.
Wrong problem
A project with no validated business case delivers perfectly against an objective nobody needed.
Wrong people
A stakeholder discovered in month six brings requirements that should have shaped month one.
Wrong authority
Without a signed charter the PM has responsibility without the power to apply resources.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
99

## Slide 100
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Project Integration Management: The Unifying Discipline
1
What integration is
The work of identifying, defining, combining, unifying and coordinating the other knowledge areas so they behave as one system, not ten silos.
2
Why it exists
Scope, schedule, cost, quality, resources, communications, risk and procurement all trade against each other; someone must own the trade-off.
3
Who owns it
Integration is the one area the project manager cannot delegate — it is the definition of the PM role in the PMBOK Guide.
4
The through-line
A researched business case, an approved charter and a well-planned project management plan tie every decision back to business value.
5
The test of integration
Change a date and you can immediately state the cost, scope, quality and risk consequence — that is an integrated project.
6
The failure mode
Silo optimisation: each function hits its own target while the project as a whole misses the business outcome entirely.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
100

## Slide 101
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
The Key Benefits of Project Integration
1
Strategic alignment
Every deliverable can be traced upward to an organisational objective, so the project earns its funding rather than merely consuming it.
2
A single decision point
Competing demands from stakeholders arrive at one integrating role that can weigh them against the whole rather than a part.
3
Coherent baselines
Scope, schedule and cost baselines are built to be consistent with each other, so variance analysis measures reality rather than mismatch.
4
Controlled change
Changes are assessed for their ripple effect across all knowledge areas before approval, not discovered downstream.
5
Value assurance
Business value is examined throughout the life cycle, so a project whose case has evaporated can be stopped honestly.
6
Clean handover
Integration carries the project through to transition, so benefits are actually realised by operations after the team disbands.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
101

## Slide 102
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
From Idea to Authorised Project: The Initiation Flow
STEP 1
Need or opportunity
A market demand, regulation, technology shift or customer request creates pressure for change.
STEP 2
Business case
Economic feasibility is studied; costs, benefits and alternatives are documented for a decision.
STEP 3
Selection decision
Governance compares candidates using payback, NPV, IRR, ROI and strategic fit, then funds one.
STEP 4
Charter developed
The sponsor issues a charter naming the PM and authorising resources against stated objectives.
STEP 5
Stakeholders identified
Everyone affected is found, analysed and recorded before planning assumptions harden.
STEP 6
Kick-off
Team and stakeholders align on vision, roles and approach, and planning begins in earnest.
Exam cue: the charter is an OUTPUT of initiating, not of planning. Nothing in the project management plan may be baselined before the charter authorises the project to exist.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
102

## Slide 103
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Develop Project Charter — ITTO
Purpose: to produce a document that formally authorises the existence of the project and gives the project manager authority to apply organisational resources to project activities.
INPUTS
Business documents (business case, benefits management plan)
Agreements (contracts, MOUs, SLAs, letters of intent)
Enterprise environmental factors (market, standards, culture)
Organizational process assets (templates, historical data, policies)
TOOLS & TECHNIQUES
Expert judgement (strategy, industry, technical, legal)
Data gathering: brainstorming, focus groups, interviews
Interpersonal and team skills: conflict management, facilitation
Meetings — notably the charter workshop with sponsor and key stakeholders
OUTPUTS
Project charter — the authorising document
Assumption log — assumptions and constraints captured from day one
(The charter feeds every subsequent planning process)
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
103

## Slide 104
ECO PEOPLE T1 · DEVELOP A COMMON VISION
What the Project Charter Actually Does
1
Authorises the project
It is the formal statement that this project exists and may consume organisational resources — issued by a sponsor senior enough to fund it.
2
Empowers the project manager
It names the PM and states their authority level, converting a job title into the right to direct people, spend money and make decisions.
3
Defines rationale and need
It records why the organisation is doing this, so the reasoning survives sponsor turnover and mid-project pressure to change direction.
4
Verifies strategic alignment
It links the project explicitly to strategic goals, which is what makes the funding defensible at portfolio review.
5
Sets the shared vision
It gives every stakeholder one short reference for what success looks like, supporting ECO People T1 — develop a common vision.
6
Anchors change control
Later change requests are assessed against charter objectives; a change that breaks the charter needs sponsor, not PM, approval.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
104

## Slide 105
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
What Is Included in the Project Charter
Charter element | What goes in it | Why it matters
Names and roles | Project sponsor, project manager, key stakeholders and their authority | Removes ambiguity about who decides and who must be consulted
Project description | High-level product description plus preliminary requirements | Bounds the solution space before detailed requirements work
Measurable objectives | Objectives with success criteria that can be objectively tested | Makes acceptance at closure a measurement, not an argument
Business need | The problem or opportunity, plus financial goals or milestones | Preserves the 'why' when the 'what' comes under pressure
Summary schedule | High-level milestones and any externally imposed dates | Signals feasibility and exposes immovable constraints early
Assumptions and constraints | Boundaries, overall project risk, approval requirements, approved budget | Seeds the assumption log and the initial risk register
Exit criteria | Success criteria and the conditions under which the project is stopped | Makes cancelling a failing project a planned option, not a failure
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
105

## Slide 106
ECO PEOPLE T1 · DEVELOP A COMMON VISION
How a Charter Gets Approved
STEP 1
Draft with the sponsor
The PM facilitates; the sponsor owns the content and the authority behind it.
STEP 2
Validate with stakeholders
Key stakeholders confirm objectives and success criteria are the ones they will be judged on.
STEP 3
Governance review
Portfolio or steering body confirms strategic fit, funding and priority against other work.
STEP 4
Sponsor signs
Signature converts a proposal into an authorisation, releasing budget and named resources.
STEP 5
Publish and socialise
The charter is communicated widely so the vision is shared, not filed in a drawer.
The project manager does not approve their own charter. If an exam option has the PM signing off the charter, it is wrong — the sponsor or initiating authority signs.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
106

## Slide 107
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Business Value: The Six Reasons Organisations Fund Projects
1
Financial gain
Direct revenue increase or cost reduction, usually the easiest form of value to quantify and therefore the easiest to defend.
2
New customers
Access to a new segment, geography or channel, where the value is in the lifetime revenue of the relationship rather than the first sale.
3
Social benefit
Community, environmental or sustainability outcomes that build licence to operate — increasingly explicit in ECO 2026 sustainability language.
4
First to market
Speed itself is the value: capturing share, setting the standard or shaping customer expectations before competitors arrive.
5
Improvement
Technological or process uplift that raises capability, reduces cycle time or removes chronic defects in how work is done.
6
Regularization
Alignment or compliance with standards and regulations, where the value is the avoided penalty, avoided shutdown or preserved certification.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
107

## Slide 108
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Tangible vs Intangible Business Value
TANGIBLE VALUE
Countable, auditable, defensible in a business case
Monetary assets and direct revenue from new sales
Stockholder equity and improved market capitalisation
Utility, fixtures, tools and physical assets acquired
Market share expressed as a measurable percentage
Cost avoidance and hard headcount or licence savings
Measured cycle-time or defect-rate improvement
INTANGIBLE VALUE
Real but harder to measure — still must be tracked
Goodwill and brand recognition in the market
Public benefit, sustainability and community standing
Trademarks, patents and other intellectual property
Strategic alignment and organisational reputation
Employee capability, morale and retention
Customer satisfaction and loyalty
Both count. ECO Process T3 asks you to identify value components WITH key stakeholders and to verify a measurement system exists — including for the intangibles.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
108

## Slide 109
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
The Three Business Documents
1
Business case
The documented economic feasibility study that justifies the investment and establishes the benefits the project work is expected to deliver.
2
Cost-benefit analysis
The quantitative core of the business case: all costs against all benefits over a defined horizon, used to compare candidate projects.
3
Benefits management plan
How benefits will be created, maximised and sustained after delivery, with owners, metrics and time frames for realisation.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
109

## Slide 110
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Business Documents: Who Owns Them and When
OWNED BY THE SPONSOR / ORGANISATION
Created before the project — the PM is a consumer, not an author
The business case is developed by the sponsor or a business analyst
The benefits management plan is owned by a benefits owner
Both predate the charter and are inputs to Develop Project Charter
The PM may recommend updates but does not unilaterally change them
They are maintained beyond project closure into benefits realisation
USED BY THE PROJECT MANAGER
Consumed continuously to keep the project honest about value
Source the charter's rationale, objectives and success criteria
Test every significant change request against continued value
Feed the value discussion at each phase gate or stage review
Trigger an escalation when the business case no longer holds
Provide the acceptance and exit criteria used at closure
Exam cue: 'the business case no longer supports the project' means escalate to the sponsor for a stop/continue decision — not quietly re-plan.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
110

## Slide 111
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
How to Run a Cost-Benefit Analysis
STEP 1
Define the horizon
Fix the period over which costs and benefits will be counted, typically three to five years.
STEP 2
Enumerate all costs
Capital, implementation, licensing, training, change management and ongoing operating cost.
STEP 3
Quantify benefits
Revenue uplift, cost avoidance and quantified proxies for intangible benefits, per period.
STEP 4
Discount to present value
Apply the organisation's discount rate so future money is compared fairly with today's spend.
STEP 5
Compute the metrics
Payback period, NPV, IRR, ROI and benefit-cost ratio for the selection decision.
STEP 6
Test sensitivity
Re-run with pessimistic assumptions to see how fragile the conclusion really is.
Sunk costs are irrelevant to a go/no-go decision. Money already spent cannot be recovered by continuing; only future costs and future benefits belong in the analysis.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
111

## Slide 112
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
The Business Case as an Economic Feasibility Study
1
Documented, not verbal
It is a written study that can be reviewed, challenged and audited — an enthusiastic sponsor's confidence is not a business case.
2
Establishes the benefits
It states specifically what benefits the project work will produce, in units that can later be measured against reality.
3
Basis for authorisation
It provides the justification on which further project activities are authorised — no case, no charter, no funding.
4
Includes alternatives
Do nothing, buy, build and partial-scope options are compared, so the chosen route is a decision rather than a default.
5
States success criteria
Defines what 'it worked' will mean, which flows into charter objectives and eventually into acceptance at closure.
6
Is revisited, not filed
ECO Process T3 requires examining business value throughout the project, so the case is a live document across the life cycle.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
112

## Slide 113
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Benefits Management Plan — Required Contents
Element | What it specifies | Typical example
Target benefits | The value expected, expressed in measurable terms | Reduce order-processing cost by 18% per transaction
Strategic alignment | Which organisational objective the benefit serves | Supports the 'digital-first operations' strategic pillar
Time frame | When short-term and long-term benefits will be realised | 40% at go-live, full run-rate 12 months post-transition
Benefits owner | The accountable person who monitors and reports realisation | Head of Operations, named by the sponsor
Metrics | Direct and indirect measures used to demonstrate realisation | Cost per order, error rate, customer satisfaction score
Assumptions | Conditions that must hold for the benefits to appear | Volumes remain within +/-10% of forecast
Risks | Threats to benefit realisation, distinct from delivery risks | Operations does not adopt the new process after handover
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
113

## Slide 114
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
The Benefits Owner: An Accountability Beyond Delivery
1
Works alongside the PM
Partners with the project manager or team lead during delivery to ensure planned benefits are actively managed as they are delivered.
2
Owns the transition
Assists in transitioning the requested benefits to the receiving organisation so value is not lost at handover.
3
Establishes measurement
Ensures measurement metrics and methods are established, baselined and monitored — you cannot claim a benefit you never measured.
4
Reports realised value
Reports to management on the realised results of delivered benefits, often long after the project team has been released.
5
Who holds the role
Typically a business analyst, the sponsor or an operations manager — a business-side role, not a project-side one.
6
In adaptive contexts
The product owner is responsible for making sure the work reaps benefits for the organisation, prioritising the backlog by value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
114

## Slide 115
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Benefit Measurement Formulas You Must Recognise
Return on investment
ROI = (Benefit − Cost) / Cost
Expressed as a percentage. Bigger is better. Ignores the timing of cash flows entirely.
Benefit-cost ratio
BCR = Benefits / Costs
Greater than 1.0 means benefits exceed costs. Bigger is better; used to rank competing proposals.
Net present value
NPV = Σ CFt / (1+r)^t − C0
Today's value of all future cash flows minus the investment. Positive NPV means proceed; choose the highest.
Payback period
Payback = Cost / Annual net inflow
How long until you recover the investment. Smaller is better; ignores everything after payback.
Rule of thumb for the exam: financial-return measures (NPV, IRR, ROI, BCR) are 'bigger is better'; time and cost measures (payback period, opportunity cost) are 'smaller is better'.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
115

## Slide 116
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Benefit Measurement Methods Compared
Method | What it answers | Decision rule | Main weakness
Payback period | How fast do we get our money back? | Choose the shortest duration | Ignores all cash flow after payback and the time value of money
Opportunity cost | What is the value of the option we gave up? | Choose the option with the smaller opportunity cost | Depends entirely on which alternative you compare against
Net present value | What is this worth in today's dollars? | Choose the highest positive NPV | Highly sensitive to the discount rate chosen
Internal rate of return | What effective interest rate does it earn? | Choose the highest IRR above the hurdle rate | Misleads when comparing projects of very different sizes
Return on investment | What percentage return on money spent? | Choose the highest ROI | Ignores timing, duration and risk of the cash flows
Benefit-cost ratio | How many dollars of benefit per dollar spent? | Choose the highest ratio, must exceed 1.0 | Sensitive to whether an item is classed as cost or negative benefit
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
116

## Slide 117
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Payback Period: Cumulative Cash Flow of a $500k Project
Chart: 
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Project A cumulative ($k) | -500 | -320 | -140 | 60 | 260 | 460
Project B cumulative ($k) | -500 | -430 | -300 | -110 | 180 | 620
WHAT IT TELLS YOU
Project A crosses zero during year 3 — payback is roughly 2.8 years, the shorter and therefore preferred payback.
Project B pays back later but ends higher, so a payback-only rule would reject the project with more total value.
This is exactly why payback is never used alone: pair it with NPV, which counts everything after the crossover point.
Shorter payback also means less exposure to forecast error, which matters most in volatile business environments.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
117

## Slide 118
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
NPV of Four Competing Project Proposals
Chart: 
| Proposal A | Proposal B | Proposal C | Proposal D
NPV at 10% discount rate ($k) | 420 | 610 | -80 | 180
WHAT IT TELLS YOU
Proposal B has the highest NPV and is the correct selection on financial grounds alone.
Proposal C has a negative NPV — it destroys value and should not be funded regardless of how attractive it sounds.
NPV is additive across projects, which is why portfolios are built on NPV rather than on IRR or ROI percentages.
Financial ranking is only one input: strategic fit, risk and capacity can still override the highest NPV.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
118

## Slide 119
EXAM FOCUS
Exam Traps: Project Selection and Business Documents
IF THE QUESTION SAYS
Two projects, one has higher NPV and the other has shorter payback
THE BEST ANSWER IS
Choose the higher NPV — it accounts for the full value of every cash flow, not just the recovery point.
IF THE QUESTION SAYS
A large sum has already been spent and the project now looks unviable
THE BEST ANSWER IS
Ignore the sunk cost. Decide on future costs versus future benefits and escalate a stop recommendation to the sponsor.
IF THE QUESTION SAYS
You are asked who writes the business case
THE BEST ANSWER IS
The sponsor or business analyst — it exists before the project, and the PM is a consumer of it, not its author.
IF THE QUESTION SAYS
A stakeholder wants a change that breaks the charter objectives
THE BEST ANSWER IS
Escalate to the sponsor. The PM cannot approve a change that invalidates the authorising document.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
119

## Slide 120
ECO PEOPLE T1 · DEVELOP A COMMON VISION
The Project Vision Statement
1
Created by the sponsor
Written by the project sponsor or an executive, because vision requires the authority to commit the organisation to a direction.
2
Describes desired objectives
States clearly what the desired end state looks like, in language a non-specialist stakeholder can repeat accurately.
3
Shows strategic alignment
Makes explicit which organisational strategic goal this project advances, so the vision is anchored rather than aspirational.
4
Referred to throughout
Revisited at every major decision point to maintain alignment — a vision used once at kick-off is decoration.
5
Kept current
ECO People T1 requires keeping the vision current: when the business environment shifts, the vision is updated, not ignored.
6
Root-cause the drift
When people act inconsistently with the vision, break the situation down to find the root cause of the misunderstanding rather than blaming.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
120

## Slide 121
ECO PEOPLE T1 · DEVELOP A COMMON VISION
ECO People Task 1 — Develop a Common Vision
A vision only exists if the team can state it without reading it.
Help ensure it is shared
Co-create the vision with key stakeholders so they own it rather than receive it.
Promote it actively
Repeat the vision at stand-ups, reviews and steering meetings until it becomes the team's default language.
Keep it current
Revalidate the vision whenever strategy, market or sponsorship changes; a stale vision misdirects everyone.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
121

## Slide 122
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Predictive Charter vs Agile Team Charter
PREDICTIVE PROJECT CHARTER
Authorisation document, issued top-down by the sponsor
Purpose: authorise the project and empower the PM
Author: sponsor or initiating authority signs it
Contains measurable objectives and approved budget
Contains summary milestones and approval requirements
Changes require formal sponsor approval
Written once, referenced throughout the life cycle
AGILE TEAM CHARTER
Working agreement, created bottom-up by the team itself
Purpose: define how this team will work together
Author: the whole team, facilitated by the servant leader
Team vision or mission in the team's own words
Team roles, responsibilities and the stakeholders served
Team values and the ceremonies the team commits to
Revisited at retrospectives and amended as the team learns
They are complements, not alternatives. A hybrid project commonly has both: a signed project charter for authority and a team charter for day-to-day working agreements.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
122

## Slide 123
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Choosing the Development Approach
Adaptive / Agile
Volatile requirements and unfamiliar technology. Deliver in short increments, inspect and adapt, expect the plan to change.
Iterative
Technology is unfamiliar but the goal is clear. Prototype and refine the solution through repeated passes.
Incremental
Technology is well understood but stakeholders need value early. Ship usable slices in sequence.
Predictive / Waterfall
Stable requirements and proven technology. Plan fully, baseline, and control change through a formal process.
REQUIREMENTS STABILITY → high
high ← TECHNICAL UNCERTAINTY
ECO Process T1 asks you to assess project needs, complexity and magnitude, then RECOMMEND an approach. The recommendation must be justified by the project's characteristics, not by fashion.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
123

## Slide 124
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Stakeholder Definition
A stakeholder is anyone affected — or who believes they are affected — by your project.
Perception counts
Someone who merely believes they are affected can still block you, so they are a real stakeholder.
The outcome we want
Productive relationships in which stakeholders actively support project objectives rather than merely tolerate them.
The five-step cycle
Identify, analyse, prioritise and engage stakeholders — then monitor their engagement continuously.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
124

## Slide 125
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
The Stakeholder Engagement Cycle
STEP 1
Identify
Find everyone affected using the OBS, document analysis, contracts and expert judgement.
STEP 2
Analyse
Assess each stakeholder's power, interest, influence, attitude and expectations of the project.
STEP 3
Prioritise
Classify with grids, the cube or the salience model to decide where engagement effort goes.
STEP 4
Engage
Execute the stakeholder engagement plan with tailored communication and relationship building.
STEP 5
Monitor
Track actual versus desired engagement and adjust strategies as relationships shift.
This cycle repeats. New stakeholders appear at every phase boundary, reorganisation and change of sponsor — identification is a continuous activity, not an initiating-phase task you complete once.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
125

## Slide 126
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Identify Stakeholders — ITTO
Purpose: to identify project stakeholders and analyse and document relevant information about their interests, involvement, interdependencies, influence and potential impact on project success.
INPUTS
Project charter (names sponsor and key stakeholders)
Business documents (business case, benefits management plan)
Project management plan (communications and risk management plans)
Project documents (change log, issue log, requirements documentation)
Agreements — contracting parties are always stakeholders
Enterprise environmental factors and organizational process assets
TOOLS & TECHNIQUES
Expert judgement on organisational politics and industry context
Data gathering: questionnaires and surveys, brainstorming
Data analysis: stakeholder analysis, document analysis
Data representation: stakeholder mapping and representation
Meetings — profile workshops with the sponsor and team
OUTPUTS
Stakeholder register — the central artefact of this process
Change requests (after the first pass)
Project management plan updates
Project documents updates (assumption log, issue log, risk register)
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
126

## Slide 127
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Stakeholder Identification in Practice
1
Start early, repeat often
Identify and analyse engagement early and throughout the project — the cost of a missed stakeholder rises steeply with every planning decision.
2
Use the OBS
Walk the organisational breakdown structure top to bottom to find the initial population of internal stakeholders systematically.
3
Mine the documents
Contracts, regulations, prior lessons learned and the business case each name parties who have a stake in the outcome.
4
Ask the stakeholders you have
Snowball sampling: every stakeholder you interview can name two more you had not considered, especially external ones.
5
Look outward deliberately
Regulators, unions, communities, suppliers and end users rarely appear on an internal org chart but can stop a project cold.
6
Record it, do not remember it
Everything found goes into the stakeholder register so the knowledge survives handover and team changes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
127

## Slide 128
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
The Stakeholder Register — Fields and Purpose
Field | What you record | Why you need it
Name and organisation | Identity, department, employer and contact details | Basic addressability — you cannot engage whom you cannot reach
Role on the project | Sponsor, customer, end user, regulator, supplier, team member | Sets the default expectations and rights of that party
Power | Authority to grant, withhold or reverse decisions and resources | Determines how much of the PM's personal attention is warranted
Interest | How much the stakeholder cares about the project outcome | Predicts how actively they will seek involvement
Influence | Ability to affect the project through others, formally or informally | Reveals people with little authority but high real effect
Expectations and needs | What this stakeholder believes success looks like for them | The raw material for aligning expectations (ECO People T5)
Communication requirements | Preferred content, format, channel, frequency and language | Drives the communications management plan
Attitude / classification | Unaware, resistant, neutral, supportive or leading | Feeds the stakeholder engagement assessment matrix
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
128

## Slide 129
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Typical Project Stakeholders
1
End users
The people who will actually operate the product daily; their adoption decides whether benefits are realised or the system is worked around.
2
Customers
Those who acquire or pay for the product — sometimes but not always the same people as the end users, a distinction worth making explicit.
3
Employees and the team
Those doing the work and those whose jobs change because of it; both populations need engagement, not just the project team.
4
Sponsors and managers
The sponsor funds and champions; functional managers control the resources you must borrow and can quietly withdraw them.
5
Business partners and suppliers
Contractors, vendors and integrators whose commitments become your constraints and whose performance becomes your risk.
6
Government and community
Regulators, standards bodies and affected communities who cannot be negotiated with but must be satisfied.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
129

## Slide 130
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Organisation Breakdown Structure as an Identification Tool
1
What an OBS is
A hierarchical decomposition of the organisation by department and reporting line, mirroring how the WBS decomposes the work.
2
Why it works
Walking it forces a systematic sweep of every function rather than listing the stakeholders who happen to be top of mind.
3
Map work to units
Cross the OBS against the WBS to see which organisational unit owns each work package — those owners are stakeholders by definition.
4
Find the silent affected
Departments that receive the output but do no project work — finance, legal, support — surface only through this sweep.
5
Its blind spot
An OBS only shows internal parties; regulators, customers and community groups must be found by other means.
6
Keep it alive
Reorganisations change the OBS mid-project, which is a trigger to re-run stakeholder identification.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
130

## Slide 131
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Stakeholder and Communications Artefacts
Artefact | What it holds | When it is used
Stakeholder register | Identity, role, power, interest, influence, expectations, attitude | Created in Identify Stakeholders; updated continuously
Stakeholder engagement plan | Strategies and actions to move each stakeholder to the desired level | Part of the project management plan; drives daily engagement
Communications management plan | Who receives what information, in what format, how often, by whom | Executed throughout; the operational half of engagement
Stakeholder engagement assessment matrix (SEAM) | Current (C) versus desired (D) engagement per stakeholder | Reviewed in Monitor Stakeholder Engagement to target effort
Assessment grids and models | Power/interest, power/influence, impact/influence, cube, salience | Used during analysis to prioritise and classify
Issue log | Stakeholder-raised issues, owners and resolution status | Continuous — unresolved issues erode engagement fast
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
131

## Slide 132
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Assess Stakeholders: Data Gathering and Data Analysis
DATA GATHERING
Collecting raw information about stakeholders
Questionnaires and surveys reach large, dispersed populations cheaply
Surveys work well for end-user expectations across many sites
Brainstorming with the team surfaces stakeholders nobody listed
Brainwriting lets quieter contributors add names without pressure
Interviews go deep with high-power individuals
Focus groups expose disagreements between stakeholder groups
DATA ANALYSIS
Turning raw information into engagement decisions
Stakeholder analysis produces a list of interests and their weight
It classifies each party by power, interest, influence and attitude
Document analysis mines charters, contracts and lessons learned
Root-cause analysis explains WHY a stakeholder is resistant
Assumption and constraint analysis tests what we believe about them
Output feeds directly into the register and the engagement plan
Gathering tells you who they are and what they say they want; analysis tells you what to do about it. The exam frequently asks you to sort a technique into the correct bucket.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
132

## Slide 133
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Data Representation: Five Ways to Map Stakeholders
1
2D grid: power/interest
Classifies by authority to act against level of concern — the default grid, giving manage-closely, keep-satisfied, keep-informed, monitor.
2
2D grid: power/influence
Classifies by formal authority against active involvement, useful when informal networks matter more than the org chart.
3
2D grid: impact/influence
Classifies by ability to cause change against active involvement, best when the risk is disruption rather than opposition.
4
3D grid: the stakeholder cube
Combines three dimensions at once so a stakeholder is a point in a volume, capturing combinations a flat grid flattens away.
5
Salience model
Classifies by power, legitimacy and urgency, producing seven classes and identifying the definitive stakeholder who has all three.
6
Directions of influence
Classifies by where the stakeholder sits relative to the PM — upward, downward, sideward or outward — shaping the engagement style.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
133

## Slide 134
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Power / Interest Grid
Keep satisfied
High power, low interest. Sponsors' peers and senior executives. Brief them concisely and do not overload them; sudden interest is dangerous.
Manage closely
High power, high interest. The sponsor and key customers. Involve them in decisions, meet frequently and never surprise them.
Monitor
Low power, low interest. Peripheral departments. Minimal effort, but re-check periodically since positions change.
Keep informed
Low power, high interest. End users and subject experts. Communicate regularly; they are your best source of requirement detail.
INTEREST IN THE OUTCOME → high
high ← POWER OVER THE PROJECT
Power is the authority to impose your will. Interest is how much you care about the outcome. A stakeholder's position moves as the project progresses, so re-plot at every phase gate.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
134

## Slide 135
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Power / Influence Grid
Latent authority
High power, low involvement. Can intervene decisively but currently does not. Keep the relationship warm before you need it.
Decision makers
High power, high involvement. They both can and do shape the project. Engage constantly and build genuine trust here.
Bystanders
Low power, low involvement. Monitor for changes in either dimension rather than investing engagement effort now.
Opinion shapers
Low power, high involvement. No formal authority but they move opinion through networks. Underestimating them is a classic failure.
ACTIVE INVOLVEMENT (INFLUENCE) → high
high ← FORMAL AUTHORITY (POWER)
Power and influence are not the same thing. A respected long-serving engineer may have no authority and enormous influence — the power/influence grid exists precisely to expose that person.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
135

## Slide 136
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Impact / Influence Grid
High impact, low influence
Can force change to the project but is not currently involved — for example a regulator. Engage proactively before they act.
High impact, high influence
Can both cause change and is actively involved. This is where your engagement plan must be strongest and most personal.
Low impact, low influence
Little ability to change the project and little involvement. Standard project communications are sufficient here.
Low impact, high influence
Actively involved but cannot force change. Valuable allies and useful advocates — recruit them deliberately.
INFLUENCE — ACTIVE INVOLVEMENT → high
high ← IMPACT — ABILITY TO CAUSE CHANGE
Impact asks 'can they change the project?' Influence asks 'are they in the room?' The dangerous quadrant is high impact with low influence — they act without warning.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
136

## Slide 137
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
The Stakeholder Cube — Three Dimensions at Once
1
Why a cube
Two-dimensional grids lose information: two stakeholders can share a quadrant yet need completely different engagement approaches.
2
Dimension one: power
The stakeholder's level of authority to impose decisions on the project or withhold what the project needs.
3
Dimension two: interest
The degree to which the stakeholder cares about and attends to the project's outcome.
4
Dimension three: attitude
Whether the stakeholder is supportive, neutral or resistant — the dimension flat grids most often omit.
5
What it reveals
A high-power, high-interest, resistant stakeholder is a very different problem from a high-power, high-interest supporter.
6
How to use it
Treat each cell as a distinct engagement archetype and write a tailored strategy per archetype in the engagement plan.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
137

## Slide 138
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Salience Model — Power, Legitimacy, Urgency
Dominant (power + legitimacy)
Real authority and a proper claim, but no time pressure. Sponsors and steering members. Engage on a planned cadence.
Definitive (all three)
Power, legitimacy AND urgency together. The highest-salience class — act on their claims immediately and personally.
Discretionary (legitimacy only)
A proper claim but no power or urgency, such as a community group. Engagement here is a choice, often an ethical one.
Dependent (legitimacy + urgency)
A legitimate, pressing claim but no power to enforce it — end users. They depend on an advocate; often the PM.
LEGITIMACY — IS THE CLAIM APPROPRIATE? →
→ POWER TO IMPOSE WILL
Seven classes exist in total. The other three are single-attribute: Dormant (power only), Demanding (urgency only) and Dangerous (power + urgency but no legitimacy — coercive, watch closely).
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
138

## Slide 139
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
The Seven Salience Classes in Full
Class | Attributes held | Typical example | Engagement response
Dormant | Power only | A regulator not yet engaged | Monitor; the power can activate at any time
Discretionary | Legitimacy only | A community or charity group | Engage by choice; usually a reputational decision
Demanding | Urgency only | A vocal individual user | Acknowledge but do not let noise set priority
Dominant | Power + legitimacy | Sponsor, steering committee | Formal, planned, regular engagement
Dangerous | Power + urgency | A coercive group applying pressure | Manage carefully; escalate; involve governance
Dependent | Legitimacy + urgency | End users needing an advocate | Give them a voice through a powerful sponsor
Definitive | Power + legitimacy + urgency | Customer at a crisis point | Immediate, personal, highest-priority attention
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
139

## Slide 140
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Directions of Influence
1
Upward
Senior management, the sponsor and the steering committee. Engage with concise, decision-ready information and never surprise them in public.
2
Downward
The project team and specialists providing knowledge or skills. Engage by clarifying purpose, removing impediments and empowering decisions.
3
Sideward
Peers of the project manager and other middle managers who control the resources you borrow. Engage through negotiation and reciprocity.
4
Outward
Suppliers, users, government departments and the public. Engage through formal agreements, structured consultation and compliance evidence.
5
Why direction matters
The same message needs a different form in each direction; a status report that satisfies the sponsor will not motivate the team.
6
Where PMs under-invest
Sideward influence is the most commonly neglected direction, and it is where resource conflicts are actually resolved.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
140

## Slide 141
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Stakeholder Mapping, Step by Step
STEP 1
List from the register
Take every identified stakeholder as a candidate — do not pre-filter by who seems important.
STEP 2
Score each dimension
Rate power, interest, influence and attitude on a consistent scale, with the team, not alone.
STEP 3
Plot on the grid
Place each stakeholder on the chosen model so the pattern becomes visible rather than anecdotal.
STEP 4
Derive strategies
Write a specific engagement action per quadrant, naming who does what and how often.
STEP 5
Re-plot each phase
Positions shift as the project progresses; a stale map produces misdirected effort.
Keep the completed map confidential. A grid that labels a named executive as low-power, high-resistance is professionally damaging if it circulates — this is an ethics point as well as a practical one.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
141

## Slide 142
ECO PEOPLE T6 · MANAGE STAKEHOLDER EXPECTATIONS
Stakeholder Engagement Assessment Matrix (SEAM)
Stakeholder | Unaware | Resistant | Neutral | Supportive | Leading
Operations Director |  | C |  | D | 
Finance Manager |  |  | C | D | 
End-user representative |  |  |  | C / D | 
External regulator | C |  | D |  | 
IT Infrastructure lead |  |  | C |  | D
C marks current engagement, D marks desired. Every gap between C and D is an action item for the stakeholder engagement plan. Where C equals D, protect the position rather than invest further.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
142

## Slide 143
ECO PEOPLE T6 · MANAGE STAKEHOLDER EXPECTATIONS
Engagement Levels Across the Stakeholder Population
Chart: 
| Unaware | Resistant | Neutral | Supportive | Leading
Current engagement (count) | 6 | 8 | 14 | 9 | 3
Desired engagement (count) | 0 | 2 | 8 | 21 | 9
WHAT IT TELLS YOU
Six unaware stakeholders is an identification and communication failure, not an attitude problem — inform them first.
Eight resistant stakeholders need root-cause analysis: resistance usually signals an unaddressed expectation, not obstinacy.
The desired profile deliberately keeps two resistant: total consensus is unrealistic and often means dissent is hidden.
Moving fourteen neutrals to supportive is the highest-leverage engagement investment available on this project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
143

## Slide 144
ECO PEOPLE T6 · MANAGE STAKEHOLDER EXPECTATIONS
Monitor Stakeholder Engagement
1
What the process does
Monitors project stakeholder relationships and tailors strategies for engaging stakeholders through modification of plans and approaches.
2
Key input: the SEAM
The current-versus-desired matrix is re-scored regularly; movement in the wrong direction is an early warning signal.
3
Watch the issue log
A rising count of unresolved stakeholder issues predicts a drop in engagement long before anyone says so openly.
4
Watch participation
Declining attendance at reviews, slow sign-offs and delegated attendance are behavioural signals of falling engagement.
5
Monitor satisfaction explicitly
ECO People T6 requires monitoring internal and external customer satisfaction and expectations — and responding as needed.
6
Outputs
Work performance information, change requests, and updates to the plan, the register, the issue log and the risk register.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
144

## Slide 145
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
ECO 2026 People Task 5 — Align Stakeholder Expectations
Most project conflict is not disagreement. It is two people holding different definitions of done.
Categorize stakeholders
Group them so expectations can be surfaced and reconciled by group rather than one conversation at a time.
Identify expectations
Ask directly what each group believes success looks like — do not infer it from the requirements document.
Facilitate alignment
Bring conflicting parties into the same conversation and converge them on one agreed definition.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
145

## Slide 146
ECO PEOPLE T5 · ALIGN STAKEHOLDER EXPECTATIONS
Facilitating an Expectation-Alignment Session
STEP 1
Surface privately first
Interview each group separately so positions are honest before they become public and defended.
STEP 2
Categorise the gaps
Group differences by theme — scope, quality, timing, cost — so the session has structure.
STEP 3
Convene the parties
Bring conflicting stakeholders together with the sponsor present to supply decision authority.
STEP 4
Converge to one definition
Drive to a single written statement of objectives and acceptance criteria that all parties sign.
STEP 5
Document and republish
Update the charter, register and requirements so the agreement survives memory and staff turnover.
ECO People T5 also lists 'organize and act on mentoring opportunities'. Alignment sessions are where a PM can mentor stakeholders in how project trade-offs actually work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
146

## Slide 147
ECO PEOPLE T6 · MANAGE STAKEHOLDER EXPECTATIONS
ECO People Task 6 — Manage Stakeholder Expectations
1
Identify customer expectations
Distinguish internal customers (other departments receiving the output) from external customers (paying clients and end users) explicitly.
2
Align outcomes continuously
Maintain the fit between what is being built and what customers expect, rather than confirming alignment only at acceptance.
3
Monitor satisfaction
Use surveys, net promoter scores, review attendance and complaint rates as running indicators of customer satisfaction.
4
Respond as needed
The enabler explicitly requires response, not just measurement — a satisfaction survey nobody acts on is worse than none.
5
Manage expectation drift
Expectations inflate over a long project; periodic re-confirmation against the charter prevents a scope surprise at acceptance.
6
Under-promise deliberately
Committing to what you can reliably deliver protects trust far more than an optimistic commitment that slips.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
147

## Slide 148
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Building Trust and Influence Without Authority
1
Trust is the engagement multiplier
ECO People T4 explicitly requires building trust and influencing stakeholders to accomplish project objectives — it is an assessed skill.
2
Competence
Demonstrate that your estimates, forecasts and status reports have been accurate before; credibility is built from a track record.
3
Consistency
Behave the same way under pressure as you do in calm periods; inconsistency is what stakeholders read as risk.
4
Transparency
Report bad news early and unvarnished. A PM who hides a slip once is never fully believed again.
5
Reciprocity
Help peers with their problems before you need help with yours — this is the currency of sideward influence.
6
Follow-through
Close every commitment visibly. Small kept promises compound into the influence you need when the stakes are large.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
148

## Slide 149
EXAM FOCUS
Exam Traps: Stakeholders and Engagement
IF THE QUESTION SAYS
A previously unknown stakeholder appears mid-project with requirements
THE BEST ANSWER IS
Add them to the stakeholder register and analyse them first, before assessing the impact of their requirements.
IF THE QUESTION SAYS
A key stakeholder is resistant and you must decide what to do
THE BEST ANSWER IS
Meet them to understand the root cause of the resistance. Do not escalate, exclude, or simply add more reports.
IF THE QUESTION SAYS
You are asked which model uses power, legitimacy and urgency
THE BEST ANSWER IS
The salience model. Power/interest, power/influence and impact/influence are all two-dimensional grids.
IF THE QUESTION SAYS
Stakeholders disagree about what the project should deliver
THE BEST ANSWER IS
Facilitate a discussion to align expectations against the charter — alignment first, change request only if truly needed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
149

## Slide 150
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Communication Channels and Why Team Size Matters
Communication channels
N × (N − 1) / 2
N is the number of people. Channels grow quadratically, which is why small teams communicate so much more cheaply.
Team of 5
5 × 4 / 2 = 10
Ten channels — everyone can plausibly stay in sync through informal conversation alone.
Team of 10
10 × 9 / 2 = 45
Forty-five channels. Informal alignment starts failing; explicit communication planning becomes necessary.
Adding one person to 10
55 − 45 = 10 new channels
The eleventh person adds ten channels, not one — the arithmetic behind 'adding people to a late project makes it later'.
Exam tip: if a question adds or removes people, compute channels before and after and report the DIFFERENCE — that is usually what is being asked, not the absolute number.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
150

## Slide 151
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Agile Considerations for Starting Well
1
The whole-team approach
All skills needed to deliver sit inside one team, removing the hand-off delays and the finger-pointing that cross-functional silos create.
2
Small teams
Typically three to nine people, keeping communication channels low enough that alignment happens naturally rather than by process.
3
Co-location
Physical or deliberate virtual co-location maximises the osmotic communication that makes small teams fast.
4
Close customers
A customer representative available continuously replaces long requirement documents with short conversations and fast feedback.
5
Information radiators
Big visible charts — task boards, burndowns, impediment lists — in the team space so status is pulled, not reported.
6
Osmotic communication
Useful information overheard in a shared space; team members absorb context without anyone scheduling a meeting to transmit it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
151

## Slide 152
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Traditional Management vs Servant Leadership
TRADITIONAL COMMAND AND CONTROL
The manager holds the plan and issues the assignments
The manager assigns tasks to named individuals
Decisions escalate up and instructions come back down
Status is reported to the manager who consolidates it
The manager owns the estimates and commits on the team's behalf
Problems are solved by the manager and communicated as decisions
Performance is managed individually against assigned tasks
SERVANT LEADERSHIP
The leader removes impediments so the team can lead itself
The team pulls work from a prioritised backlog
Decisions are made at the level with the most information
Status is visible to everyone on a radiator, always current
The team estimates and commits to what it believes it can do
The leader's first question is 'what is blocking you?'
Performance is a team outcome, improved through retrospectives
Servant leadership: the practice of leading by understanding and addressing the needs and development of team members, in order to enable the highest possible team performance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
152

## Slide 153
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Self-Organising Teams
1
The definition
A cross-functional team in which people fluidly assume leadership as needed to achieve the team's objectives, rather than by fixed title.
2
Cross-functional by design
The team collectively holds every skill required to take an item from idea to done, so no external hand-off is needed.
3
Leadership is situational
Whoever has the most relevant expertise leads that decision, then hands leadership on — authority follows knowledge.
4
The leader still matters
Self-organising does not mean unled: the servant leader sets boundaries, protects focus and removes impediments from outside.
5
What it requires
Psychological safety, a clear goal, real decision authority and time — teams do not become self-organising by being told to be.
6
Why it is faster
Decisions are made where the information already is, eliminating the escalate-and-wait cycle that dominates traditional structures.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
153

## Slide 154
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Project Team Roles You Must Distinguish
Role | Accountable for | Not accountable for
Project manager | Integration, the plan, stakeholder engagement and delivery of objectives | Doing the technical work or approving their own charter
Project sponsor | Funding, the business case, charter approval and removing senior blockers | Day-to-day management of the project team
Team members | Producing the deliverables and estimating their own work | Setting priority between competing business needs
Product owner | Backlog priority, maximising value and representing the customer voice | Telling the team how to build it or managing their performance
Scrum master / facilitator | Process health, removing impediments, coaching and shielding the team | Assigning work, estimating for the team or setting priority
Functional manager | Supplying skilled resources and developing their people's capability | Directing project scope or accepting project deliverables
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
154

## Slide 155
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
T-Shaped People and Why Teams Want Them
1
What T-shaped means
Deep expertise in one discipline — the vertical stroke — plus working competence across several others, the horizontal stroke.
2
Individual value and versatility
T-shaped people contribute their specialism at full depth while still being able to pick up adjacent work when the queue demands it.
3
Flexibility for the organisation
Teams can rebalance around a bottleneck without waiting for a new hire or a formal resource request.
4
Avoids work stoppages
Reduces the key-person dependency that halts a whole team when one specialist takes leave or resigns.
5
Built deliberately
Train and coach team members to become T-shaped through pairing, rotation and shadowing — it does not happen by accident.
6
The contrast
I-shaped specialists create hand-off queues; generalists without depth create quality problems. T-shaped is the balance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
155

## Slide 156
ECO PEOPLE T2 · MANAGE CONFLICTS
Team Charter and Ground Rules — What Goes In
Section | What the team agrees | Example agreement
Shared values | The principles the team holds itself to | We surface bad news early and without blame
Behaviour guidelines | How members treat each other day to day | One conversation at a time; no interrupting
Communication and tools | Which channel is used for what and expected response times | Chat for the day, email for decisions, board for status
Decision-making | How the team decides and what needs consensus | Fist-of-five; a two-thirds majority carries technical decisions
Performance expectations | What good contribution looks like on this team | Definition of done applies to every item, no exceptions
Conflict resolution | The agreed path when disagreement escalates | Direct conversation, then the team, then the servant leader
Meetings | Time, frequency and channel of each ceremony | Stand-up 09:15 daily, 15 minutes, cameras on
Other agreements | Shared core hours, improvement time and team norms | Core hours 10:00-16:00; Friday afternoon for improvement work
Critical point: the team charter is created WITH the team, not issued to it. A charter written by the PM alone produces compliance, not commitment — and ground rules nobody helped write get broken.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
156

## Slide 157
ECO PEOPLE T2 · MANAGE CONFLICTS
Making Ground Rules Actually Work
1
Make it visible
An electronic document or a poster on the team wall — ground rules filed in a shared drive stop influencing behaviour within a week.
2
Co-create it
Rules the team wrote itself are enforced by the team; rules imposed on the team are enforced only by the manager, and only when watching.
3
Keep it short
Six to ten rules the team can recall beats a thirty-item document nobody has finished reading.
4
Address violations early
ECO People T2 requires managing and rectifying ground-rule violations — an unaddressed breach becomes the new de facto rule.
5
Model it from the top
The project manager who breaks a ground rule cancels it for everyone, regardless of what the poster says.
6
Revisit at retrospectives
Rules that no longer serve the team are removed and new ones added as the team's context changes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
157

## Slide 158
ECO PEOPLE T1 · DEVELOP A COMMON VISION
The Kick-Off Meeting: Two Distinct Audiences
ORGANISATIONAL / PUBLIC KICK-OFF
Announcing the project to the wider organisation
Formally announce project initiation to the organisation
Share a common understanding of the high-level vision and purpose
State the business value the project will deliver
Identify the sponsor, key stakeholders and the project manager
Present high-level items drawn from the project charter
Signal executive commitment so the project is taken seriously
INTERNAL / TEAM KICK-OFF
Turning a group of assigned people into a project team
Give an overview of the project charter and its objectives
Clarify each team member's role and responsibilities
Present the results of planning efforts completed so far
Initiate the product backlog or the initial work breakdown
Agree the team charter and ground rules together
Establish the ceremony cadence and communication norms
Purpose of any kick-off: establish project context, assist in team formation, and align team and stakeholders with the project vision.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
158

## Slide 159
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
When Kick-Off Happens in Each Approach
1
Predictive
One kick-off after planning is largely complete, because the plan is what is being communicated.
2
Iterative
Kick-off at the start, then a re-alignment at each major iteration boundary as the solution takes shape.
3
Incremental
Kick-off at the start plus a short launch for each increment, focused on the value being shipped.
4
Agile / adaptive
A short project kick-off, then effectively a mini kick-off every sprint at sprint planning.
5
Hybrid
A formal organisational kick-off for governance, plus agile ceremonies for the delivery team.
Exam cue: in predictive projects the kick-off usually occurs at the END of planning; in adaptive projects it occurs at the start of execution and repeats each iteration.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
159

## Slide 160
EXAM FOCUS
Exam Traps: Charter, Team and Kick-Off
IF THE QUESTION SAYS
You are newly assigned as PM and asked what to do first
THE BEST ANSWER IS
Read the project charter and the business documents to understand objectives, then identify stakeholders.
IF THE QUESTION SAYS
A team member asks who assigns work on an agile team
THE BEST ANSWER IS
Nobody assigns it. The team self-organises and pulls work from the prioritised backlog.
IF THE QUESTION SAYS
The team is repeatedly missing agreed stand-up times
THE BEST ANSWER IS
Address the ground-rule violation with the team and revisit the team charter together — do not escalate first.
IF THE QUESTION SAYS
A predictive project asks when the kick-off should be held
THE BEST ANSWER IS
At the end of planning, once there is an integrated plan worth communicating to stakeholders.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
160

## Slide 161
RECAP
Topic 2 Recap — Start the Project
1
Integration is the PM's job
Unifying scope, schedule, cost, quality, risk and stakeholders so they deliver one coherent business value.
2
The charter authorises
Signed by the sponsor, it empowers the PM, states measurable objectives and anchors all later change control.
3
Business documents justify
Business case, cost-benefit analysis and benefits management plan exist before the project and outlive it.
4
Know the six value drivers
Financial gain, new customers, social benefit, first to market, improvement and regularization.
5
Financial metrics rank options
Bigger is better for NPV, IRR, ROI and BCR; smaller is better for payback period and opportunity cost.
6
Identify stakeholders early
Use the OBS, document analysis and brainstorming, and record everything in the stakeholder register.
7
Analyse before you engage
Power/interest, power/influence, impact/influence, the cube and the salience model each answer a different question.
8
Align, then manage expectations
ECO People T5 and T6: surface expectations, converge them, then monitor customer satisfaction and respond.
9
Start the team deliberately
Co-create the team charter and ground rules; build T-shaped, self-organising capability through servant leadership.
10
Kick off with purpose
Establish context, form the team and align everyone with the project vision before execution begins.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
161

## Slide 162
WHAT YOU WILL BUILD
Hands-on Labs — Topic 2
1
Lab 05. Business Case and Cost-Benefit Analysis
Process T3 · LO1 · 25 min in class + 25 min self-study
Produces: Business case, NPV/ROI/payback model
2
Lab 06. Project Charter
Process T1 · LO1 · 20 min in class + 25 min self-study
Produces: Approved project charter
3
Lab 07. Stakeholder Register, Power/Interest Grid and Salience Model
People T4, T5 · LO4 · 25 min in class + 25 min self-study
Produces: Stakeholder register, Power/interest grid, Salience classification
4
Lab 08. Team Charter, Ground Rules and Shared Vision
People T1, T2 · LO3 · 30 min in class + 15 min self-study
Produces: Team charter, Ground rules, Vision statement
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
162

## Slide 163
HANDS-ON ACTIVITY
Lab 05. Business Case and Cost-Benefit Analysis
Case study: Contoso Training Portal Upgrade. Process T3 · LO1. Produces Business case, NPV/ROI/payback model.
25 min in class
1
State the business problem in one sentence and the opportunity in one more.
2
List three options including 'do nothing', with the cost and benefit of each.
3
Build the cash-flow table: initial investment, annual benefit, and running net position across five years.
4
Calculate payback period, NPV at a 6% discount rate, ROI and the benefit-cost ratio using the Statistics tool.
5
Identify the non-financial benefits and state how each will be measured.
6
Write the recommendation, naming the benefits owner accountable after the project closes.
DELIVERABLE
Business case, NPV/ROI/payback model
TOOL
Statistics
alfredang.github.io/novastats/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
163

## Slide 164
HANDS-ON ACTIVITY
Lab 06. Project Charter
Case study: Contoso Training Portal Upgrade. Process T1 · LO1. Produces Approved project charter.
20 min in class
1
Draft the charter's purpose statement and its measurable success criteria — numbers, not adjectives.
2
Record high-level requirements and explicitly list what is OUT of scope.
3
Name the sponsor, project manager and key stakeholders, and state the authority delegated to the project manager.
4
Add the summary milestone schedule and the high-level budget with its confidence range.
5
Record assumptions, constraints and the top five high-level risks.
6
Define the approval criteria and who signs the charter into effect.
DELIVERABLE
Approved project charter
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
164

## Slide 165
HANDS-ON ACTIVITY
Lab 07. Stakeholder Register, Power/Interest Grid and Salience Model
Case study: Contoso Training Portal Upgrade. People T4, T5 · LO4. Produces Stakeholder register, Power/interest grid, Salience classification.
25 min in class
1
List every stakeholder affected by the portal upgrade, including those who merely believe they are affected.
2
For each, record interest, influence, expectations and their current attitude toward the project.
3
Plot all stakeholders on a power/interest grid and assign the four strategies: manage closely, keep satisfied, keep informed, monitor.
4
Re-classify the top eight using the salience model — power, legitimacy and urgency — and note where it disagrees with the grid.
5
Complete a SEAM recording Current (C) and Desired (D) engagement for each key stakeholder.
6
Write the engagement action that moves each stakeholder from C to D, with an owner and a date.
DELIVERABLE
Stakeholder register, Power/interest grid, Salience classification
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
165

## Slide 166
HANDS-ON ACTIVITY
Lab 08. Team Charter, Ground Rules and Shared Vision
Case study: Contoso Training Portal Upgrade. People T1, T2 · LO3. Produces Team charter, Ground rules, Vision statement.
30 min in class
1
Draft the team's shared vision in a single sentence every member can repeat without reading it.
2
Define roles and responsibilities so no member is unclear what they own.
3
Agree working hours, core overlap for the distributed members, and expected response times.
4
Set the ground rules: meeting norms, decision rules, and how disagreement is raised and settled.
5
Define the Definition of Ready and Definition of Done the team will hold each other to.
6
Agree the conflict protocol and the escalation path before any conflict actually occurs.
DELIVERABLE
Team charter, Ground rules, Vision statement
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
166

## Slide 167
03
TOPIC
Plan the Project
Building the integrated plan — scope, schedule, cost, quality, resources, communications, risk and procurement.
1
The integrated project management plan
2
Scope: requirements, WBS and baselines
3
Schedule: activities, dependencies, critical path
4
Cost: estimating, budget and reserves
5
Quality: planning and problem-solving tools
6
Resources, communications and procurement
7
Risk: identification, analysis and response
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
167

## Slide 168
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Why planning is the heart of the Process domain
A plan is a decision record, not a document
Reduces rework
Decisions made deliberately up front cost a fraction of the same decisions made reactively during delivery.
Creates alignment
A shared plan lets thirty people make consistent choices without asking the project manager each time.
Enables control
You cannot detect variance without a baseline to measure the actual result against.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
168

## Slide 169
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Develop Project Management Plan — ITTO
Integration is the only knowledge area whose job is to reconcile the other twelve — the PM owns the seams between the plans.
INPUTS
Project charter — the authorised high-level boundaries
Outputs from other planning processes (all subsidiary plans)
Enterprise environmental factors (EEFs)
Organisational process assets (OPAs), templates, standards
TOOLS & TECHNIQUES
Expert judgment from PMO, SMEs and delivery leads
Data gathering: brainstorming, checklists, focus groups
Interpersonal and team skills: conflict management, facilitation
Meetings — notably the project kick-off meeting
OUTPUTS
Project management plan — the integrated, approved artefact
Contains all subsidiary plans plus the three baselines
Contains the development approach and life cycle description
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
169

## Slide 170
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
What the project management plan actually enables
1
Execute
Tells the team what work to do, in what order, with which resources and to which acceptance criteria.
2
Monitor
Defines the metrics, the reporting cadence and the thresholds that trigger a management conversation.
3
Control
Establishes the baselines against which variance is measured and the change control process that protects them.
4
Close
Defines the exit criteria, handover conditions and the evidence needed for formal acceptance of deliverables.
5
Guardrails
Sets the boundaries inside which the team may act autonomously without escalating every decision upward.
6
Tailoring
Records what was deliberately omitted or simplified for this project's size, risk and regulatory profile.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
170

## Slide 171
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
The subsidiary plans inside the integrated plan
1
Scope management plan
How scope is defined, validated and controlled, and how the WBS will be produced and maintained.
2
Schedule management plan
The scheduling method, tool, units of measure, accuracy thresholds and control rules.
3
Cost management plan
Estimating accuracy, units, control thresholds, earned value rules and reporting formats.
4
Quality management plan
Standards to be met, quality roles, review activities and the improvement approach.
5
Resource management plan
How people and physical resources are identified, acquired, developed and released.
6
Communications plan
Who needs what information, in what format, how often, and through which channel.
7
Risk management plan
Methodology, roles, budgeting, timing, categories, probability and impact definitions.
8
Procurement plan
What is bought versus built, contract types, and how sellers are selected and managed.
9
Stakeholder engagement plan
The strategies used to move each stakeholder from current to desired engagement level.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
171

## Slide 172
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Plan-driven versus collaborative planning
PLAN-DRIVEN (PREDICTIVE)
The plan is authored, then approved, then followed
The project manager drafts the plan and seeks formal sign-off
Detail is pushed as far forward as the information allows
Change after baseline requires a formal change request
Strong on auditability, regulatory evidence and contract control
Risk: the plan ages badly when the environment moves fast
COLLABORATIVE (ADAPTIVE)
The plan is co-created continuously by those doing the work
The product owner sets objectives from customer needs and value
The team estimates and sequences its own work each iteration
Team members are the local domain experts on how work gets done
The PM or scrum master facilitates rather than dictates
Risk: without discipline, planning degrades into improvisation
Most real projects are hybrid: governance-level milestones are plan-driven while the work inside each milestone is planned collaboratively by the delivery team.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
172

## Slide 173
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Rolling wave planning — progressive elaboration in practice
STEP 1
Plan the horizon
Decompose only the near-term work to work-package detail; leave later work as planning packages.
STEP 2
Execute the wave
Deliver the detailed work while the longer-term scope stays deliberately coarse.
STEP 3
Learn
Capture actuals, estimating error and emerging risks from the wave just completed.
STEP 4
Elaborate next
Decompose the next horizon using what you just learned, not what you guessed at the start.
STEP 5
Re-baseline
Fold the newly detailed work into the baseline through the agreed change control route.
Rolling wave applies to BOTH predictive and adaptive approaches — it is applied to work packages, planning packages and release planning, and is the standard answer when a question says 'not enough information is available to plan the later phases'.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
173

## Slide 174
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Plan Stakeholder Engagement — ITTO
Engagement is planned, not improvised: you decide deliberately who must be moved from resistant to supportive, and how.
INPUTS
Project charter and project management plan
Project documents: stakeholder register, issue log, change log
Agreements with contracting parties
EEFs — organisational culture, political climate, regulation
TOOLS & TECHNIQUES
Expert judgment on politics and organisational power
Data gathering: benchmarking against comparable projects
Data analysis: assumption/constraint and root cause analysis
Decision making: prioritisation and ranking of stakeholders
Data representation: mind mapping, engagement assessment matrix
OUTPUTS
Stakeholder engagement plan — the strategies and actions needed
Defines required involvement level per stakeholder group
Feeds directly into the communications management plan
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
174

## Slide 175
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Stakeholder Engagement Assessment Matrix (SEAM)
Level | What it looks like | Typical intervention
Unaware | Does not know the project exists or that it will affect them | Awareness communication; briefing pack; named contact point
Resistant | Aware of the project and actively opposed to the change | Surface the objection, negotiate, find the win, escalate if needed
Neutral | Aware but neither supportive nor opposed; will not help | Show the personal and unit-level benefit; invite to a demo
Supportive | Aware and in favour, will speak well of the project | Keep informed, use as a reference and as an internal advocate
Leading | Actively engaged in ensuring the project succeeds | Give real influence: steering seat, sponsorship of a workstream
Mark C for the CURRENT level and D for the DESIRED level in each row. Where C and D differ you have an engagement gap that needs a named action and an owner — not a hope.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
175

## Slide 176
EXAM FOCUS
Exam focus — planning and stakeholder engagement
IF THE QUESTION SAYS
A stakeholder is surprised by a project decision that affected them
THE BEST ANSWER IS
Review and update the stakeholder engagement plan and the communications plan — the omission is a planning defect
IF THE QUESTION SAYS
Later phases cannot be planned in detail yet
THE BEST ANSWER IS
Apply rolling wave planning; use planning packages now and elaborate them when information becomes available
IF THE QUESTION SAYS
The team asks who decides how the work will be done
THE BEST ANSWER IS
The team members do — they are the local domain experts; the PM facilitates and removes impediments
IF THE QUESTION SAYS
Sponsor asks 'what is the project management plan for?'
THE BEST ANSWER IS
It is the approved basis for executing, monitoring, controlling and closing the work — not a status report
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
176

## Slide 177
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Knowledge area 1 of 8 in the planning block
Scope: agree what is in, and prove what is out
Product scope
The features and functions that characterise the product, service or result being delivered.
Project scope
The work that must be performed to deliver that product with the specified features and functions.
Why it matters
Every schedule, cost, quality and risk number in the plan is derived from the agreed scope.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
177

## Slide 178
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Plan Scope Management — ITTO
These two plans are process documents: they describe how you will do scope work, not what the scope actually is.
INPUTS
Project charter — high-level requirements and boundaries
Project management plan: quality and life cycle descriptions
EEFs — organisational culture, infrastructure, marketplace
OPAs — policies, historical scope statements, lessons learned
TOOLS & TECHNIQUES
Expert judgment from prior similar projects
Data analysis — alternatives analysis on how to collect requirements
Meetings with sponsor, selected stakeholders and the team
OUTPUTS
Scope management plan — how scope will be defined and controlled
Requirements management plan — how requirements are gathered, analysed, documented and traced
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
178

## Slide 179
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
What the scope management plan must specify
1
Scope statement preparation
The process used to prepare a detailed project scope statement from the charter and requirements.
2
WBS creation
How the WBS will be created from the detailed scope statement, and the decomposition rules to apply.
3
Baseline approval
How the scope baseline will be reviewed, approved and subsequently maintained.
4
Deliverable acceptance
How formal acceptance of completed deliverables will be obtained and evidenced.
5
Change control
How change requests to the scope statement are raised, assessed, and routed for a decision.
6
Tailoring decisions
Which scope activities are simplified or omitted given this project's size and risk.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
179

## Slide 180
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Scope planning analysis techniques
Technique | What it does | When you reach for it
Document analysis | Derives requirements from existing documents such as contracts, SOPs, regulations and prior project files | A predecessor system or process already exists on paper
Alternatives analysis | Evaluates possible options or approaches for executing and performing the project work | More than one credible way to deliver the same outcome
Product analysis | Asks questions about a product and forms answers describing its use, characteristics and value | The deliverable is a product rather than a service
Product breakdown | Splits a product and its requirements into components to gain a clear understanding of the work | Complex physical or software product with many subsystems
Systems engineering | Approaches design, integration, management and the life cycle of complex systems in a multidisciplinary way | Highly interdependent, safety- or mission-critical systems
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
180

## Slide 181
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Scope in predictive versus agile delivery
PREDICTIVE SCOPE
Fixed early, defended by change control
Scope is planned in full at the start of the project
Captured in a detailed project scope statement and WBS
Baselined once approved by the sponsor or change board
Any change during delivery requires a formal change request
Time and cost flex; scope is held constant wherever possible
AGILE SCOPE
Fixed in the sprint, variable across the release
Product owner determines and prioritises the product backlog
Scope may legitimately change between every sprint
Detail is added just in time, at backlog refinement
Time (the sprint) and cost (the team) are fixed instead
Value delivered per iteration is the control mechanism
Exam cue: 'requirements are expected to evolve' points to adaptive; 'requirements are stable and the contract is fixed price' points to predictive.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
181

## Slide 182
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Agile scope artefacts
1
Product roadmap
Envisions and plans the big picture — product strategy, direction and the value to be delivered over time.
2
Themes and goals
Groups related features under overarching goals so structure and association are visible to stakeholders.
3
Milestones
Dates when major items will occur or be delivered — the fixed points a fluid backlog must still respect.
4
Story map
Organises user stories into functional groups within a narrative flow, so the whole product is visible at once.
5
Product backlog
The single ordered list of everything that might be built, owned and prioritised by the product owner.
6
Increment
The working, potentially releasable slice of product produced by each iteration and inspected at review.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
182

## Slide 183
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Collect Requirements — ITTO
Requirements are the bridge between stakeholder need and deliverable — every later baseline traces back to them.
INPUTS
Project charter and business documents (business case)
Project management plan: scope, requirements and stakeholder plans
Project documents: assumption log, lessons learned, stakeholder register
Agreements and enterprise environmental factors
TOOLS & TECHNIQUES
Data gathering: brainstorming, interviews, focus groups, questionnaires and surveys, benchmarking
Data analysis: document analysis
Decision making: voting, multi-criteria decision analysis
Data representation: affinity diagram, mind mapping
Interpersonal and team skills: nominal group technique, observation/conversation, facilitation
Context diagram and prototypes
OUTPUTS
Requirements documentation — grouped, unambiguous, testable
Requirements traceability matrix (RTM)
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
183

## Slide 184
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
The requirements management plan
1
What it is
The defined process for how requirements will be gathered, analysed, documented, managed and controlled.
2
Also called
The business analysis plan — in organisations with a formal BA function it is owned jointly with the BA.
3
Configuration
States how requirement changes are initiated, analysed, traced, tracked and approved.
4
Prioritisation
Records the prioritisation method that will be used, such as MoSCoW or a weighted scoring model.
5
Traceability
Defines the traceability structure — which attributes are recorded against each requirement.
6
Metrics
Defines the product metrics that will be used and the rationale for choosing them.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
184

## Slide 185
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Requirements Traceability Matrix — what each column proves
Column | Contents | Question it answers
Requirement ID | Unique persistent identifier for the requirement | Can I refer to this unambiguously in every other artefact?
Business need | The business case objective or benefit it supports | Why are we building this at all?
Project objective | The charter objective the requirement serves | Is this in scope or is it somebody's pet feature?
WBS deliverable | The work package that produces it | Who is building it and where is it in the schedule?
Product design | The design element or component that realises it | Has anyone actually designed a solution for this?
Test case | The verification or acceptance test | How will we prove it works before handover?
Status | Active, cancelled, deferred, added, approved, assigned | Is this still live and who signed it off?
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
185

## Slide 186
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Requirement gathering techniques compared
Technique | How it works | Best for
Brainstorming | Relaxed informal group idea generation using lateral thinking; quantity first, judgement deferred | Wide divergent option generation early in discovery
Interviews | Structured or unstructured one-to-one questioning of stakeholders and SMEs | Sensitive, political or expert-held detail
Focus groups | Moderated discussion with pre-qualified stakeholders and subject matter experts | Attitudes, expectations and reactions
Questionnaires/surveys | Written question sets to large or geographically dispersed audiences | Statistically meaningful breadth
Benchmarking | Compares practices against other organisations to identify best practice | Setting a performance bar to meet or exceed
Nominal group technique | Brainstorm, then rank ideas by individual vote to produce a prioritised list | Converging a large idea pool
Observation (job shadowing) | Watch people do the work in situ | Tacit process detail people cannot articulate
Facilitation | Focused workshops (JAD, QFD) that cross functions | Reconciling conflicting cross-department requirements
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
186

## Slide 187
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Requirement prioritisation techniques
Technique | Mechanics | Benefit
MoSCoW (Dai Clegg) | Sort into Must have, Should have, Could have, Won't have this time | Reaches shared understanding of importance fast
Kano model | Classify features as Basic, Performance, Delighter, Indifferent or Reverse | Separates satisfiers from mere expectations
100-point method | Each stakeholder distributes 100 points across the candidate requirements | Forces trade-offs; exposes true preference
Weighted/multi-criteria | Score each requirement against weighted criteria and rank the totals | Defensible, auditable decision trail
Paired comparison | Compare requirements two at a time and tally the wins | Works when stakeholders cannot rank a long list
Value/effort matrix | Plot benefit against cost of delivery on a 2x2 | Surfaces the quick wins and the money pits
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
187

## Slide 188
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
MoSCoW as a decision grid
MUST HAVE
Non-negotiable for this release; without it the delivery has no legal, safety or business viability.
SHOULD HAVE
Important and painful to omit, but a workaround exists for the duration of this release.
COULD HAVE
Desirable and included only if time and cost allow; the first thing dropped when the sprint is tight.
WON'T HAVE (THIS TIME)
Explicitly agreed as out of scope now — recorded, not forgotten, and revisited next release.
URGENCY OF NEED
IMPACT IF ABSENT
The discipline is in the W: writing down what you are NOT doing is what stops scope creep later. Cap Must-haves at roughly 60% of capacity so there is room to absorb reality.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
188

## Slide 189
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Backlog and backlog refinement
1
Product backlog
A single ordered list of everything that might be built; the product owner owns its content and order.
2
User stories
Work items describing desired functionality from the user's point of view, with acceptance criteria attached.
3
Refinement (grooming)
Continual work by the product owner before iteration planning to add detail, estimates and order.
4
Joint refinement
Team and product owner refine together during the sprint so the next sprint starts with ready items.
5
Reprioritisation
Allows reorganisation so higher-value items are completed first as the market and feedback change.
6
Emergent detail
Only the top of the backlog needs full detail — the bottom stays coarse until it approaches delivery.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
189

## Slide 190
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Relative sizing techniques
Technique | Scale | How to use it
T-shirt sizing | XS, S, M, L, XL | Fast, coarse sizing of a large backlog or a roadmap before any detail exists
Story points | Fibonacci: 1, 2, 3, 5, 8, 13, 21 | Relative measure of difficulty, effort, volume and uncertainty combined
Planning poker | Simultaneous reveal of point cards | Removes anchoring bias; the discussion of outliers is the real value
Ideal days | Uninterrupted working days | Intuitive for new teams but invites confusion with calendar duration
Affinity estimation | Silent sorting of cards by size | Sizing 100+ backlog items in under an hour
Points are relative and team-specific: 8 points on one team is not 8 points on another. Never use velocity to compare teams.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
190

## Slide 191
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Define Scope — ITTO
Define Scope converts a long list of requirements into a single agreed statement of what will and will not be delivered.
INPUTS
Project charter with the high-level boundaries
Project management plan — the scope management plan
Project documents: assumption log, requirements documentation, risk register
EEFs and OPAs including prior scope statements
TOOLS & TECHNIQUES
Expert judgment on comparable deliverables
Data analysis — alternatives analysis
Decision making — multi-criteria decision analysis
Interpersonal and team skills — facilitation workshops
Product analysis: product breakdown, systems analysis, value engineering, value analysis
OUTPUTS
Project scope statement — the detailed description
Project document updates: assumption log, requirements documentation, RTM, stakeholder register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
191

## Slide 192
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Anatomy of the project scope statement
1
Product scope description
Progressively elaborated description of the characteristics of the product, service or result.
2
Deliverables
Every unique verifiable product or capability required, including project management reports and documents.
3
Acceptance criteria
The conditions that must be met before the deliverables will be formally accepted by the customer.
4
Exclusions
Explicitly identifies what is out of scope, so stakeholder expectations are managed before delivery starts.
5
Constraints
Limiting factors — fixed budget, imposed dates, mandated technology, contractual provisions.
6
Assumptions
Factors treated as true without proof; each one is a risk with a friendlier name and belongs in the risk register.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
192

## Slide 193
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Baselines — the approved versions you measure against
1
Scope baseline
Approved project scope statement + WBS + WBS dictionary; changed only via approved change request.
2
Schedule baseline
The approved version of the schedule model, with baseline start and finish dates for each activity.
3
Cost baseline
The approved time-phased budget excluding management reserve; the S-curve you track EV against.
4
Performance measurement baseline
Scope + schedule + cost combined; the single reference for earned value analysis.
5
Why baseline at all
Variance is meaningless without a fixed reference; an un-baselined project cannot be controlled.
6
Changing a baseline
Only through integrated change control — never by quietly editing the file to match the actual.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
193

## Slide 194
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Changing a baselined item — the change request route
STEP 1
Raise
Any stakeholder may raise a change request; it is logged the moment it is raised, not after it is approved.
STEP 2
Analyse impact
Assess the effect on scope, schedule, cost, quality, resources and risk — never on one dimension alone.
STEP 3
Record
Enter it in the change log with the impact analysis and the recommended disposition.
STEP 4
Decide
The change control board approves, defers or rejects; the decision and its rationale are recorded.
STEP 5
Implement/update
If approved, update the baselines and all affected documents, then communicate the change.
A rejected change request is still a valuable artefact: it records that the request was considered, so it does not resurface as an informal expectation later in the project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
194

## Slide 195
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Scope creep versus gold plating
SCOPE CREEP
Uncontrolled expansion without approval
Scope or features added that were not planned or approved
Usually requested by stakeholders, accepted informally by the team
Impacts cost and schedule that nobody has funded
Root cause is a weak or bypassed change control process
Cure: an explicit scope statement plus disciplined change control
GOLD PLATING
Extra work nobody asked for
The team delivers features the customer did not need or request
Motivated by pride, boredom or a wish to delight the customer
Consumes budget and introduces untested, unrequested risk
Never adds value the customer will pay for or thank you for
Cure: definition of done, and acceptance criteria as the ceiling
Both destroy the baseline, but the direction differs: creep comes from outside the team, gold plating comes from inside.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
195

## Slide 196
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Definition of Ready versus Definition of Done
DEFINITION OF READY (DoR)
What must be true before work may START
Story is written from the user's perspective with clear value
Acceptance criteria are written and agreed with the product owner
Dependencies identified and either resolved or scheduled
The story is small enough to complete inside one iteration
The team has estimated it and understands what 'done' means
DEFINITION OF DONE (DoD)
What must be true before work is COMPLETE
Code written, peer reviewed and merged to the mainline
Unit, integration and acceptance tests written and passing
Documentation updated; no known defects above agreed severity
Deployed to the agreed environment and demonstrated
Accepted by the product owner against the acceptance criteria
DoD is the team's quality contract with itself and is the single most effective agile defence against gold plating and against carrying unfinished work between sprints.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
196

## Slide 197
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Create WBS — ITTO
The WBS is deliverable-oriented, not activity-oriented: its elements are nouns (things produced), not verbs.
INPUTS
Project management plan — the scope management plan
Project documents: project scope statement, requirements documentation
EEFs — industry-specific WBS standards
OPAs — WBS templates from prior similar projects
TOOLS & TECHNIQUES
Expert judgment on how far to decompose
Decomposition — dividing and subdividing scope into smaller, more manageable parts
OUTPUTS
Scope baseline — scope statement + WBS + WBS dictionary
Project document updates: assumption log and requirements documentation
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
197

## Slide 198
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Decomposition — from deliverable to work package
STEP 1
Identify deliverables
Take the deliverables and related work from the approved project scope statement.
STEP 2
Structure the WBS
Organise by phase, by major deliverable, or by subproject — pick one logic and stay consistent.
STEP 3
Decompose downward
Break upper components into lower-level, more detailed components with the team, not alone.
STEP 4
Assign codes
Give every element a unique code of accounts identifier so cost and schedule can roll up cleanly.
STEP 5
Verify sufficiency
Confirm the degree of decomposition is enough to estimate, assign and control — then stop.
Over-decomposition is a real defect: it produces inefficient use of resources, decreased efficiency in performing the work, and a schedule so granular nobody maintains it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
198

## Slide 199
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Work packages, planning packages and the 100% rule
1
Work package
The lowest level of the WBS — small enough to estimate cost and duration reliably and assign to one owner.
2
Control account
A management control point where scope, budget and schedule are integrated and compared to earned value.
3
Planning package
A control account component with known work but no detailed activities yet — rolling wave's placeholder.
4
The 100% rule
The WBS includes 100% of the work defined by the scope, and captures all deliverables — internal and external.
5
Nothing extra
Work not in the WBS is outside the project scope; this is what makes the WBS a scope-creep detector.
6
8/80 heuristic
A common rule of thumb: a work package should be between 8 and 80 hours of effort. It is guidance, not doctrine.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
199

## Slide 200
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
WBS dictionary — the detail behind each work package
Field | Why it is there
WBS code identifier | Links the package to the code of accounts so cost and schedule data roll up to the right control account
Description of work | Removes ambiguity about what the package includes and, critically, what it excludes
Assumptions and constraints | Records the conditions the estimate depends on so the estimate can be challenged fairly
Responsible organisation | Names the accountable unit or person for the package — no orphan work
Schedule milestones/activities | Connects the package to the schedule model and its associated activities
Resources required | States the people, equipment and materials the package consumes
Cost estimates | The package-level cost that bottom-up rolls into the project budget
Quality requirements and acceptance criteria | Defines what 'complete and correct' means for this package
Technical references / agreement information | Points to the standards, drawings or contract clauses that govern the work
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
200

## Slide 201
EXAM FOCUS
Exam focus — scope
IF THE QUESTION SAYS
A stakeholder asks for a small extra feature mid-sprint
THE BEST ANSWER IS
Predictive: raise a change request. Agile: add it to the product backlog for the product owner to prioritise — never mid-sprint
IF THE QUESTION SAYS
The team added a feature the customer never asked for
THE BEST ANSWER IS
That is gold plating; it is not a benefit, it is an unapproved scope change consuming budget
IF THE QUESTION SAYS
You need to know if a requirement was delivered and tested
THE BEST ANSWER IS
Consult the requirements traceability matrix — it links need to deliverable to test to acceptance
IF THE QUESTION SAYS
A question mentions 'approved scope statement + WBS + dictionary'
THE BEST ANSWER IS
That combination is the definition of the scope baseline
IF THE QUESTION SAYS
Work is not shown anywhere in the WBS
THE BEST ANSWER IS
It is out of scope. The 100% rule means the WBS contains all of the work and only the work of the project
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
201

## Slide 202
RECAP
Recap — scope planning
1
Two plans first
Plan Scope Management yields the scope management plan and the requirements management plan — process, not content.
2
Collect then define
Requirements documentation and the RTM come before the project scope statement can be written.
3
The RTM is the spine
It traces need to objective to deliverable to test to acceptance and status.
4
Prioritise explicitly
MoSCoW, Kano and the 100-point method turn 'everything is critical' into a defensible order.
5
The WBS is deliverables
Decompose to work packages; the WBS dictionary carries the detail; obey the 100% rule.
6
Baseline and defend
Scope baseline changes only by approved change request; watch for creep from outside and gold plating from inside.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
202

## Slide 203
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Knowledge area 2 of 8 in the planning block
Schedule: sequence the work, then face the maths
Derived, not chosen
A credible schedule is calculated from scope, dependencies and resources — it is not a date you were told.
The constraint
The critical path defines the shortest possible duration; everything else has float to spend.
Adaptive equivalent
Agile replaces the Gantt with cadence, velocity and a prioritised backlog — but still forecasts.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
203

## Slide 204
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Plan Schedule Management — ITTO
This plan may be formal or informal, broadly framed or highly detailed — tailored to the needs of the project.
INPUTS
Project charter — summary milestone schedule and approval requirements
Project management plan: scope baseline, development approach
EEFs — organisational culture, scheduling software availability
OPAs — historical schedules, templates, scheduling policies
TOOLS & TECHNIQUES
Expert judgment on scheduling methodology and tooling
Data analysis — alternatives analysis on scheduling approaches, level of detail, durations and rolling wave horizons
Meetings with the team, sponsor and the PMO
OUTPUTS
Schedule management plan — establishes criteria and activities for developing, monitoring and controlling the schedule
Defines the units of measure, accuracy, control thresholds and the rules of performance measurement
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
204

## Slide 205
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
What the schedule management plan specifies
1
Scheduling method
Critical path method, critical chain, or an iteration-based cadence — chosen deliberately, stated explicitly.
2
Scheduling tool
The software of record; if two tools exist you will eventually have two conflicting truths.
3
Level of accuracy
The acceptable range for activity duration estimates, including a contingency amount.
4
Units of measure
Hours, days or weeks for time; staff hours for effort — mixing them silently is a classic estimating error.
5
Control thresholds
The variance that may be tolerated before an action is required — for example ±10% of planned duration.
6
Reporting formats
The formats and frequency of schedule reports, and the maintenance process for the schedule model.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
205

## Slide 206
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Predictive versus adaptive scheduling
PREDICTIVE (WATERFALL) SCHEDULING
Activities decomposed from work packages, then sequenced
Activities broken down from work packages and put in order
Dependencies, durations and resources drive the calculated dates
The critical path determines the shortest possible duration
Once approved and baselined, changes need a change request
Presented as a Gantt chart, milestone chart or network diagram
ADAPTIVE (AGILE) SCHEDULING
Fixed cadence, variable content, forecast by velocity
Product owner owns the product backlog and the product roadmap
The roadmap shows the order features are expected to be delivered
Iteration length is fixed; the content of each iteration varies
Forecasts come from measured velocity, not from imposed dates
Presented as a roadmap, Kanban board, burndown or burnup chart
Both start from benchmarking and historical data: comparing against a similar product or service schedule gives a defensible starting point before detailed analysis.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
206

## Slide 207
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Schedule presentation formats — choose to fit the audience
1
Roadmap
High-level, time-boxed view of themes and releases for executives who want direction rather than detail.
2
Gantt chart
Bar chart of activities against a calendar; shows duration, overlap and progress at a glance.
3
Milestone chart
Only zero-duration events on a timeline — the right artefact for a steering committee.
4
Network diagram
Nodes and arrows showing logical dependencies; the only format that reveals the critical path.
5
Kanban board
Columns per workflow stage with WIP limits — for continuous flow rather than time-boxed work.
6
Burndown/burnup
Work remaining or work completed over time, compared with the ideal line for the iteration or release.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
207

## Slide 208
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Kanban board mechanics
1
Visualise
Organise work into tasks on cards so the whole flow is visible to everyone, including stakeholders.
2
Columns as stages
Each column is a workflow stage; tailor the stages to your actual process, not a textbook one.
3
Card information
Display owner, size, blocked status and age at every stage so the board answers questions without a meeting.
4
WIP limits
Cap the number of items allowed in a column; the cap is what converts a to-do list into a flow system.
5
Pull, not push
Work is pulled when capacity frees up, rather than pushed onto a team already saturated.
6
Expose bottlenecks
The column that keeps hitting its WIP limit is the constraint — improve there, nowhere else.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
208

## Slide 209
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Burndown chart — work remaining against the ideal line
Chart: 
| Day 0 | Day 2 | Day 4 | Day 6 | Day 8 | Day 10
Ideal remaining | 80 | 64 | 48 | 32 | 16 | 0
Actual remaining | 80 | 78 | 66 | 55 | 30 | 8
WHAT IT TELLS YOU
Tracks the work to be completed in the current iteration, measured in story points or hours.
Used to analyse variance against the ideal burndown of work committed to during iteration planning.
A flat start then a cliff usually means work was integrated late — a definition-of-done problem, not a capacity problem.
A line above ideal at mid-sprint is the trigger for a scope conversation with the product owner, not overtime.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
209

## Slide 210
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Burnup chart — completed work against total scope
Chart: 
| Iter 1 | Iter 2 | Iter 3 | Iter 4 | Iter 5 | Iter 6
Total scope | 100 | 100 | 112 | 112 | 120 | 120
Work completed | 18 | 39 | 57 | 74 | 95 | 118
WHAT IT TELLS YOU
Shows accumulated progress of completed work, updated after each iteration.
Unlike a burndown, it separates the two causes of a slipping date: slower delivery versus growing scope.
A rising top line is scope growth made visible — the single most useful chart in a scope-creep conversation.
The intersection of the two lines is the forecast completion point for the release.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
210

## Slide 211
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Velocity — the team's measured rate of progress
Chart: 
| Iter 1 | Iter 2 | Iter 3 | Iter 4 | Iter 5 | Iter 6
Story points completed | 18 | 21 | 18 | 24 | 22 | 23
WHAT IT TELLS YOU
Velocity is the number of story points completed during an iteration, counted only for items meeting the definition of done.
Estimate it initially, then modify it using actuals from subsequent iterations — never negotiate it upward.
The goal is a constant, predictable velocity from one iteration to the next, not a rising one.
Forecast: remaining backlog points divided by average velocity gives the number of iterations still required.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
211

## Slide 212
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Continuous flow metrics
Metric | Definition | What it tells you
WIP (work in progress) | Measure of work started but not yet completed | High WIP means context switching and delayed value
Lead time | Length of time a work item takes to go through the entire process, from request to delivery | What the customer actually experiences as responsiveness
Cycle time | Length of time a work item is actively being worked on | Your team's execution speed once work truly starts
Throughput | Number of items entering or exiting the system per unit of time | Delivery capacity — the basis for flow forecasting
Queue time | Lead time minus cycle time | The waiting; usually the largest and most ignored part of lead time
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
212

## Slide 213
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Little's Law and flow arithmetic
Little's Law
L = λ × W
Average work in progress equals arrival rate times average lead time — cut WIP and lead time falls.
Average cycle time
WIP ÷ Throughput
If 12 items are in progress and you finish 3 per week, each takes about 4 weeks.
Flow efficiency
Cycle time ÷ Lead time
Typically 5-15% in knowledge work; the rest is queueing, not working.
Iterations remaining
Backlog points ÷ Velocity
The agile forecast — a range, using best and worst recent velocity.
Little's Law is why WIP limits work: with throughput roughly fixed by team capacity, the only lever you control for faster delivery is starting less work at once.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
213

## Slide 214
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Define Activities — ITTO
Work packages are nouns; activities are verbs. Define Activities is where the deliverable-oriented WBS becomes executable work.
INPUTS
Project management plan: schedule management plan, scope baseline
EEFs — organisational structure, published commercial information
OPAs — activity lists from prior projects, standard templates
TOOLS & TECHNIQUES
Expert judgment from those who will perform the work
Decomposition of work packages into schedule activities
Rolling wave planning for the later horizons
Meetings — including team planning sessions
OUTPUTS
Activity list — all schedule activities with scope of work
Activity attributes — predecessors, successors, leads, lags, resource requirements, constraints and assumptions
Milestone list — mandatory and optional milestones
Change requests and plan updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
214

## Slide 215
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
The schedule development sequence
STEP 1
Define activities
Break each work package into the activities required to produce it.
STEP 2
Sequence
Determine dependencies and precedence relationships between the activities.
STEP 3
Estimate durations
Estimate each activity based on the resources assumed to be assigned to it.
STEP 4
Analyse the network
Run forward and backward passes to find float and the critical path.
STEP 5
Optimise and baseline
Level resources, compress if needed, then baseline the approved schedule model.
Every one of these steps is iterative: over-allocated resources or a date constraint will send you back to re-sequence and re-estimate before you can baseline anything.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
215

## Slide 216
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Activity dependency types
Type | Meaning | Action by the project manager
Mandatory (hard logic) | Contractually required or inherent in the nature of the work — concrete must cure before you build on it | Must schedule it; there is no way around this sequence
Discretionary (soft logic) | Established because of best practice or because a specific sequence is preferred | Can be changed; the first place to look when compressing
External | Relationship between a project activity and a non-project activity, such as a regulator's approval | Outside your control; manage as a risk and monitor closely
Internal | Relationship between two project activities, generally inside the team's control | Within the team's control; re-sequence freely if it helps
Dependencies combine: a dependency can be mandatory-external (a legally required inspection) or discretionary-internal (a preferred build order). Name both attributes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
216

## Slide 217
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Sequence Activities — ITTO
Sequencing produces logic, not dates. Dates only appear after durations are estimated and the network is analysed.
INPUTS
Project management plan: schedule management plan, scope baseline
Project documents: activity list and attributes, assumption log, milestone list
EEFs — government standards, scheduling tools, PMIS
OPAs — existing schedule methodology and network templates
TOOLS & TECHNIQUES
Precedence diagramming method (PDM)
Dependency determination and integration — mandatory, discretionary, external, internal
Leads and lags
Project management information system (PMIS)
OUTPUTS
Project schedule network diagram — the logical flow
Project document updates: activity attributes, activity list, assumption log, milestone list
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
217

## Slide 218
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Precedence relationships in the PDM
Relationship | Rule | Everyday example
Finish-to-Start (FS) | The successor cannot start until the predecessor finishes | Testing cannot start until the build is finished — by far the most common
Start-to-Start (SS) | The successor cannot start until the predecessor starts | Pouring concrete starts once levelling starts, running in parallel behind it
Finish-to-Finish (FF) | The successor cannot finish until the predecessor finishes | Document writing cannot finish until testing finishes
Start-to-Finish (SF) | The successor cannot finish until the predecessor starts | The old shift cannot end until the new shift starts — rare, appears on the exam
Memory aid: name the PREDECESSOR's end first, then the SUCCESSOR's end. Start-to-Finish is the only one that feels backwards, which is exactly why it is examined.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
218

## Slide 219
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Leads versus lags
LEAD — BRING IT FORWARD
Accelerates the successor; shown as a negative value
The amount of time a successor activity can be advanced
Example: start writing training material two weeks before build ends
Written as FS minus 2 weeks on the network diagram
Used to compress a schedule by overlapping activities
Adds risk: you are working on an unfinished predecessor
LAG — DELAY IT
Delays the successor; shown as a positive value
The amount of time a successor activity must be delayed
Example: concrete must cure for 7 days before the next activity
Written as FS plus 7 days on the network diagram
Represents mandatory waiting, not slack or float
Cannot usually be removed — it is physics or contract, not choice
Do not confuse lag with float. Lag is designed waiting inside the logic; float is calculated flexibility that falls out of the network analysis.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
219

## Slide 220
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Estimate Activity Durations — ITTO
Duration is not effort: 40 hours of effort by one half-time person is a two-week duration.
INPUTS
Project management plan: schedule management plan, scope baseline
Project documents: activity list and attributes, assumption log, lessons learned register, milestone list, resource requirements, resource calendars, risk register
EEFs — productivity metrics, published commercial information
OPAs — historical duration information, calendars, scheduling method
TOOLS & TECHNIQUES
Expert judgment from the people doing the work
Analogous estimating — top-down from a similar past activity
Parametric estimating — a rate times a quantity
Three-point estimating — optimistic, most likely, pessimistic
Bottom-up estimating — aggregate the detailed components
Data analysis: alternatives analysis, reserve analysis
Decision making and meetings
OUTPUTS
Duration estimates — quantitative assessments, with ranges
Basis of estimates — assumptions, constraints, confidence level
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
220

## Slide 221
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Duration and cost estimating techniques compared
Technique | How it works | Accuracy and cost
Expert judgment | Ask the team or the people who will do the work, using their experience of similar tasks | Fast; quality depends entirely on the expert's relevance
Analogous (top-down) | Use a similar past project, product or system as the analogy and scale it | Fast and cheap; lowest accuracy — used early when little detail exists
Parametric | Multiply a unit rate by a quantity — $55 per metre, 8 hours per drawing | More accurate than analogous if the historical data is genuinely comparable
Three-point (PERT) | Weighted average of optimistic, most likely and pessimistic estimates | Accounts for uncertainty and reduces single-point optimism bias
Bottom-up | Estimate each work package and aggregate upward through the WBS | Most accurate but the most time-consuming and costly
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
221

## Slide 222
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Three-point estimating — PERT arithmetic
Triangular (simple average)
(O + M + P) / 3
Equal weight to all three points; used when the distribution is genuinely unknown.
Beta / PERT
(O + 4M + P) / 6
Weights the most likely estimate four times; the PMI default for three-point estimating.
Standard deviation
(P - O) / 6
The spread of the estimate — a large sigma is a signal to decompose further.
Variance
((P - O) / 6)²
Variances are additive along a path; standard deviations are not. Sum variances, then square-root.
O = optimistic, M = most likely, P = pessimistic. Worked example: O=6, M=10, P=20 gives PERT = (6 + 40 + 20)/6 = 11 days, with sigma = (20-6)/6 = 2.33 days.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
222

## Slide 223
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Develop Schedule — ITTO
Develop Schedule is iterative — you will loop through analysis, optimisation and compression before anything is baselined.
INPUTS
Project management plan: schedule management plan, scope baseline
Project documents: activity list and attributes, assumption log, basis of estimates, duration estimates, milestone list, network diagram, resource calendars and requirements, risk register
Agreements, EEFs and OPAs
TOOLS & TECHNIQUES
Schedule network analysis
Critical path method (CPM)
Resource optimisation — levelling and smoothing
Data analysis: what-if scenario analysis, simulation (Monte Carlo)
Leads and lags
Schedule compression — crashing and fast tracking
PMIS and agile release planning
OUTPUTS
Schedule baseline — the approved version of the schedule model
Project schedule — with planned dates for each activity
Schedule data and project calendars
Change requests and project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
223

## Slide 224
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Float and critical path arithmetic
Total float
LS − ES (or LF − EF)
How long an activity can slip without delaying the project end date.
Free float
ES(successor) − EF(activity) − 1
How long an activity can slip without delaying its earliest successor.
Critical path
The path with zero total float
The longest path through the network and therefore the shortest project duration.
Project float
Imposed date − Calculated finish
Slack against an externally imposed deadline; can be negative.
Negative total float means the network cannot meet the imposed date as sequenced — the trigger for schedule compression, not for quietly changing the finish date in the tool.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
224

## Slide 225
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Forward and backward pass — calculating the network
STEP 1
Forward pass
Move left to right computing Early Start and Early Finish: EF = ES + Duration − 1.
STEP 2
Take the maximum
Where paths merge, the successor's ES is the LARGEST EF of its predecessors — the latest gate governs.
STEP 3
Backward pass
Move right to left computing Late Finish and Late Start: LS = LF − Duration + 1.
STEP 4
Take the minimum
Where paths diverge, the predecessor's LF is the SMALLEST LS of its successors.
STEP 5
Compute float
Total float = LS − ES. Activities with zero float form the critical path.
Exam discipline: a network can have more than one critical path, and the critical path can change during execution as actuals come in. Recalculate; never assume it is fixed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
225

## Slide 226
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Schedule compression — crashing versus fast tracking
CRASHING
Add resources to critical path activities
Adds cost to buy back duration on the critical path only
Overtime, extra staff, paying to expedite deliveries
Subject to diminishing returns — nine women, one month
Always increases cost; may increase risk through fatigue
Choose the activity with the lowest cost per day saved
FAST TRACKING
Overlap activities normally done in sequence
Converts finish-to-start logic into overlap or start-to-start
Costs nothing directly — you pay in risk instead
Only discretionary dependencies can be fast tracked
Increases rework risk: the predecessor may still change
Try fast tracking first, then crash what remains
Neither technique changes scope. If compression cannot recover the date, the correct move is to escalate the trade-off, not to silently reduce quality.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
226

## Slide 227
EXAM FOCUS
Exam focus — schedule
IF THE QUESTION SAYS
The question gives a network diagram and asks for the shortest duration
THE BEST ANSWER IS
That is the critical path — the longest path through the network, with zero float
IF THE QUESTION SAYS
You need to shorten the schedule without adding cost
THE BEST ANSWER IS
Fast track by overlapping discretionary dependencies; crashing always costs money
IF THE QUESTION SAYS
An activity has 5 days of total float and slips 3 days
THE BEST ANSWER IS
The project end date is unaffected; only floats downstream change
IF THE QUESTION SAYS
Concrete must cure for 7 days before the next activity
THE BEST ANSWER IS
That is a mandatory dependency with a 7-day lag, not float
IF THE QUESTION SAYS
The team's velocity is 20 points and 100 points remain
THE BEST ANSWER IS
Forecast roughly 5 more iterations — express it as a range using best and worst recent velocity
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
227

## Slide 228
RECAP
Recap — schedule planning
1
Six processes
Plan Schedule Management, Define Activities, Sequence, Estimate Durations, Develop Schedule, Control Schedule.
2
Logic before dates
Sequencing produces a network diagram; dates only exist after durations and network analysis.
3
Four dependencies
Mandatory, discretionary, external, internal — and they combine into pairs.
4
Four relationships
FS is the default; SS and FF enable overlap; SF is rare and examined.
5
Float is calculated
Total float protects the end date; free float protects the successor; zero float is critical.
6
Agile still forecasts
Velocity, burndown, burnup and flow metrics replace the Gantt but do the same forecasting job.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
228

## Slide 229
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Knowledge area 3 of 8 in the planning block
Cost: estimate honestly, then fund the uncertainty
Estimate
Determine the approximate monetary resources needed to complete each activity and work package.
Budget
Aggregate those estimates into an authorised, time-phased cost baseline you can measure against.
Reserve
Fund the known-unknowns and the unknown-unknowns separately — they have different owners.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
229

## Slide 230
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Plan Cost Management — ITTO
Set the rules of the money before you produce a number — otherwise nobody agrees what the number means.
INPUTS
Project charter — summary budget and approval requirements
Project management plan: schedule and risk management plans
EEFs — exchange rates, market conditions, financial controls
OPAs — financial policies, historical cost data, estimating templates
TOOLS & TECHNIQUES
Expert judgment on financial management and estimating
Data analysis — alternatives analysis on funding, make-or-buy, and on how to acquire project resources
Meetings with sponsor, finance and the PMO
OUTPUTS
Cost management plan — units of measure, precision, accuracy, organisational procedure links (control accounts / code of accounts)
Control thresholds and rules of performance measurement (EVM)
Reporting formats and process descriptions
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
230

## Slide 231
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Estimate Costs — ITTO
Cost estimates are a prediction with a range and a confidence level, never a single number stated as fact.
INPUTS
Project management plan: cost and quality management plans, scope baseline
Project documents: lessons learned register, project schedule, resource requirements, risk register
EEFs — market conditions, published commercial information
OPAs — cost estimating policies and templates, historical data
TOOLS & TECHNIQUES
Expert judgment
Analogous estimating
Parametric estimating
Bottom-up estimating
Three-point estimating
Data analysis: alternatives analysis, reserve analysis, cost of quality
Project management information system and decision making (voting)
OUTPUTS
Cost estimates for each activity, including contingency
Basis of estimates — assumptions, constraints, range, confidence
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
231

## Slide 232
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
The four cost estimating methods in detail
1
Analogous estimating
Uses historical information and expert judgment from a previous similar project; pick the next closest project when an exact match does not exist.
2
When to use analogous
Low cost and quick — the right choice very early when detail is scarce and a rough order of magnitude is all that is needed.
3
Parametric estimating
Takes variables from historical data and applies them: cost = number of resistors × cost per resistor, or rate per operator × number of operators.
4
When to use parametric
When there is a genuine linear driver and credible historical data; scales far better than analogous.
5
Bottom-up estimating
Rolls costs up from the smallest activity upward, using the WBS to structure the estimates.
6
When to use bottom-up
The most accurate method but the most time consuming and costly; used once the WBS is complete.
7
Three-point estimating
Uses a weighted average of three estimates to reduce bias and represent uncertainty explicitly.
8
When to use three-point
Whenever a single number would hide real uncertainty — especially for novel or high-risk work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
232

## Slide 233
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Three-point cost estimating
Beta / PERT cost
Ce = (Co + 4Cm + Cp) / 6
Ce estimated cost, Co optimistic, Cm most likely, Cp pessimistic.
Triangular cost
Ce = (Co + Cm + Cp) / 3
Used when there is no reason to weight the most likely value more heavily.
Cost standard deviation
σ = (Cp − Co) / 6
The spread; quote Ce ± 2σ to give the sponsor a 95% range.
Range example
O=80k, M=100k, P=180k
PERT = (80 + 400 + 180)/6 = $110k, σ = $16.7k, so 95% range is roughly $77k to $143k.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
233

## Slide 234
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Determine Budget — ITTO
The cost baseline is the S-curve. Management reserve sits above it and forms the total project budget.
INPUTS
Project management plan: cost management plan, resource management plan, scope baseline
Project documents: basis of estimates, cost estimates, project schedule, risk register
Business documents: business case and benefits management plan
Agreements, EEFs and OPAs
TOOLS & TECHNIQUES
Expert judgment
Cost aggregation — roll work package costs to control accounts
Data analysis — reserve analysis
Historical information review
Funding limit reconciliation
Financing
OUTPUTS
Cost baseline — the approved time-phased budget, excluding management reserve
Project funding requirements — total and periodic, including expected expenditure and liabilities
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
234

## Slide 235
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
The cost baseline S-curve and the funding steps
Chart: 
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8
Cumulative cost baseline | 40 | 110 | 230 | 420 | 640 | 810 | 910 | 950
Funding requirements | 200 | 200 | 400 | 600 | 800 | 1000 | 1000 | 1000
WHAT IT TELLS YOU
The cost baseline is time-phased: it says not only how much, but when the money is expected to be spent.
Cumulative spend follows an S-curve — slow at first, steep in execution, flattening at closure.
Funding arrives in steps, usually quarterly; funding limit reconciliation aligns the smooth curve to the steps.
The gap between the funding line and the baseline is the management reserve plus the funding buffer.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
235

## Slide 236
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Contingency reserve versus management reserve
CONTINGENCY RESERVE
For identified risks — the known-unknowns
Set aside to deal with identified risks should they occur
Calculated from quantitative risk analysis or EMV of the register
INCLUDED in the cost baseline and in the schedule baseline
The project manager may spend it without a change request
Reserve analysis reports risk remaining versus contingency remaining
MANAGEMENT RESERVE
For unidentified risks — the unknown-unknowns
Set aside for unforeseen work that is still within project scope
Typically a management-set percentage of the total baseline
EXCLUDED from the cost baseline; part of the total project budget
Requires management approval to access — usually a change request
Using it changes the cost baseline; using contingency does not
Total project budget = cost baseline + management reserve. Cost baseline = work package costs + contingency reserve. This distinction is examined heavily.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
236

## Slide 237
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
ECO 2026 emphasis — managing financial reserves
1
Quantify allocations
Quantify risk and contingency financial allocations explicitly rather than adding a round percentage.
2
Plan spend tracking
Design how spend will be tracked across the whole life cycle before the first invoice arrives.
3
Plan financial reporting
Agree the format, frequency and audience of financial reporting with finance and the sponsor.
4
Anticipate challenges
Look ahead for funding gaps, exchange rate exposure, and cost inflation on long-lead procurement.
5
Monitor variation
Work with the governance process when financial variations exceed the agreed control threshold.
6
Release unused reserve
Reserves for risks that have passed should be returned, not quietly absorbed into the project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
237

## Slide 238
EXAM FOCUS
Exam focus — cost
IF THE QUESTION SAYS
A risk in the register occurs and you need funds
THE BEST ANSWER IS
Use the contingency reserve — no change request needed, it is already inside the cost baseline
IF THE QUESTION SAYS
Unforeseen in-scope work appears that nobody identified
THE BEST ANSWER IS
Request management reserve through management approval; this changes the cost baseline
IF THE QUESTION SAYS
You need a quick figure with almost no detail available
THE BEST ANSWER IS
Analogous estimating — fast and cheap, lowest accuracy
IF THE QUESTION SAYS
The question gives O, M and P values
THE BEST ANSWER IS
Apply (O + 4M + P) / 6 unless the question explicitly says triangular or simple average
IF THE QUESTION SAYS
You are asked for the total project budget
THE BEST ANSWER IS
Cost baseline plus management reserve — the baseline alone is not the budget
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
238

## Slide 239
RECAP
Recap — cost planning
1
Rules first
The cost management plan sets units, precision, thresholds and the EVM rules before any number is produced.
2
Four methods
Analogous, parametric, bottom-up and three-point — trading speed against accuracy.
3
PERT
(O + 4M + P) / 6 with σ = (P − O) / 6 turns a guess into a range with a stated confidence.
4
Aggregate to baseline
Work packages roll to control accounts, then to the time-phased cost baseline S-curve.
5
Two reserves
Contingency is inside the baseline for known risks; management reserve sits outside it for unknown ones.
6
Reconcile funding
Funding limit reconciliation aligns the smooth spend curve to the stepped release of actual funds.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
239

## Slide 240
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Knowledge area 4 of 8 in the planning block
Quality: how well deliverables meet requirements
Quality vs grade
Quality is conformance to requirements; grade is the category of features. Low grade can be acceptable; low quality never is.
Prevention over inspection
It is always cheaper to design defects out than to inspect and rework them later.
Everyone's job
In agile the whole team owns quality, from writing correct requirements to automated testing.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
240

## Slide 241
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Quality in predictive versus agile delivery
PREDICTIVE QUALITY
Build, then test — usually in large batches
The product is developed and then tested in sequential order
Testing is a distinct phase performed by a separate QA function
Defects are found late, when they are most expensive to fix
Formal quality audits and phase gate reviews provide assurance
Acceptance is a single formal event near the end
AGILE QUALITY
Build quality in, continuously
Quality is everyone's responsibility, from requirement to release
Test-driven development and automated regression on every commit
Definition of done enforces quality before a story is accepted
Continuous integration finds integration defects within hours
Acceptance happens every iteration at the review
Both approaches tie quality to the product acceptance criteria described in the statement of work or design documents — update those criteria as experimentation and prioritisation occur, then validate them at acceptance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
241

## Slide 242
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Plan Quality Management — ITTO
Plan Quality Management defines what good looks like and how it will be proven, before any deliverable exists.
INPUTS
Project charter — high-level requirements and success criteria
Project management plan: requirements, risk and stakeholder engagement plans, and the scope baseline
Project documents: assumption log, requirements documentation, RTM, risk register, stakeholder register
EEFs — regulations, rules, standards and geographic conditions
OPAs — quality policy, historical databases, lessons learned
TOOLS & TECHNIQUES
Expert judgment on quality assurance and control
Data gathering: benchmarking, brainstorming, interviews
Data analysis: cost-benefit analysis, cost of quality
Decision making: multi-criteria decision analysis
Data representation: flowcharts, logical data model, matrix diagrams, mind mapping
Test and inspection planning; meetings
OUTPUTS
Quality management plan — how standards will be implemented
Quality metrics — the specific attribute and how it is measured
Project management plan updates and document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
242

## Slide 243
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
The quality management plan and its benefits
1
What it contains
The activities and resources that will achieve the quality objectives, and who is accountable for each.
2
How formal
May be formal or informal, highly detailed or broadly framed — tailored to the project's risk and regulatory context.
3
Living document
Reviewed throughout the project as the product and the risk profile change.
4
Sharper value focus
Forces the team to state what the customer actually values, rather than what is easy to measure.
5
Cost reduction
Prevention and appraisal spend consistently costs less than the failure costs it avoids.
6
Fewer schedule overruns
Most predictive schedule overrun is rework; designing rework out protects the date.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
243

## Slide 244
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Cost of Quality (CoQ) — the four categories
Category | Definition | Typical spend
Prevention (conformance) | The cost to prevent future defects or errors in the product | Training, prototypes, code refactoring, design reviews, standards, tooling
Appraisal (conformance) | The cost to find defects or errors in the product | Testing, quality audits, inspections, the sprint review, destructive test loss
Internal failure (non-conformance) | Failure found by the project, before the customer sees it | Rework, scrap, re-testing, defect triage, schedule slip
External failure (non-conformance) | Failure found by the customer, after delivery | Warranty work, recalls, liability, lost business, reputational damage
Cost of conformance (prevention + appraisal) is money spent during the project to avoid failure. Cost of non-conformance is money spent during and after the project because you did not.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
244

## Slide 245
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
The cost of change curve — quality is cheapest early
Chart: 
| Requirements | Design | Build | System test | Production
Relative cost to fix one defect | 1 | 5 | 10 | 25 | 100
WHAT IT TELLS YOU
Quality is more expensive to fix the closer it gets to the customer — the classic 1:100 relationship.
This curve is the economic justification for prevention spend, code review and test automation.
It is also the argument for short iterations: shorter feedback loops keep you at the cheap end of the curve.
Project risk follows exactly the same curve — early treatment is dramatically cheaper than late response.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
245

## Slide 246
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
PDCA — the Deming/Shewhart improvement cycle
STEP 1
Plan
Review real data or go and see the problem directly; find the root cause, then brainstorm and prioritise solutions with the team.
STEP 2
Do
Put the plan into action as a pilot or test in a small area first, so a failed idea is cheap.
STEP 3
Check
Check the results against what you predicted, using the same measure you baselined.
STEP 4
Act
Adopt, adapt or abandon — standardise what worked, then start the next turn of the cycle.
PDCA is a cycle, not a project: the value comes from turning it repeatedly and quickly, not from executing it perfectly once.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
246

## Slide 247
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
DMAIC — the Six Sigma improvement framework
STEP 1
Define
Define the problem clearly, as the gap between where you are and where you want to be.
STEP 2
Measure
Measure the current problem with real data, not with opinion or recollection.
STEP 3
Analyse
Analyse the data, find the root cause, then brainstorm and prioritise solutions with the team.
STEP 4
Improve
Put the plan into action and measure whether the gap actually closed.
STEP 5
Control
Lock the gain in with standards, monitoring and control charts so the problem cannot quietly return.
Six Sigma focuses on removing variation and waste. Kaizen — 'change for better' — is the complementary philosophy of many small continuous improvements made by the people doing the work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
247

## Slide 248
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Root cause analysis toolkit
1
Fishbone / Ishikawa
A cause-and-effect diagram grouping candidate causes into categories around a single problem statement.
2
The 6M categories
Manpower, Method, Machine, Material, Measurement, Mother Nature — the classic manufacturing spine.
3
Five Whys
Ask 'why' repeatedly to drill from the visible symptom down to the systemic cause that actually needs fixing.
4
Pareto chart
Ranks defect categories by frequency to find the vital few driving most of the pain.
5
Six Thinking Hats
De Bono's method: examine a situation deliberately from six distinct thinking modes in turn.
6
Control chart
Plots a process against control limits over time to separate special-cause signal from common-cause noise.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
248

## Slide 249
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Pareto chart — the vital few defect categories
Chart: 
| Data entry | Interface | Validation | Timeout | Formatting | Other
Defect count | 88 | 54 | 31 | 14 | 9 | 4
WHAT IT TELLS YOU
The 80/20 rule: roughly 80% of the defects come from roughly 20% of the causes.
Directs improvement effort where it makes the biggest impact, instead of spreading it evenly across every category.
Takes a big vague problem ('quality is poor') and breaks it into actionable, countable pieces.
Re-run after the improvement: the bars should shrink and the ranking should change.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
249

## Slide 250
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Quality standards, regulations and compliance
1
ASQ
The American Society for Quality — steward of the ISO 9000 series quality management standards.
2
Chartered Quality Institute
The UK professional body for quality practitioners and quality management systems.
3
ASTM International
Publishes technical standards for materials, products, systems and services across industries.
4
Government regulation
Appropriate government regulations are mandatory inputs, not optional quality aspirations.
5
Organisational policies
Internal quality policy and product standards constrain what 'acceptable' can mean.
6
Compliance actions
Classify compliance categories, determine threats to compliance, analyse the consequences of non-compliance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
250

## Slide 251
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
ECO 2026 emphasis — sustainability in quality planning
1
Sustainability as a requirement
Environmental and social criteria are gathered as quality requirements, not treated as PR.
2
Measure it
Define metrics — energy per transaction, waste diverted, carbon per deliverable — and baseline them like any other.
3
Cost of quality extension
Environmental failure cost (remediation, penalties, disposal) belongs in the non-conformance column.
4
Design out waste
Prevention applies to material and energy waste exactly as it applies to defects.
5
Regulatory exposure
Sustainability reporting obligations are compliance requirements with real legal consequence.
6
AI-assisted review
AI tools can scan designs and specifications for waste and compliance gaps — the human still decides.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
251

## Slide 252
EXAM FOCUS
Exam focus — quality
IF THE QUESTION SAYS
The team wants to inspect more to raise quality
THE BEST ANSWER IS
Prefer prevention over inspection — the cheapest defect is the one never created
IF THE QUESTION SAYS
A customer reports a defect after handover
THE BEST ANSWER IS
That is an external failure cost — the most expensive category of cost of non-conformance
IF THE QUESTION SAYS
You must find why a defect keeps recurring
THE BEST ANSWER IS
Root cause analysis: five whys or an Ishikawa diagram — treat the cause, not the symptom
IF THE QUESTION SAYS
Many defect categories; limited improvement budget
THE BEST ANSWER IS
Build a Pareto chart and attack the vital few that produce most of the defects
IF THE QUESTION SAYS
The product meets all specifications but is low-featured
THE BEST ANSWER IS
That is low grade with high quality — acceptable if agreed; low quality never is
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
252

## Slide 253
RECAP
Recap — quality planning
1
Quality is conformance
How well the deliverable meets the requirement — distinct from grade, which is feature category.
2
Plan it
The quality management plan states standards, metrics, roles and review activity before delivery starts.
3
Four CoQ buckets
Prevention and appraisal are conformance; internal and external failure are non-conformance.
4
Cost of change curve
Defect fix cost rises roughly 1:100 from requirements to production — buy prevention.
5
Improvement cycles
PDCA and DMAIC give a repeatable structure; Kaizen supplies the culture of small continuous change.
6
RCA toolkit
Fishbone, five whys, Pareto, Six Thinking Hats and control charts — pick the tool that fits the data you have.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
253

## Slide 254
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Knowledge area 5 of 8 in the planning block
Resources: people and things, planned deliberately
Team resources
The people who will do the work, their roles, authority, responsibility and required competency.
Physical resources
Materials, equipment, facilities and infrastructure that must be acquired and released.
The constraint
Resource availability, not activity duration, is what most often determines the real schedule.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
254

## Slide 255
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Plan Resource Management — ITTO
This plan covers physical resources and team resources — most exam errors come from forgetting the physical half.
INPUTS
Project charter — high-level roles and sponsor commitment
Project management plan: quality management plan, scope baseline
Project documents: project schedule, requirements documentation, risk register, stakeholder register
EEFs — organisational structure, existing resources, marketplace
OPAs — HR policies, safety policies, templates, historical data
TOOLS & TECHNIQUES
Expert judgment on resourcing and organisational design
Data representation: hierarchical charts, responsibility assignment matrix (RAM/RACI), text-oriented formats
Organisational theory (Tuckman, Maslow, Herzberg, McGregor)
Meetings with functional managers and the team
OUTPUTS
Resource management plan — how resources are identified, acquired, managed and released
Team charter — team values, agreements and operating guidelines
Project document updates: assumption log, risk register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
255

## Slide 256
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Role definition — the four attributes
Attribute | Definition | What goes wrong if it is vague
Role | A person's designated function on the project — business analyst, test lead, architect | People duplicate work or assume someone else is covering a gap
Authority | The right to apply resources, make decisions, sign approvals and accept deliverables | Decisions stall waiting for someone who never had the mandate
Responsibility | The assigned duties a role must perform to complete project activities | Work is 'everybody's job' and therefore nobody's job
Competency | The skill and capacity required to complete the assigned activities within the constraints | Work is assigned to people who cannot succeed at it — a schedule risk, not a people problem
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
256

## Slide 257
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Resource optimisation — levelling versus smoothing
RESOURCE LEVELLING
Fix over-allocation; the end date may move
Applied when shared resources are over-allocated
Or when a resource is assigned to two or more activities in the same period
Adjusts start and finish dates based on resource constraints
CAN change the critical path — usually extending it
Use when the resource limit is genuinely hard (one specialist)
RESOURCE SMOOTHING
Even out demand; the end date is protected
Adjusts activities only within their free and total float
The critical path is NOT changed by smoothing
Cannot fully resolve a genuine over-allocation
Produces a more even resource demand profile over time
Use when the date is fixed and float is available to spend
Memory hook: LEVELLING may LENGTHEN the project; SMOOTHING Stays inside Slack. If the question says the end date must not move, the answer is smoothing.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
257

## Slide 258
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Estimate Activity Resources — ITTO
Estimate Activity Resources runs closely with Estimate Activity Durations — the two are mutually dependent.
INPUTS
Project management plan: resource management plan, scope baseline
Project documents: activity attributes and list, assumption log, cost estimates, resource calendars, risk register
EEFs — resource location, availability, skills, marketplace
OPAs — policies on staffing and equipment, historical information
TOOLS & TECHNIQUES
Expert judgment on resource types and quantities
Bottom-up estimating from activity level upward
Analogous and parametric estimating
Data analysis — alternatives analysis (make/rent/buy, skill mix)
Project management information system and meetings
OUTPUTS
Resource requirements — types and quantities per work package
Basis of estimates — method, assumptions, confidence level
Resource breakdown structure (RBS) by category and type
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
258

## Slide 259
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
RACI — the responsibility assignment matrix
Letter | Meaning | Rule
R — Responsible | The person or people who actually perform the work | At least one per activity; more than one is fine
A — Accountable | The single person answerable for the outcome, who approves the work | EXACTLY ONE per activity — two means nobody
C — Consulted | People whose input is sought before the work is done; two-way communication | Keep the list short; every C is a delay
I — Informed | People told about progress or outcomes; one-way communication | Cheap to add, so it is where over-communication usually hides
A responsibility assignment matrix shows which team members are responsible for which work packages. Read the ROWS to find unassigned work; read the COLUMNS to find overloaded people.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
259

## Slide 260
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Co-location, osmotic communication and the team charter
1
Co-location
Agile teams prefer to sit together so that coordination happens continuously rather than in scheduled meetings.
2
Osmotic communication
Team members absorb useful information from overheard conversations without anyone having to brief them.
3
Information radiator
A large visible display of project information in the team area — status without a status meeting.
4
Team charter
Created WITH the team; it establishes values, agreements and operating guidelines the team owns.
5
Ground rules
Explicit agreements on meetings, decisions, conflict and communication — enforced by the team, not just the PM.
6
Virtual co-location
Persistent video rooms and shared boards recreate some osmotic benefit for distributed teams.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
260

## Slide 261
EXAM FOCUS
Exam focus — resources
IF THE QUESTION SAYS
A key specialist is booked on two activities at the same time
THE BEST ANSWER IS
Resource levelling — and accept that the end date may move
IF THE QUESTION SAYS
Demand is uneven but the finish date is fixed and float exists
THE BEST ANSWER IS
Resource smoothing — adjust only within free and total float
IF THE QUESTION SAYS
Two people are marked Accountable for the same deliverable
THE BEST ANSWER IS
That is the defect: RACI allows exactly one Accountable per row
IF THE QUESTION SAYS
The team keeps rediscovering the same information late
THE BEST ANSWER IS
Co-locate or add an information radiator; osmotic communication solves this without adding meetings
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
261

## Slide 262
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Knowledge area 6 of 8 in the planning block
Communication: the PM's largest single time cost
The 90% figure
Project managers spend the overwhelming majority of their time communicating — plan it like any other work.
Planned, not ad hoc
Who needs what, in what format, how often, through which channel, and why.
Two-way by design
Communication without a feedback loop is broadcasting, and broadcasting is not engagement.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
262

## Slide 263
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Plan Communications Management — ITTO
The plan defines the strategy; execution is Manage Communications and Monitor Communications.
INPUTS
Project charter — key stakeholders and their roles
Project management plan: resource management plan, stakeholder engagement plan
Project documents: requirements documentation, stakeholder register
EEFs — organisational culture, geographic distribution, regulatory and legal reporting requirements
OPAs — historical information, lessons learned, templates
TOOLS & TECHNIQUES
Expert judgment on politics, media and cross-cultural nuance
Communication requirements analysis
Communication technology, models and methods
Interpersonal and team skills: communication styles assessment, political awareness, cultural awareness
Data representation — stakeholder engagement assessment matrix
Meetings
OUTPUTS
Communications management plan
Project management plan updates and document updates (stakeholder register, project schedule)
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
263

## Slide 264
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
What the communications management plan records
1
Roles
Identifies team members and stakeholders as senders, receivers, and the authorising person for confidential information.
2
Type of information
What is communicated — status, decisions, risks, escalations, financials.
3
Reason for communication
Why the communication exists; a report nobody can justify is a report you can stop producing.
4
Language, format, detail
Written in the audience's language and at the level of detail their decision actually requires.
5
Time frame and frequency
When and how often, including escalation-triggered rather than calendar-triggered messages.
6
Method and technology
The channel: meeting, dashboard, email, report — chosen for urgency and richness, not habit.
7
Escalation process
The route and the thresholds for escalating an issue when the normal channel fails.
8
Glossary and constraints
Common terminology, plus any legal or regulatory reporting constraints that apply.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
264

## Slide 265
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
The communication model — where meaning goes missing
STEP 1
Encode
The sender converts thought into a message using words, images or gestures — meaning is already partly lost here.
STEP 2
Transmit
The message travels through a medium: speech, email, chat, video, document.
STEP 3
Noise
Anything distorting the signal — jargon, poor connection, cultural difference, distraction, emotion, fatigue.
STEP 4
Decode
The receiver converts the message back into thought using their own frame of reference, not the sender's.
STEP 5
Acknowledge/feedback
The receiver confirms receipt and understanding; only now is communication actually complete.
On the exam, if a message was sent but not confirmed, communication has NOT occurred. The sender is responsible for making the message clear, complete and understood.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
265

## Slide 266
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Communication channels
Channels formula
N × (N − 1) / 2
N is the number of people; the result is the number of potential communication paths.
Team of 10
10 × 9 / 2 = 45
Ten people generate forty-five possible two-way channels to keep coherent.
Adding one person
From 10 to 11: 45 → 55
One extra person adds ten new channels — complexity grows quadratically.
Team of 50
50 × 49 / 2 = 1225
Why large teams need structure, sub-teams and a plan rather than goodwill.
Exam trap: read carefully whether the question includes the project manager in N. If it says 'you have a team of 8', N is usually 9. If it asks for ADDITIONAL channels, subtract the original count.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
266

## Slide 267
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Push, pull and interactive communication
Method | How it works | Use it for
Interactive | Multi-directional real-time exchange between two or more parties — meetings, calls, video, workshops | Complex, sensitive, ambiguous or urgent topics needing agreement
Push | Sent to specific recipients who need the information — email, memos, reports, letters, voicemail | Distribution where receipt matters but discussion does not
Pull | Recipients access the information at their discretion — intranets, dashboards, knowledge repositories, wikis | Large volumes of information for large, self-serving audiences
Push guarantees distribution but NOT understanding. Only interactive communication closes the loop, which is why bad news is always delivered interactively first.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
267

## Slide 268
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
The Five Cs of written communication
1
Correct
Correct grammar and spelling — errors undermine credibility before the content is even read.
2
Concise
Concise expression with excess words eliminated; length is not a measure of thoroughness.
3
Clear
Clear purpose and expression directed towards the needs of the reader, not the convenience of the writer.
4
Coherent
A logical flow of ideas so the reader can follow the argument without re-reading.
5
Controlling
Controlled flow of words and ideas — structure, headings and emphasis that guide attention.
6
Applied where
Status reports, escalations, meeting minutes, change requests and every stakeholder email.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
268

## Slide 269
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Active listening, feedback and non-verbal signals
1
Listen actively
Stay engaged with the speaker, show interest, and summarise or repeat the message back to check understanding.
2
Seek feedback
Listen to written, verbal and non-verbal feedback to ensure your message and others' were heard correctly.
3
Read non-verbals
Body language, tone and gesture carry a large share of the meaning, especially in conflict.
4
Ask open questions
Questions that cannot be answered yes or no surface the concern behind the objection.
5
Paraphrase, don't parrot
Restating in your own words proves you understood; repeating words only proves you heard.
6
Manage your own bias
The receiver decodes through their own frame of reference; assume misunderstanding, then verify.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
269

## Slide 270
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Virtual versus co-located teams
VIRTUAL TEAM
Now normal in most workplaces
Access to better skills at lower cost across geographies
Avoids relocation expense and widens the talent pool
Supports work/life balance and inclusion of remote members
Relies entirely on communication technology to function
May have bonding challenges and slower trust formation
CO-LOCATED TEAM
Everyone in one team space
Interaction is easy and unplanned — questions cost seconds
Bonding and trust are facilitated by informal contact
Osmotic communication and information radiators work naturally
Non-verbal signals are visible, so conflict surfaces earlier
Constrained to the talent available in one location
For virtual teams, invest deliberately in what co-location gives you free: explicit working agreements, a persistent shared board, video-on norms and scheduled social contact.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
270

## Slide 271
EXAM FOCUS
Exam focus — communication
IF THE QUESTION SAYS
You have 8 team members and 3 new people join
THE BEST ANSWER IS
Channels go from 9×8/2 = 36 to 12×11/2 = 66 — read whether the PM is counted in N
IF THE QUESTION SAYS
A stakeholder says they were never informed of a decision
THE BEST ANSWER IS
Review the communications management plan; the omission is a planning defect, not a personal failing
IF THE QUESTION SAYS
You must deliver bad news to a sponsor
THE BEST ANSWER IS
Use interactive communication — face-to-face or a call — never a push email as the first contact
IF THE QUESTION SAYS
Large volumes of reference material for many stakeholders
THE BEST ANSWER IS
Pull communication: publish to a repository or dashboard they access at their own discretion
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
271

## Slide 272
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Knowledge area 7 of 8 in the planning block
Risk: uncertainty that matters, managed on purpose
Both directions
Risks can be negative (threats) or positive (opportunities) — PMI expects you to plan for both.
Known causes
Risk originates from known and unknown causes inside and outside the business environment.
Trigger conditions
Risk development is signalled by a trigger — identify the trigger, not just the risk.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
272

## Slide 273
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Plan Risk Management — ITTO
Plan Risk Management defines HOW risk work will be done — the definitions of 'high probability' and 'high impact' are set here.
INPUTS
Project charter — high-level risks and success criteria
Project management plan — all subsidiary plans
Project documents: stakeholder register
EEFs — organisational risk thresholds and appetite
OPAs — risk policy, risk categories, templates, lessons learned
TOOLS & TECHNIQUES
Expert judgment on risk methodology
Data analysis — stakeholder risk appetite analysis
Meetings — the risk planning meeting with the team, sponsor and selected stakeholders
OUTPUTS
Risk management plan — methodology, roles and responsibilities, funding, timing, risk categories (RBS)
Stakeholder risk appetite, probability and impact definitions
Probability and impact matrix, reporting formats, tracking
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
273

## Slide 274
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Risk versus issue
RISK
An uncertain future event
Focused on the FUTURE — it may or may not happen
Can be positive (opportunity) or negative (threat)
Documented in the RISK REGISTER
The reaction is called a RISK RESPONSE, planned in advance
Has a probability, an impact, an owner and a trigger condition
ISSUE
A present condition already affecting the project
Focused on the PRESENT — it has already occurred
Will always be negative
Documented in the ISSUE LOG
The reaction is called a WORKAROUND, produced reactively
Has an owner, a target resolution date and an escalation path
When a risk becomes an issue you must act: implement the planned response, log it in the issue log, and update the risk register status. Recognising that transition is an explicit ECO enabler.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
274

## Slide 275
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Risk attitude, appetite, tolerance and threshold
1
Risk attitude
The organisation's or individual's disposition toward uncertainty — averse, neutral or seeking.
2
Risk appetite
The degree of uncertainty the organisation is willing to accept in anticipation of a reward.
3
Risk tolerance
The measurable degree of variation around an objective that is acceptable — for example ±10% of budget.
4
Risk threshold
The specific point at which a risk becomes unacceptable and a response or escalation is mandatory.
5
Why it matters
Thresholds turn a subjective conversation into an automatic, auditable trigger for action.
6
Where captured
Stakeholder risk appetite is analysed in Plan Risk Management and recorded in the risk management plan.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
275

## Slide 276
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Identify Risks — ITTO
Identify Risks is iterative — new risks emerge throughout the project, so the register is never finished.
INPUTS
Project management plan — all subsidiary plans and baselines
Project documents: assumption log, cost and duration estimates, issue log, lessons learned register, requirements documentation, resource requirements, stakeholder register
Agreements, procurement documentation, EEFs and OPAs
TOOLS & TECHNIQUES
Expert judgment
Data gathering: brainstorming, checklists, interviews
Data analysis: root cause analysis, assumption and constraint analysis, SWOT analysis, document analysis
Interpersonal and team skills — facilitation
Prompt lists (RBS, PESTLE, TECOP, VUCA)
Meetings
OUTPUTS
Risk register — the master list of identified risks
Risk report — sources of overall project risk and summary information on identified individual risks
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
276

## Slide 277
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Risk identification techniques
Technique | How it works | Strength
Risk breakdown structure | Hierarchical list of risk categories used as a checklist when brainstorming | Systematic coverage; exposes categories the team never thought about
Brainstorming | Facilitated group generation of candidate risks with judgement deferred | Volume and diversity of ideas early
SWOT analysis | Examine strengths, weaknesses, opportunities and threats of the project and organisation | Systematically surfaces OPPORTUNITIES, not just threats
Assumption analysis | Test the validity and stability of each documented assumption and constraint | Every assumption is an unregistered risk until tested
Delphi technique | Anonymous rounds of expert input, summarised and recirculated until consensus | Removes dominance and groupthink from expert judgement
Document review | Structured review of plans, contracts, prior project files and lessons learned | Cheap and finds risks the organisation has already met before
Nominal group technique | Brainstorm then vote to rank the risks | Produces a prioritised list in one session
Interviews | One-to-one questioning of experienced participants | Surfaces political or commercially sensitive risks
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
277

## Slide 278
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Common project risk categories
1
Financial
Benefit shortfall, budget overrun, exchange rate movement, funding withdrawal, cost inflation on long-lead items.
2
Technical
Design risk, project complexity, integration failure, unproven technology, technical debt accumulation.
3
Commercial
Supplier failure, procurement delay, contract dispute, vendor lock-in, insolvency of a key partner.
4
Compliance
Regulatory change, legal risk, health and safety, data protection, security and IT security exposure.
5
Requirements
Scope creep, requirement volatility, poor estimates, unclear acceptance criteria, quality risk.
6
Organisational
Resistance to change, resource unavailability, programme dependency, reputation risk, key person dependency.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
278

## Slide 279
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Building a Risk Breakdown Structure (RBS)
STEP 1
Start with categories
Take the organisation's standard top-level risk categories — external, technical, organisational, PM.
STEP 2
Decompose one level
Break each into sub-categories: external becomes regulatory, market, competitor, weather.
STEP 3
Decompose again
Continue until the category is specific enough to prompt a concrete risk in a brainstorm.
STEP 4
Use as a checklist
Walk the team down the RBS branch by branch and ask what could go wrong or go unusually well here.
STEP 5
Feed the register
Record each identified risk against its RBS code so you can see which categories dominate.
The RBS also answers a management question the register cannot: which category of risk carries most of our exposure, and is that where our mitigation money is actually going?
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
279

## Slide 280
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Perform Qualitative Risk Analysis — ITTO
Perform the subjective qualitative assessment FIRST to prioritise risks; only escalate to quantitative analysis if further support is required.
INPUTS
Project management plan — risk management plan
Project documents: assumption log, risk register, stakeholder register
EEFs — industry studies of similar projects, published material
OPAs — information from prior similar completed projects
TOOLS & TECHNIQUES
Expert judgment
Data gathering — interviews
Data analysis: risk data quality assessment, risk probability and impact assessment, assessment of other risk parameters (urgency, proximity, dormancy, manageability, controllability)
Interpersonal and team skills — facilitation
Risk categorisation, data representation (probability and impact matrix, hierarchical charts), meetings
OUTPUTS
Project document updates: risk register with priority ratings, risk report, assumption log, issue log
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
280

## Slide 281
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Probability and impact matrix
HIGH P / LOW I
Frequent nuisances. Mitigate through process change or accept actively with a small contingency.
HIGH P / HIGH I
Red zone. Escalate, avoid or transfer. Needs a named owner, a funded response and board visibility.
LOW P / LOW I
Watch list. Record in the register, review periodically, spend nothing on them now.
LOW P / HIGH I
Insurable catastrophes. Transfer, or fund a contingency plan with a defined trigger condition.
IMPACT IF IT OCCURS
PROBABILITY OF OCCURRING
Priority score = probability × impact, using the numeric scales defined in the risk management plan. The matrix converts subjective judgement into a consistent, comparable ranking.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
281

## Slide 282
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Other risk parameters beyond probability and impact
1
Urgency
How soon a response must be implemented for it to be effective — a short period indicates high urgency.
2
Proximity
How soon the risk itself is likely to occur — a short period means the risk is imminent.
3
Dormancy
The period between the risk occurring and the project discovering it — long dormancy is dangerous.
4
Manageability
How easily the risk owner can actually manage the occurrence or impact of the risk.
5
Controllability
The degree to which the organisation is able to control the risk outcome at all.
6
Connectivity
How strongly the risk is linked to other risks — clustered risks fail together.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
282

## Slide 283
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Risk register — the fields that matter
Field | Why it is there
Risk ID and title | A unique persistent reference used in reporting and in every escalation
Category (RBS code) | Lets you analyse where exposure is concentrated rather than only listing items
Risk description | Written as cause → event → effect, so the response can target the cause
Probability and impact | Rated on the scales defined in the risk management plan; produces the priority score
Risk score / priority | The ranking that decides where analysis and money go next
Risk owner | One named person accountable for monitoring and implementing the response — never a team
Planned response | The chosen strategy and the specific actions, with cost and schedule impact
Trigger condition | The observable signal that the risk is materialising and the response should be executed
Residual and secondary risk | What remains after the response, and what the response itself creates
Status | Open, occurred, closed, or retired — with the date
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
283

## Slide 284
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Perform Quantitative Risk Analysis — ITTO
Quantitative analysis is optional and usually reserved for large, complex or high-value projects where the modelling pays for itself.
INPUTS
Project management plan: risk management plan, scope, schedule and cost baselines
Project documents: assumption log, basis of estimates, cost and duration estimates, milestone list, risk register and report, resource requirements, schedule
EEFs and OPAs — industry studies and historical databases
TOOLS & TECHNIQUES
Expert judgment
Data gathering — interviews to quantify probability and impact
Interpersonal and team skills — facilitation
Representations of uncertainty (probability distributions)
Data analysis: simulation (Monte Carlo), sensitivity analysis, decision tree analysis, influence diagrams, EMV
OUTPUTS
Project document updates — risk report with a quantified assessment of overall project risk exposure, probabilistic analysis of the project and a prioritised list of individual risks
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
284

## Slide 285
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Tornado chart — sensitivity analysis
Chart: 
| Regulatory delay | Vendor lead time | Labour rate | Scope volatility | FX movement | Site access
Downside impact on project NPV ($k) | 420 | 310 | 240 | 180 | 120 | 70
WHAT IT TELLS YOU
Sensitivity analysis shows which individual risks have the greatest potential impact on the project outcome.
Bars are sorted longest at the top, producing the tornado shape that gives the chart its name.
Bars show the size of the downside swing in NPV when that one input is varied and all others are held constant.
Management action: fund mitigation for the top two or three bars; the tail rarely justifies the spend.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
285

## Slide 286
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Expected Monetary Value and decision trees
EMV of a risk
EMV = P × I
Probability times impact. Threats are negative, opportunities positive.
EMV of a branch
Σ (P × I) for all outcomes
Sum the expected values of every outcome on that decision branch.
Decision value
Branch EMV − Cost of branch
Choose the path with the best net expected value, not the best best-case.
Worked example
0.3 × (−$200k) = −$60k
A 30% chance of a $200k loss carries $60k of contingency, not $200k.
Decision trees show the decisions and their impacts (costs or benefits) along each path, together with their probabilities, producing an expected monetary value for each branch outcome.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
286

## Slide 287
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Monte Carlo simulation
1
What it does
Runs the schedule or cost model thousands of times, sampling each uncertain input from its distribution.
2
What you supply
Three-point estimates or distributions for the uncertain activities, plus the network logic.
3
What you get
An S-curve of possible outcomes with a confidence level attached to every date or cost.
4
The P-values
P50 is the median outcome; P80 is the value you have an 80% chance of meeting — commit to P80, not P50.
5
Criticality index
How often each activity lands on the critical path across all runs — a better target list than one static CPM.
6
The limitation
Output quality is bounded by input quality; precise-looking numbers from guessed inputs are still guesses.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
287

## Slide 288
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Plan Risk Responses — ITTO
Every response must be timely, cost-effective, agreed by all parties and owned by one named person.
INPUTS
Project management plan: resource, risk and cost management plans, and the cost baseline
Project documents: lessons learned register, project schedule, project team assignments, resource calendars, risk register, risk report, stakeholder register
EEFs — risk appetite and thresholds; OPAs — historical responses
TOOLS & TECHNIQUES
Expert judgment
Data gathering — interviews
Interpersonal and team skills — facilitation
Strategies for threats, opportunities and overall project risk
Contingent response strategies
Data analysis: alternatives analysis, cost-benefit analysis
Decision making — multi-criteria decision analysis
OUTPUTS
Change requests
Project management plan updates: schedule, cost, quality, resource, procurement plans, scope/schedule/cost baselines
Project document updates: risk register, risk report, assumption log, lessons learned register, project schedule
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
288

## Slide 289
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Threat response strategies
Strategy | What it means | Example
Escalate | The threat is outside the project's scope or authority; hand it to the programme or portfolio level | A regulatory change affecting the whole business unit
Avoid | Eliminate the threat entirely by removing its cause or changing the plan | Drop the risky feature, or change to proven technology
Transfer | Shift the impact and ownership of the threat to a third party — the threat still exists | Insurance, warranties, performance bonds, fixed-price contracts
Mitigate | Reduce the probability or impact of the threat to an acceptable level | Prototype early, add redundancy, run more tests
Accept | Acknowledge the threat and take no proactive action. ACTIVE acceptance funds a contingency reserve; PASSIVE does nothing but document it | Minor weather delay risk with a small time buffer
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
289

## Slide 290
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Opportunity response strategies
Strategy | What it means | Example
Escalate | The opportunity is outside the project's authority to pursue; raise it to programme or portfolio | A reusable component that benefits the entire portfolio
Exploit | Ensure the opportunity definitely happens — remove all uncertainty from it | Assign your best people to guarantee an early finish that unlocks a bonus
Share | Allocate ownership to a third party best able to capture the benefit | Joint venture, partnership, risk-sharing consortium
Enhance | Increase the probability or the positive impact of the opportunity | Add resource to a task whose early finish would pull in the whole schedule
Accept | Take advantage of it if it arises but do not actively pursue it | Note a possible favourable exchange rate movement, take no action
Mirror pairs: Avoid ↔ Exploit, Transfer ↔ Share, Mitigate ↔ Enhance, and Escalate and Accept appear on both sides. Learning them as pairs halves the memorisation.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
290

## Slide 291
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Secondary risk, residual risk and contingency plans
1
Trigger condition
The observable signal that a risk is about to develop — the cue for the team to implement the response.
2
Secondary risk
A new risk that arises as a direct result of implementing a risk response — always re-assess after responding.
3
Residual risk
The risk that remains after responses have been implemented; it is accepted knowingly and stays in the register.
4
Contingency plan
The prepared response executed if the risk occurs, funded from the contingency reserve.
5
Fallback plan
The backup executed if the contingency plan itself proves inadequate — plan B for plan B.
6
Risk owner
One named individual accountable for watching the trigger and executing the response — never a committee.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
291

## Slide 292
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
ECO 2026 emphasis — AI-assisted risk detection
1
Pattern detection
AI can scan issue logs, commit history and supplier data to surface risk signals a human would not spot.
2
Estimation support
Models trained on historical project data produce range estimates and challenge optimistic single points.
3
Register hygiene
Language models can cluster duplicate risks and rewrite vague entries as cause–event–effect statements.
4
Early warning
Sentiment and cadence signals from team communication can flag emerging delivery risk earlier than reports.
5
Human accountability
The risk owner remains a named human; AI output is an input to judgement, never the decision itself.
6
New risk category
AI use introduces its own risks: data privacy, hallucinated output, model bias and vendor dependency.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
292

## Slide 293
EXAM FOCUS
Exam focus — risk
IF THE QUESTION SAYS
A risk has occurred and is now affecting the project
THE BEST ANSWER IS
It is an issue: implement the planned response, record it in the issue log and update the risk register
IF THE QUESTION SAYS
You buy insurance against a possible loss
THE BEST ANSWER IS
That is transfer, not mitigate — the risk still exists, only the impact ownership moved
IF THE QUESTION SAYS
You cancel the risky component of the scope entirely
THE BEST ANSWER IS
That is avoid — the only strategy that removes the risk rather than reducing or moving it
IF THE QUESTION SAYS
A new risk appears because of the response you implemented
THE BEST ANSWER IS
That is a secondary risk; add it to the register and analyse it like any other
IF THE QUESTION SAYS
The question asks what remains after you respond
THE BEST ANSWER IS
Residual risk — knowingly accepted and still tracked in the register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
293

## Slide 294
RECAP
Recap — risk planning
1
Five planning processes
Plan Risk Management, Identify, Qualitative, Quantitative, Plan Responses — in that order.
2
Definitions come first
The risk management plan sets the probability and impact scales everything else uses.
3
Qualitative before quantitative
Prioritise subjectively first; model numerically only where it pays for itself.
4
Ten strategies
Five for threats and five for opportunities, learned as mirror pairs.
5
Register discipline
Cause–event–effect wording, one named owner, a trigger condition and a status on every row.
6
Never finished
Identification is iterative; the register is reviewed at every status cycle for the life of the project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
294

## Slide 295
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Knowledge area 8 of 8 in the planning block
Procurement: what you buy, and who carries the risk
Make or buy
The first decision is whether the work should be done internally at all.
Agreement vs contract
You can have an agreement without a contract, but you cannot have a contract without an agreement.
Risk allocation
Contract type is not an administrative detail — it decides who absorbs cost overrun.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
295

## Slide 296
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Plan Procurement Management — ITTO
Procurement planning decides what to buy, how to buy it, how much to buy and when — before any seller is contacted.
INPUTS
Project charter and business documents (business case, benefits plan)
Project management plan: scope, quality, resource management plans and the scope baseline
Project documents: milestone list, project team assignments, requirements documentation, RTM, resource requirements, risk register, stakeholder register
EEFs — marketplace conditions, legal jurisdiction, contract management systems; OPAs — pre-qualified seller lists, policies
TOOLS & TECHNIQUES
Expert judgment on contracting and the relevant market
Data gathering — market research
Data analysis — make-or-buy analysis
Source selection analysis (least cost, qualifications only, quality-based, quality and cost-based, sole source, fixed budget)
Meetings with prospective sellers and internal stakeholders
OUTPUTS
Procurement management plan and procurement strategy
Bid documents (RFI, RFP, RFQ, IFB) and procurement SOW
Source selection criteria, make-or-buy decisions
Independent cost estimates, change requests, document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
296

## Slide 297
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Procurement strategy fundamentals
1
What procurement covers
Any resource external to your company — a vendor, contractors, consultants or any other outside resource.
2
Agreement without contract
The project charter can agree the use of internal resources without any contract existing.
3
Contract needs agreement
You cannot have a contract without an underlying agreement between the parties.
4
Delivery method
Decide turnkey, design-build, design-bid-build or staff augmentation before writing the bid documents.
5
Payment approach
Choose the contract payment type that matches how well the scope is actually defined.
6
Procurement phases
Sequence the procurement across the life cycle so long-lead items are ordered early enough to arrive.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
297

## Slide 298
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
The procurement process end to end
STEP 1
Plan
Make-or-buy analysis, procurement strategy, bid documents, procurement SOW and source selection criteria.
STEP 2
Advertise
Advertise in specialty trade publications or websites to invite more bids and grow the pre-qualified seller list.
STEP 3
Bidder conference
Meet all prospective sellers together before bidding so every seller has the same information.
STEP 4
Evaluate and select
Score proposals against the published source selection criteria; negotiate the agreement.
STEP 5
Administer and close
Manage seller performance against the contract, then close the procurement formally.
Bidder conferences (also vendor or pre-bid conferences) exist to ensure no seller receives preferential treatment — every question and answer is shared with all prospective sellers.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
298

## Slide 299
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Bid documents — pick the right instrument
Document | Use it when | What you get back
Request for Information (RFI) | You need more information about what sellers can provide before you can even specify | Capability statements that shape your requirements
Request for Proposal (RFP) | There is a problem and the solution is not obvious — you need someone to propose an approach | Technical solutions with methodology, team and price
Request for Quote (RFQ) | You know exactly what you need and just require the cost from the seller | Prices for a clearly specified item or service
Invitation for Bid (IFB) | A well-defined scope where price is the deciding factor, often in public sector | Sealed price bids against an identical specification
The rule of thumb: RFI when you do not know what to ask for, RFP when you know the problem but not the solution, RFQ/IFB when you know exactly what you want and only need a number.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
299

## Slide 300
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Why contracts exist, and what they must contain
1
Legalise agreements
A contract turns a working understanding into a legally enforceable obligation for both parties.
2
Structure relationships
Defines who does what, by when, to what standard, and what happens when that fails.
3
Description of work
The deliverables and scope, usually via an attached procurement statement of work.
4
Schedule and delivery
Delivery dates, milestones, and the schedule information both parties are bound to.
5
Authority and responsibility
Identification of authority where appropriate, and the responsibilities of both parties.
6
Price and payment terms
The amount, the milestones that trigger payment, and the invoicing and approval route.
7
Termination and disputes
Provisions for termination, alternative dispute resolution and governing jurisdiction.
8
Change and management
How technical and business aspects are managed, including how contract changes are agreed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
300

## Slide 301
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Contract types and who carries the cost risk
Type | How it works | Risk sits with
Firm Fixed Price (FFP) | One price for a well-defined scope, regardless of the seller's actual cost | SELLER — the most common and simplest fixed-price form
Fixed Price Incentive Fee (FPIF) | Fixed price plus an incentive for meeting agreed cost or performance targets | Mostly seller, shared above the target through a share ratio
Fixed Price with Economic Price Adjustment (FP-EPA) | Fixed price with a defined adjustment for inflation or currency | Seller, with defined external exposure shared — for multi-year deals
Cost Plus Fixed Fee (CPFF) | Actual allowable costs reimbursed plus a fixed fee that does not vary with cost | BUYER — the seller has no incentive to control cost
Cost Plus Incentive Fee (CPIF) | Costs reimbursed plus a fee that varies with performance against targets | Buyer, partially shared through the incentive formula
Cost Plus Award Fee (CPAF) | Costs reimbursed plus an award fee at the buyer's subjective judgement | Buyer; award is usually not subject to appeal
Time and Materials (T&M) | Hourly or daily rates plus materials; a hybrid of fixed unit price and cost reimbursable | Buyer — cap it with a not-to-exceed clause
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
301

## Slide 302
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Fixed price versus cost reimbursable — when to choose
FIXED PRICE
Choose when the scope is well defined
Requirements are clear, stable and fully specified
The seller carries the cost risk and prices it in
Buyer's cost is predictable from the day of signature
Change is expensive: every variation is a renegotiation
Sellers may cut corners if their margin disappears
COST REIMBURSABLE
Choose when the scope is uncertain
Requirements are expected to evolve, or the work is R&D
The buyer carries the cost risk and must actively monitor it
Buyer's final cost is unknown until the work is complete
Change is cheap and flexible to accommodate
Requires strong buyer-side cost control and audit rights
Time and materials sits between the two: use it for small amounts of work, staff augmentation, or when you need to start before the scope can be written — always with a ceiling.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
302

## Slide 303
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Make-or-buy analysis and vendor qualification
1
Make-or-buy analysis
Compare the total cost, capability, capacity and risk of doing the work internally versus procuring it.
2
Beyond price
Consider strategic capability retention, intellectual property and long-term supportability, not just cost.
3
Independent estimate
Produce your own cost estimate before you see any bid, so you can judge whether a bid is realistic.
4
Qualified vendors
Pre-approved by the organisation, with a history of work and accounts already set up.
5
Preferred vendors
Often preferred precisely because they are proven — the procurement cycle is shorter and less risky.
6
Source selection criteria
Published in advance and applied consistently: capability, capacity, price, references, risk.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
303

## Slide 304
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
ECO 2026 emphasis — sustainable procurement
1
Sustainability criteria
Environmental and social performance sit in the source selection criteria alongside price and capability.
2
Supply chain due diligence
Assess labour practice, provenance and modern slavery exposure across the seller's own supply chain.
3
Whole-life cost
Evaluate energy, maintenance and disposal cost over the asset life, not just the purchase price.
4
Contractual commitments
Write sustainability obligations and reporting duties into the contract, with measurable targets.
5
Local and inclusive sourcing
Many jurisdictions now weight local content and supplier diversity in public procurement.
6
Reporting obligation
Sustainability disclosure is increasingly a regulatory requirement flowing down to project suppliers.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
304

## Slide 305
EXAM FOCUS
Exam focus — procurement
IF THE QUESTION SAYS
The scope is unclear and likely to change
THE BEST ANSWER IS
Choose a cost-reimbursable or T&M contract; a fixed price forces renegotiation on every variation
IF THE QUESTION SAYS
The buyer wants maximum cost certainty
THE BEST ANSWER IS
Firm Fixed Price — the seller carries the cost risk entirely
IF THE QUESTION SAYS
All prospective sellers must receive the same information
THE BEST ANSWER IS
Hold a bidder conference; share every question and answer with all sellers
IF THE QUESTION SAYS
You need to know what solutions exist before specifying
THE BEST ANSWER IS
Issue an RFI — an RFP presumes you can already state the problem
IF THE QUESTION SAYS
A T&M contract is running over budget
THE BEST ANSWER IS
T&M should carry a not-to-exceed ceiling; the buyer holds the cost risk and must monitor actively
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
305

## Slide 306
RECAP
Recap — procurement planning
1
Make or buy first
Decide internally versus externally on total cost, capability, capacity and risk — not price alone.
2
Strategy then documents
The procurement strategy sets delivery method and payment type before bid documents are written.
3
Right instrument
RFI to learn, RFP to solve, RFQ and IFB to price a known specification.
4
Contract type allocates risk
Fixed price puts cost risk on the seller; cost reimbursable puts it on the buyer.
5
Fair process
Bidder conferences and published source selection criteria keep the process defensible.
6
Sustainability counts
ECO 2026 expects environmental and social criteria in selection and in the contract itself.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
306

## Slide 307
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Bringing the eight plans back together
The integrated plan is a system, not a folder
Dependencies
Assess the consolidated plans for dependencies, gaps and continued business value before you baseline anything.
Consistency
The schedule, budget and resource plan must all describe the same project or none of them is true.
Maintenance
The integrated plan is maintained throughout, not written once and archived.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
307

## Slide 308
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
The planning sequence at a glance
1
Integrate
Establish the plan, the development approach and the engagement strategy.
2
Scope
Collect requirements, define scope, build the WBS, baseline it.
3
Schedule
Define, sequence, estimate, analyse the network, baseline it.
4
Cost
Estimate costs, aggregate to the budget, set reserves, baseline it.
5
Quality & resources
Set standards and metrics; plan people and physical resources.
6
Comms, risk, procurement
Plan communication, risk responses and what will be bought.
The order matters because the outputs cascade: you cannot estimate a duration without a work package, or a budget without a duration and a resource. Late scope change ripples through all of it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
308

## Slide 309
RECAP
Topic 3 recap — plan the project
1
Integration
The project management plan reconciles all subsidiary plans and the three baselines into one coherent system.
2
Scope
Requirements, RTM, scope statement, WBS and WBS dictionary define and defend what will be delivered.
3
Schedule
Activities, dependencies, durations and network analysis produce a calculated, defensible date.
4
Cost
Estimating methods and reserve strategy produce a time-phased cost baseline plus management reserve.
5
Quality
Standards, metrics, cost of quality and improvement cycles build quality in instead of inspecting it in.
6
Resources
Roles, authority, responsibility, competency, RACI, levelling and smoothing make the plan executable.
7
Communication
A planned strategy with channels, methods, cadence and a feedback loop for every stakeholder.
8
Risk & procurement
Ten response strategies, a disciplined register, and contract types that allocate risk deliberately.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
309

## Slide 310
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Where Topic 3 leads next
A plan is only a hypothesis until it meets reality
Topic 4 — lead
Take the resource and communication plans into practice: leadership style, motivation, conflict and coaching.
Topic 5 — control
Measure actuals against these baselines with earned value, quality control and integrated change control.
Topic 6 — close
Confirm the acceptance criteria written here were actually met, and harvest the lessons.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
310

## Slide 311
WHAT YOU WILL BUILD
Hands-on Labs — Topic 3
1
Lab 09. Requirements Elicitation and Traceability Matrix
Process T2 · LO1 · 30 min in class + 20 min self-study
Produces: Requirements list, RTM
2
Lab 10. MoSCoW and Kano Prioritisation with Product Backlog
Process T3 · LO1 · 30 min in class + 20 min self-study
Produces: Prioritised backlog, Story point estimates
3
Lab 11. Work Breakdown Structure and WBS Dictionary
Process T2 · LO1 · 30 min in class + 20 min self-study
Produces: WBS, WBS dictionary, Scope baseline
4
Lab 12. Network Diagram, PERT Estimating and Critical Path
Process T8 · LO2 · 35 min in class + 25 min self-study
Produces: Network diagram, Critical path, Float table
5
Lab 13. Cost Estimating, Budget and Reserve Analysis
Process T6 · LO2 · 25 min in class + 25 min self-study
Produces: Cost estimates, Cost baseline, Reserve plan
6
Lab 14. Risk Register, Probability/Impact Matrix and EMV Decision Tree
BE T5 · LO4 · 30 min in class + 30 min self-study
Produces: Risk register, P/I matrix, EMV decision tree
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
311

## Slide 312
HANDS-ON ACTIVITY
Lab 09. Requirements Elicitation and Traceability Matrix
Case study: Contoso Training Portal Upgrade. Process T2 · LO1. Produces Requirements list, RTM.
30 min in class
1
Run a requirements elicitation session using the Mind Mapping tool, branching from the portal's core capabilities.
2
Convert each branch into a numbered requirement written as a testable statement, not a wish.
3
Classify each requirement as functional, non-functional, business, stakeholder, transition or quality.
4
Build the Requirements Traceability Matrix linking requirement to business need, deliverable, test and acceptance criterion.
5
Identify gaps: requirements with no test, and deliverables with no originating requirement.
6
Have a nominated 'business owner' review and sign off the matrix.
DELIVERABLE
Requirements list, RTM
TOOL
Mind Mapping
alfredang.github.io/mindmapping/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
312

## Slide 313
HANDS-ON ACTIVITY
Lab 10. MoSCoW and Kano Prioritisation with Product Backlog
Case study: Contoso Training Portal Upgrade. Process T3 · LO1. Produces Prioritised backlog, Story point estimates.
30 min in class
1
Take the requirements from Lab 09 and apply MoSCoW: Must, Should, Could, Won't have this release.
2
Challenge the Musts — if more than 60% of effort is Must, the prioritisation has failed and must be redone.
3
Apply Kano classification: basic, performance and delight features, and note which Musts are merely basic expectations.
4
Write the top fifteen items as user stories in the standard 'As a… I want… so that…' form with acceptance criteria.
5
Estimate each story in story points using relative sizing against a chosen reference story.
6
Order the backlog by value per point and confirm the first sprint's capacity is realistic.
DELIVERABLE
Prioritised backlog, Story point estimates
TOOL
Scrum Simulator
alfredang.github.io/scrum/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
313

## Slide 314
HANDS-ON ACTIVITY
Lab 11. Work Breakdown Structure and WBS Dictionary
Case study: Contoso Training Portal Upgrade. Process T2 · LO1. Produces WBS, WBS dictionary, Scope baseline.
30 min in class
1
Decompose the portal scope into major deliverables — not activities — at WBS level 2.
2
Break each deliverable down until every work package is estimable and assignable, typically 8-80 hours.
3
Apply the 100% rule: verify the children of every parent sum to exactly the parent's scope, no more and no less.
4
Assign a unique WBS code identifier to every element.
5
Write the WBS dictionary entry for five work packages: description, resources, cost, quality requirements and acceptance criteria.
6
Assemble the scope baseline — scope statement plus WBS plus dictionary — and record who approves it.
DELIVERABLE
WBS, WBS dictionary, Scope baseline
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
314

## Slide 315
HANDS-ON ACTIVITY
Lab 12. Network Diagram, PERT Estimating and Critical Path
Case study: Contoso Training Portal Upgrade. Process T8 · LO2. Produces Network diagram, Critical path, Float table.
35 min in class
1
List the activities derived from the Lab 11 work packages with their durations.
2
Determine each dependency and classify it as mandatory, discretionary, external or internal.
3
Draw the precedence network using finish-to-start relationships, adding leads and lags where genuinely required.
4
Apply three-point PERT estimating to the five most uncertain activities: (O + 4M + P) / 6, with sigma = (P − O) / 6.
5
Run the forward and backward pass to compute early and late start and finish for every activity.
6
Identify the critical path, state the project duration, and list the total and free float for every non-critical activity.
DELIVERABLE
Network diagram, Critical path, Float table
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
315

## Slide 316
HANDS-ON ACTIVITY
Lab 13. Cost Estimating, Budget and Reserve Analysis
Case study: Contoso Training Portal Upgrade. Process T6 · LO2. Produces Cost estimates, Cost baseline, Reserve plan.
25 min in class
1
Estimate each work package by the most defensible method — analogous, parametric or bottom-up — and record which you used and why.
2
Apply three-point estimating to the packages with the widest uncertainty.
3
Roll the estimates up through the WBS to a total direct cost.
4
Calculate contingency reserve from the Lab 14 risk EMVs and add it to form the cost baseline.
5
Add management reserve above the baseline and state who must approve its release.
6
Plot the cumulative spend as an S-curve and identify the periods of highest cash demand.
DELIVERABLE
Cost estimates, Cost baseline, Reserve plan
TOOL
Statistics
alfredang.github.io/novastats/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
316

## Slide 317
HANDS-ON ACTIVITY
Lab 14. Risk Register, Probability/Impact Matrix and EMV Decision Tree
Case study: Contoso Training Portal Upgrade. BE T5 · LO4. Produces Risk register, P/I matrix, EMV decision tree.
30 min in class
1
Build a risk breakdown structure grouping risks into technical, external, organisational and project-management categories.
2
Identify at least fifteen risks, writing each in cause-event-effect form so the response is targetable.
3
Score probability and impact on 1-5 scales and plot every risk on the probability/impact matrix.
4
Use the System Thinking tool to map the reinforcing loops behind your top three risks — most schedule risk is systemic, not incidental.
5
Build an EMV decision tree for the highest-value decision and calculate the expected monetary value of each branch.
6
Assign a response strategy and a named owner to every red and amber risk, then note the secondary risks your responses create.
DELIVERABLE
Risk register, P/I matrix, EMV decision tree
TOOL
System Thinking
alfredang.github.io/systemloop/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
317

## Slide 318
04
TOPIC
Lead the Project Team
The People domain in practice. Execution is where the plan meets human beings — this topic covers how you direct the work, grow the team, resolve conflict and communicate so the plan actually lands.
1
Direct and manage project work, artifacts and knowledge
2
Develop the team: Tuckman, motivation and team-building
3
Craft your leadership style and emotional intelligence
4
Train, coach and mentor to close capability gaps
5
Manage conflict, decisions and negotiation
6
Plan and manage communication across a distributed team
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
318

## Slide 319
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Why this topic carries the most exam weight
Plans do not deliver projects. People do.
33% of the exam
The People domain is the single largest cluster of ECO tasks and is tested across every question type.
Situational questions
Most People items are scenario-based: you pick the PM's next action, not a definition.
Servant-leader default
PMI expects you to facilitate, coach and empower before you ever direct or escalate.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
319

## Slide 320
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
What 'leading the project team' actually means
1
Set expectations
Agree what good looks like at team level — quality bars, response times, definition of done, escalation rules.
2
Empower decisions
Push authority to the level closest to the work so the team decides without waiting on the project manager.
3
Solve problems
Break impediments down to root cause, then remove them or escalate with a recommended option, never just a complaint.
4
Represent the voice of the team
Carry the team's constraints, capacity and concerns upward to sponsors honestly and without filter.
5
Support varied experience
Deliberately use the differing skills, cultures and perspectives on the team as a design advantage.
6
Clarify roles
Every work package has one accountable owner; ambiguity about ownership is the number-one source of team conflict.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
320

## Slide 321
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Direct and Manage Project Work
Executing process: lead and perform the work defined in the plan and implement approved changes to achieve the objectives.
INPUTS
Project management plan (all components)
Project documents: change log, lessons learned register, milestone list, project communications
Approved change requests
Enterprise environmental factors
Organizational process assets
TOOLS & TECHNIQUES
Expert judgment
Project management information system (PMIS)
Meetings: kick-off, stand-up, status review
Interpersonal and team skills
Data and decision-making techniques
OUTPUTS
Deliverables
Work performance data
Issue log
Change requests
Project management plan updates
Project document updates and OPA updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
321

## Slide 322
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Data becomes information becomes reports
STEP 1
Work performance data
Raw observations from the work: actual cost, defect counts, hours logged, change requests raised.
STEP 2
Work performance information
Data compared against baselines or each other — schedule variance, CPI, % of packages complete.
STEP 3
Work performance reports
Physical or electronic packaging of that information — dashboards, status reports, briefings.
STEP 4
Decisions and action
Reports raise awareness, generate decisions and trigger change requests or corrective action.
Exam cue: data is produced by Direct and Manage Project Work; information by the Control processes; reports by Monitor and Control Project Work. The verb in the stem tells you which.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
322

## Slide 323
EXAM FOCUS
Data, information or report?
IF THE QUESTION SAYS
'The team logs 14 defects this sprint' — what is this?
THE BEST ANSWER IS
Work performance data. Raw, unprocessed measurement straight from the work itself.
IF THE QUESTION SAYS
'Defect rate is 40% above the baseline' — what is this?
THE BEST ANSWER IS
Work performance information. Data has been compared to a baseline and now carries meaning.
IF THE QUESTION SAYS
'The sponsor asks for the monthly status pack' — what is this?
THE BEST ANSWER IS
A work performance report — the communication artifact built from work performance information.
IF THE QUESTION SAYS
Question asks where deliverables are produced
THE BEST ANSWER IS
Direct and Manage Project Work. Deliverables are its primary output; verified deliverables come later from Control Quality.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
323

## Slide 324
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Standardise your project artifacts
1
Simple production route
One agreed way to create a document so the team spends effort on content rather than on formatting.
2
Templates and formats
Standard formats for status reports, change requests and minutes make information comparable across periods.
3
Review and approval
A defined path for who drafts, who reviews and who signs off before an artifact becomes authoritative.
4
Version control
Every artifact carries a version number so people can tell instantly whether they hold the current truth.
5
Security and access
Classify artifacts and restrict who can edit versus who can only read, especially for contracts and HR data.
6
Timely distribution
An artifact that arrives after the decision has been taken has zero value regardless of its quality.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
324

## Slide 325
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Configuration management plan vs configuration management system
Configuration management plan
A component of the project management plan
States which items are placed under configuration control
Defines how project and product information is recorded
Says who may request, review and approve a configuration change
Facilitates consistency of the product, service or result
Written during planning; maintained across the whole life cycle
Configuration management system
The tooling and procedures that enforce the plan
How the PM tracks project artifacts day to day
Monitors and controls changes to baselined items
Holds the audit trail of what changed, when and by whom
Usually a subsystem of the wider PMIS
Includes document control and version control mechanisms
Configuration management controls the PRODUCT; change control controls the PLAN. Exam items often test that distinction directly.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
325

## Slide 326
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Version control and document control in practice
1
A subset of configuration management
Document control is the part of configuration management dealing with documents and digital records.
2
New version number
Increment on every substantive change so two people can confirm they are debating the same content.
3
Date and time stamp
Establishes sequence when several edits land on the same working day from different contributors.
4
Author of the change
Names the person accountable, which makes it possible to go back and ask why a change was made.
5
Change summary line
One sentence describing what moved lets a reader decide whether they need to re-read the whole document.
6
Single source of truth
Only one location is authoritative; all other copies are explicitly labelled as reference copies.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
326

## Slide 327
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Work information management systems
Project Management Information System (PMIS)
Gathers, integrates and shares project data
Automated collection of schedule, cost and resource data
Ensures consistency in how data is collected and reported
Feeds dashboards, earned value and status reporting
Includes scheduling tools, work authorisation and configuration systems
An input to almost every executing and controlling process
Artifact management systems
Store and maintain the project's documents
Repository for plans, registers, logs and specifications
Enforces access rights, retention and version history
Makes artifacts findable — accessibility is an ECO enabler
Supports handover of records at project or phase closure
Continually assessed for effectiveness, per ECO Process T9
ECO Process T9 asks you to 'continually assess the effectiveness of artifact management' — a new emphasis in the 2026 outline.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
327

## Slide 328
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Manage Project Knowledge
Use existing knowledge and create new knowledge to achieve the project's objectives and contribute to organisational learning.
INPUTS
Project management plan (all components)
Project documents: lessons learned register, project team assignments, resource breakdown structure, stakeholder register
Deliverables
Enterprise environmental factors
Organizational process assets
TOOLS & TECHNIQUES
Expert judgment
Knowledge management (networking, communities of practice, work shadowing, seminars, storytelling)
Information management (lessons learned register, library services, information gathering)
Interpersonal and team skills: active listening, facilitation, leadership, networking, political awareness
OUTPUTS
Lessons learned register
Project management plan updates
Organizational process assets updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
328

## Slide 329
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Explicit vs tacit knowledge
Explicit knowledge
Codified — it can be written down and sent
Facts, numbers, procedures, diagrams, templates
Easily stored in a repository and searched later
Transferred by documents, training material and databases
Risk: people assume that documenting equals transferring
Managed mainly through information management techniques
Tacit knowledge
Personal — beliefs, insight, experience, know-how
Judgement, context, 'why we did it that way', relationships
Hard to articulate; often the person does not know they hold it
Transferred by conversation, shadowing, pairing and storytelling
Lost permanently when a key person leaves without handover
Managed mainly through knowledge management techniques
The hardest part of knowledge management is creating an atmosphere of trust so people are willing to share the tacit knowledge that makes them individually valuable.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
329

## Slide 330
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Information radiators
1
Big visible charts
Large, low-tech displays placed where the team works so status is absorbed passively rather than requested.
2
Task or Kanban board
Shows every work item and its state; makes work-in-progress and bottlenecks obvious without a status meeting.
3
Burndown / burnup chart
Plots remaining or completed work against time so the team sees its own trend against the commitment.
4
Impediment board
Lists blockers, owner and age — an ageing blocker on a public wall creates the pressure to resolve it.
5
Team calendar and capacity
Absences, holidays and shared commitments visible so the team plans realistically together.
6
Radiate, don't report
Radiators push information out continuously; reports pull it out periodically and are always slightly stale.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
330

## Slide 331
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
The lessons learned register
1
Created early, not at the end
Opened during Manage Project Knowledge in the first phase and updated throughout execution.
2
What it records
The situation, what was done, the impact, and the recommendation for anyone facing that situation again.
3
Categories
Lessons on requirements, estimating, risk, procurement, communication, quality and team dynamics.
4
Feeds later phases
A live register lets the current project fix itself, not just help the next project.
5
Becomes the repository
At closure the register is folded into the organisational lessons learned repository, an OPA.
6
Retrospectives supply it
In adaptive work every iteration retrospective is a scheduled input to the register.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
331

## Slide 332
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Foster a knowledge-sharing culture
1
Everyone teaches and learns
Knowledge transfer is not a one-way flow from senior to junior; every role holds transferable know-how.
2
Include stakeholders and customers
Suppliers, users and operations staff hold context the delivery team cannot generate on its own.
3
Dedicated sharing roles
Agile coaches and Scrum Masters exist partly to make knowledge move across team boundaries.
4
Essential at transition
Product handover to operations fails when only explicit knowledge crosses and tacit knowledge does not.
5
Communities of practice
Cross-project guilds keep specialists connected so a solution found once is not re-invented.
6
Psychological safety first
People share what went wrong only when they are confident the disclosure will not be used against them.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
332

## Slide 333
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Manage Stakeholder Engagement
Communicate and work with stakeholders to meet their needs, address issues and foster appropriate engagement.
INPUTS
Project management plan: communications, stakeholder engagement, risk and change management plans
Project documents: change log, issue log, lessons learned register, stakeholder register
Enterprise environmental factors
Organizational process assets
TOOLS & TECHNIQUES
Expert judgment
Communication skills: feedback
Interpersonal and team skills: conflict management, cultural awareness, negotiation, observation/conversation, political awareness
Ground rules
Meetings
OUTPUTS
Change requests
Project management plan updates
Project document updates: change log, issue log, lessons learned register, stakeholder register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
333

## Slide 334
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Manage Quality
Translate the quality management plan into executable quality activities — this is quality ASSURANCE, about the process.
INPUTS
Project management plan: quality management plan
Project documents: lessons learned register, quality control measurements, quality metrics, risk report
Organizational process assets
TOOLS & TECHNIQUES
Data gathering: checklists
Data analysis: alternatives analysis, document analysis, process analysis, root cause analysis
Decision making: multicriteria decision analysis
Data representation: affinity diagrams, cause-and-effect diagrams, flowcharts, histograms, matrix diagrams, scatter diagrams
Audits, design for X, problem solving, quality improvement methods
OUTPUTS
Quality reports
Test and evaluation documents
Change requests
Project management plan updates
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
334

## Slide 335
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Manage Quality vs Control Quality
Manage Quality (Executing)
Are we using the right process?
Quality assurance — audits the process, not the product
Outputs quality reports and test/evaluation documents
Uses process analysis and root cause analysis
Drives continuous improvement of how work is done
Owned by the PM, quality department and often the whole team
Control Quality (Monitoring & Controlling)
Did we build the right thing correctly?
Inspects deliverables against acceptance criteria
Outputs quality control measurements and verified deliverables
Uses inspection, testing, control charts and checksheets
Determines correctness of the output, one deliverable at a time
Feeds verified deliverables into Validate Scope for acceptance
Mnemonic: Manage Quality is about the PROCESS and prevention; Control Quality is about the PRODUCT and inspection.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
335

## Slide 336
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Acquire Resources
Obtain team members, facilities, equipment, materials and supplies necessary to complete the project work.
INPUTS
Project management plan: resource management plan, procurement management plan, cost baseline
Project documents: project schedule, resource calendars, resource requirements, stakeholder register
Enterprise environmental factors
Organizational process assets
TOOLS & TECHNIQUES
Decision making: multicriteria decision analysis
Interpersonal and team skills: negotiation
Pre-assignment
Virtual teams
OUTPUTS
Physical resource assignments
Project team assignments
Resource calendars
Change requests
Project management plan updates
Project document updates and EEF/OPA updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
336

## Slide 337
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Four ways you obtain project resources
Route | How it works | When to use it | Watch out for
Pre-assignment | People are named in the charter or promised in the proposal | Competitive bids won on named experts; unique specialists | The named person may no longer be available when you start
Negotiation | You bargain with functional managers, other PMs or the PMO | Matrix organisations where resources are shared | You win only what your influence and the project's priority allow
Acquisition | Hire externally or contract in the skill from a supplier | The skill genuinely does not exist inside the organisation | Cost, lead time, onboarding and knowledge leaving at contract end
Virtual teams | People contribute from different locations or time zones | Scarce skills, remote workers, cost or mobility constraints | Isolation, communication lag, weaker informal knowledge flow
If the question describes a resource you cannot get, negotiate first, then escalate to the sponsor — do not simply re-plan the schedule around the gap.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
337

## Slide 338
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Develop Team
Improve competencies, team member interaction and the overall team environment to enhance project performance.
INPUTS
Project management plan: resource management plan
Project documents: lessons learned register, project schedule, project team assignments, resource calendars, team charter
Enterprise environmental factors
Organizational process assets
TOOLS & TECHNIQUES
Colocation
Virtual teams and communication technology
Interpersonal and team skills: conflict management, influencing, motivation, negotiation, team building
Recognition and rewards
Training, individual and team assessments, meetings
OUTPUTS
Team performance assessments
Change requests
Project management plan updates
Project document updates
Enterprise environmental factors updates
Organizational process assets updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
338

## Slide 339
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Develop Team in one line
An effective team is the deliverable behind every deliverable.
Cohesion
Solidarity and mutual reliance measurably raise throughput and lower defect rates.
Bonding needs leadership
Teams do not gel by accident; the leader engineers the conditions that let it happen.
Team over individual
Team-building shifts identity from 'my task is done' to 'our increment is done'.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
339

## Slide 340
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Team-building activities
1
Formal
Facilitated offsites, chartering workshops and structured team assessments with a defined agenda and outcome.
2
Informal
Five minutes at stand-up, shared meals, coffee walks — low-cost, high-frequency contact that builds trust.
3
Brief
A short check-in ritual or icebreaker at the start of every meeting keeps connection alive between bigger events.
4
Extended
Multi-day workshops used at project start or after a major team change to reset norms and relationships.
5
Self-facilitated
The PM runs it — cheap and fast, but the PM cannot both facilitate and participate honestly.
6
Professionally facilitated
Neutral facilitator needed when the PM is part of the problem or the conflict level is high.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
340

## Slide 341
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Tuckman's ladder of team development
1
Forming
Members meet, are polite and still behave as individuals; they look to the leader for direction.
2
Storming
Personalities, working styles and role expectations collide; productivity dips and conflict surfaces.
3
Norming
The team agrees norms, learns each other's roles and settles into a working rhythm.
4
Performing
High trust and interdependence; the team self-organises and solves problems without the PM.
5
Adjourning
Work completes, resources release; the team needs closure, recognition and knowledge handover.
Teams can regress: a new member, a change of scope or a change of PM can drop a performing team back into storming.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
341

## Slide 342
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
What the project manager does at each Tuckman stage
Stage | What the team looks like | Your leadership move
Forming | Polite, cautious, dependent, unclear on roles | Be DIRECTIVE — set purpose, roles, ground rules and the team charter
Storming | Disagreement on approach, resistance, low morale | COACH — surface conflict, facilitate, do not suppress the debate
Norming | Norms accepted, trust building, rhythm forming | SUPPORT — let them own decisions, reinforce the norms they set
Performing | Interdependent, self-correcting, high output | DELEGATE — remove impediments, protect the team, stay out of the way
Adjourning | Anxiety about what is next, energy drops | CLOSE — recognise contribution, capture lessons, plan the transition
Exam pattern: 'the team is arguing about approach' = storming, and the best answer is almost always to facilitate the discussion, not to decide for them or to reassign someone.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
342

## Slide 343
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
The performance dip you must expect at storming
Chart: 
| Forming | Storming | Norming | Performing | Adjourning
Team productivity index | 40 | 25 | 62 | 92 | 55
Trust / psychological safety | 30 | 34 | 70 | 95 | 88
WHAT IT TELLS YOU
Productivity falls at storming — this is normal, not a sign your team is failing.
Trust keeps rising through storming if conflict is handled openly; suppressing it flattens the whole curve.
Teams left in storming never reach the performing payoff, which is where most of the value is created.
At adjourning output falls but trust stays high — that is exactly when knowledge transfer is easiest.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
343

## Slide 344
EXAM FOCUS
Tuckman traps on the exam
IF THE QUESTION SAYS
A new member joins a high-performing team
THE BEST ANSWER IS
The team regresses toward forming/storming; re-establish roles and ground rules rather than assuming performance continues.
IF THE QUESTION SAYS
Team members openly disagree about the technical approach
THE BEST ANSWER IS
This is storming. Facilitate a structured discussion — conflict here is productive and expected.
IF THE QUESTION SAYS
The team resolves issues without involving you
THE BEST ANSWER IS
Performing. Your job is removing impediments and shielding the team, not reasserting control.
IF THE QUESTION SAYS
Project ends and the team seems demotivated
THE BEST ANSWER IS
Adjourning. Recognise contributions, complete lessons learned and manage the release/transition of each member.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
344

## Slide 345
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
The motivational theories PMI expects you to know
Theory | Core idea | What it tells a project manager
Maslow's hierarchy of needs | Physiological, safety, belonging, esteem, self-actualisation | You cannot motivate with growth opportunities if job security is in doubt — lower needs dominate first
Herzberg's motivation-hygiene | Hygiene factors prevent dissatisfaction; motivators create satisfaction | Fixing salary or the office removes complaints but never creates engagement — that needs achievement and recognition
McGregor's Theory X / Theory Y | X assumes people avoid work; Y assumes people seek responsibility | Your assumption becomes self-fulfilling; Theory Y underpins agile and servant leadership
McClelland's achievement motivation | Achievement, affiliation or power becomes dominant per person | Match the assignment and the reward to the individual's dominant need, not to your own
Vroom's expectancy theory | Motivation = expectancy x instrumentality x valence | If any of the three is zero, motivation is zero — the reward must be attainable, linked and actually wanted
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
345

## Slide 346
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Maslow's hierarchy of needs
STEP 1
Physiological
Pay, rest, food, tolerable working conditions — nothing else motivates while these are unmet.
STEP 2
Safety
Job security, physical and psychological safety, predictable process and fair treatment.
STEP 3
Belonging
Team membership, inclusion, friendship — this is where team-building does its work.
STEP 4
Esteem
Recognition, respect, status, being trusted with meaningful and visible responsibility.
STEP 5
Self-actualisation
Mastery, growth, doing work the person finds intrinsically worth doing.
Practical read: announcing a restructure destroys the safety level, and every motivational lever above it stops working until safety is restored.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
346

## Slide 347
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Herzberg: hygiene factors vs motivators
Hygiene factors
Their absence causes dissatisfaction; their presence does not motivate
Salary, benefits and job security
Working conditions and equipment
Company policy and administration
Quality of supervision and interpersonal relations
Fix these to get to neutral — never to get to engaged
Motivators
Their presence creates genuine satisfaction and effort
Achievement — visibly completing something difficult
Recognition for the work done
The work itself being interesting and meaningful
Responsibility and autonomy over how the work is done
Advancement and personal growth
Exam cue: 'the team got a bonus but morale is still low' — you addressed a hygiene factor. Look for a motivator such as recognition, autonomy or growth.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
347

## Slide 348
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
McGregor's Theory X and Theory Y in practice
Theory X · directive
Assumes people dislike work and avoid responsibility, so supervise closely and control tightly.
Theory Y · participative
Assumes people seek responsibility and self-direct, so delegate, involve and trust.
Theory X risk
Close supervision suppresses initiative and confirms the manager's low expectations — a self-fulfilling loop.
Theory Y risk
Autonomy without clear expectations becomes drift; empowerment still needs boundaries and a definition of done.
Assumption about the team
Resulting management style
PMI's default posture is Theory Y. Agile, servant leadership and self-organising teams all assume Theory Y people.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
348

## Slide 349
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
McClelland's achievement motivation theory
1
Need for achievement (nAch)
Driven by challenging but attainable goals and concrete feedback; dislikes vague or trivial work.
2
Need for affiliation (nAff)
Driven by belonging and harmony; give collaborative work and avoid isolating or adversarial roles.
3
Need for power (nPow)
Driven by influence and impact; give coordination, negotiation and representation responsibilities.
4
Shaped by life experience
One of the three becomes dominant based on a person's history, not on their job title.
5
Use it to design roles
Craft assignments and rewards around each member's dominant need rather than a single team-wide incentive.
6
Build T-shaped people
Balance the needs across the team so it can self-organise instead of depending on one dominant personality.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
349

## Slide 350
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Vroom's expectancy theory
Motivational force
M = E x I x V
Motivation is the product of three beliefs — if any one is zero, the whole motivation is zero.
Expectancy (E)
Effort → Performance
'If I work hard, can I actually succeed?' Undermined by unrealistic targets, missing skills or missing tools.
Instrumentality (I)
Performance → Outcome
'If I succeed, will the promised reward really arrive?' Destroyed by one broken promise.
Valence (V)
Value of the outcome
'Do I actually want that reward?' A team dinner has zero valence for someone who wants a promotion.
Diagnostic use: when motivation is low, test all three terms before assuming the problem is the size of the reward.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
350

## Slide 351
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Two behaviours that quietly destroy your schedule
Parkinson's Law
Work expands to fill the time allotted to it
A five-day task given ten days will take ten days
Generous estimates get consumed, never returned as savings
Counter with short timeboxes and fixed iteration lengths
Counter by making remaining work visible on a burndown
Explains why padding every estimate does not create real buffer
Student syndrome
People start only at the last possible moment
Safety in the estimate is spent at the end, not at the start
Any early problem then hits the deadline with no buffer left
Counter with early checkpoints and definition-of-done gates
Counter by decomposing into small items that finish continuously
Together with Parkinson's Law, the core argument for timeboxing
Critical chain scheduling responds to both by stripping individual task padding and pooling it into a shared project buffer the PM controls.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
351

## Slide 352
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Servant leadership behaviours
1
Listening
Understand the problem as the team experiences it before offering your own solution or judgement.
2
Helping people grow
Treat capability building as a deliverable; grow the team's role capability, not just this project's output.
3
Safe to fail
Make it safe to make mistakes and raise concerns early, when they are still cheap to fix.
4
Coaching, not controlling
Ask questions that let the team find the answer instead of issuing the answer yourself.
5
Remove impediments
Your primary daily job: clear the blockers the team cannot clear from inside the team.
6
Pave the way for others
Promote the energy and intelligence of others; take the credit last and the blame first.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
352

## Slide 353
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Leadership styles you must recognise
Style | Behaviour | Best fit
Servant | Focuses on others' growth, learning, autonomy and well-being | Agile and knowledge work; PMI's default posture
Laissez-faire | Hands-off; the team makes its own decisions with little input | Highly mature, expert, self-organising teams
Transactional | Rewards for meeting goals; manages by exception when things go wrong | Routine, repeatable work with clear measurable targets
Transformational | Inspirational motivation, intellectual stimulation, individual attention | Change programmes needing energy and a compelling vision
Charismatic | High energy, self-confident, strong convictions, persuasive presence | Rallying stakeholders; risky if it substitutes for substance
Interactional | Blend of transactional, transformational and charismatic | Most real projects — deliberately mixed as the situation shifts
Directive | Tells people what to do and how; low participation | Crisis, safety incidents, and brand-new teams at forming
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
353

## Slide 354
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Situational leadership: match style to readiness
Low competence, high commitment
DIRECT. New and enthusiastic. Give clear instruction, standards and close checkpoints.
High competence, high commitment
DELEGATE. Hand over the outcome and the decision rights; stay available, stay out.
Low competence, low commitment
COACH. Explain the why, build skill deliberately and rebuild confidence with early wins.
High competence, low commitment
SUPPORT. The skill is there; the motivation is not. Listen, remove friction, restore purpose.
Task competence of the individual →
Commitment / confidence ↑
There is no single correct leadership style. The ECO enabler is literally 'determine an appropriate leadership style' — appropriate to this person, this task, this moment.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
354

## Slide 355
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Leading vs managing
Leading
Direction, alignment, commitment — about people
Sets and communicates the vision and the why
Aligns people around a shared goal
Inspires, motivates and builds commitment
Develops capability and challenges the status quo
Asks: are we doing the right thing?
Managing
Planning, organising, controlling — about work
Plans, budgets and schedules the work
Organises structure, roles and staffing
Monitors variance and applies corrective action
Maintains stability, predictability and control
Asks: are we doing the thing right?
A project manager does both every day. The exam usually wants leading behaviour in People-domain scenarios and managing behaviour in Process-domain scenarios.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
355

## Slide 356
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Emotional intelligence — the four domains
1
Self-awareness
Recognising your own emotions in the moment and understanding how your actions land on other people.
2
Self-management
Thinking before you act; regulating your response so pressure does not leak into the team as anxiety.
3
Social awareness
Reading the emotional state of the room; empathy for what others are experiencing but not saying.
4
Social skill
Establishing rapport, managing your own attitude and steering relationships toward a productive outcome.
5
Why it matters here
EI is the mechanism behind conflict resolution, influencing, negotiation and stakeholder trust.
6
It is trainable
Unlike personality, EI is a learnable practice — pause, name the emotion, choose the response.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
356

## Slide 357
HANDS-ON ACTIVITY
Role play: practising emotional intelligence under pressure
In trios, run a coaching conversation about a stressful workplace moment. Rotate roles: team leader, team member, observer. The full script and prompts are in the Learner Guide.
25 MIN
1
Team member recalls a recent moment when they reacted emotionally at work and describes it factually.
2
Leader coaches self-awareness: 'what were you feeling, and what did you notice in yourself first?'
3
Leader models self-management by describing a pause-and-clarify response instead of an immediate reaction.
4
Member re-runs the scenario applying the pause, then asks a clarifying question rather than defending.
5
Leader coaches empathy: what might the other person have been experiencing that you did not see?
6
Observer records which of the four EI domains appeared and where the conversation slipped into advice-giving.
DELIVERABLE
One observation sheet per trio mapping the conversation to the four EI domains, plus one improvement each person will apply this week.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
357

## Slide 358
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Interpersonal and team skills
1
Active listening
Listen for content, tone and what is being avoided; confirm understanding before responding.
2
Communication styles assessment
Identify preferred styles so you can tailor how information is delivered per stakeholder.
3
Influencing
Persuade without authority using evidence, relationships and alignment to the other party's interests.
4
Motivation
Apply the right theory to the right person to sustain discretionary effort over a long project.
5
Nominal group technique
Silent idea generation then structured ranking, so loud voices do not dominate the outcome.
6
Political awareness
Understand where real power and informal influence sit, and work with the organisation as it actually is.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
358

## Slide 359
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Rewards vs recognition
Rewards
Tangible, consumable, tied to an outcome
A bonus, a voucher, a gift, a paid course
Given for a specific achievement or measurable outcome
Used to motivate toward a defined result
Must be attainable, visible and fairly applied
Never give a reward without recognition attached to it
Recognition
Intangible, experiential, tied to behaviour
Public thanks, a note to a manager, visible credit
Acknowledges the person's behaviour, not just the outcome
Increases the recipient's sense of being valued
Costs nothing and can be given continuously
Can absolutely be given on its own without any reward
Cultural caution: public individual recognition motivates in some cultures and embarrasses in others. Ask before you design the ritual.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
359

## Slide 360
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Adopt a growth mindset as a leader
1
Experience guides, not dictates
Let past processes inform your action without locking you into last project's answer.
2
Commit to improving
Treat your own leadership practice as something to iterate on, with feedback and deliberate change.
3
Discover through discussion
Find the best approach through debate and introspection rather than asserting it up front.
4
Avoid complacency
Blind acceptance of 'how we do things' is how an organisation stops learning.
5
Model fallibility
A leader who says 'I got that wrong' licenses the whole team to surface their own errors early.
6
Inclusive competence
Lead with empathy, assume motivations vary, and deliberately include external and part-time resources.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
360

## Slide 361
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Plan training, coaching and mentoring
STEP 1
Gap analysis
Compare required knowledge, skills and attributes against what the team actually holds today.
STEP 2
Design the mix
Choose the blend of soft-skill and technical development, formal and informal, per person.
STEP 3
Schedule it close to use
Deliver training near the point of application so the skill is used before it decays.
STEP 4
Deliver and practise
Pair training with coaching so learning converts into active, on-the-job use.
STEP 5
Assess the outcome
Measure improvement, not attendance, and feed the result back into the next gap analysis.
Training is a cost that belongs in the project budget when the gap is project-specific; organisational capability gaps usually belong to the functional manager.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
361

## Slide 362
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Elements of training and delivery models
1
Instructor-led classroom
Highest interaction and fastest clarification; highest cost in time and travel.
2
Virtual classroom
Live but distributed; needs deliberate facilitation to keep participation genuine rather than passive.
3
Self-paced e-learning
Cheap and scalable for explicit knowledge; weak for tacit knowledge and judgement.
4
Document reviews
Structured reading with a comprehension checkpoint; good for standards, policies and compliance content.
5
Interactive simulation
Safe rehearsal of a high-stakes task; the only realistic option for rare, dangerous or costly scenarios.
6
On-the-job training
Real work with a safety net; highest transfer rate but consumes the time of an experienced person.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
362

## Slide 363
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Training vs coaching vs mentoring
Dimension | Training | Coaching | Mentoring
Purpose | Acquire a skill for use now | Apply or improve an existing skill | Long-term personal and professional growth
Horizon | Short — a session or a course | Medium — weeks around a performance goal | Long — months or years
Relationship | Trainer to learners | Coach to individual or team | Experienced person to a less experienced person
Content owner | The trainer sets the curriculum | The coachee sets the goal; coach asks the questions | The mentee sets the direction; mentor shares experience
Also called | Upskilling | Performance coaching | Sponsorship, job shadowing, professional guidance
Typical output | Certification, badge, new capability | Changed behaviour on a specific task | Career progression, transferred tacit knowledge
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
363

## Slide 364
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Steps to coach performance
STEP 1
Agree the goal
Establish what good looks like and confirm the coachee actually owns and wants that goal.
STEP 2
Explore reality
Ask questions to surface what is happening now, with evidence, not opinion or hearsay.
STEP 3
Give specific feedback
Describe observed behaviour and its impact — never label the person's character.
STEP 4
Demonstrate and practise
Model the desired behaviour, then let them rehearse it while you observe.
STEP 5
Agree actions and follow up
Commit to a small, dated action and schedule the check-in that makes it real.
Coaching is asking, not telling. If you find yourself giving the answer in the first two minutes, you have switched from coaching to instructing.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
364

## Slide 365
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
SBI — a technique for giving feedback
STEP 1
Situation
Anchor the feedback in a specific time and place: 'in yesterday's design review…' — never 'you always…'.
STEP 2
Behaviour
Describe only what was observable — the words said, the action taken — with no interpretation of motive.
STEP 3
Impact
State the effect on you, the team or the work: '…the tester left without the information she needed.'
STEP 4
Pause and listen
Stop talking. Let the other person respond; you may be missing context that changes the picture.
STEP 5
Agree forward action
Convert the conversation into one specific behaviour to repeat or change next time.
SBI works for positive feedback too — and positive SBI is the single cheapest way to make corrective feedback land later.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
365

## Slide 366
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Coach teams and individuals in project management
1
Delegate then observe
Hand over a real task, watch how it is done and feed back — the most common informal coaching opportunity.
2
Encourage others to lead
Let a team member run the stand-up, the demo or the risk review while you sit in the room.
3
Collaborate on a PM task
Build the schedule or the risk register together so the reasoning is transferred, not just the artifact.
4
Facilitate sessions
Formalise it: teach facilitation by co-facilitating, then handing the session over.
5
Pair individuals
Deliberately pair a strong and a developing member on the same work item to transfer tacit knowledge.
6
Model behaviours
The team copies what you do under pressure, not what you wrote in the team charter.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
366

## Slide 367
HANDS-ON ACTIVITY
Role play: coaching a struggling team member
In pairs, run a one-to-one coaching conversation about a performance gap (e.g. low customer satisfaction scores). Swap roles after the first round. Full script in the Learner Guide.
25 MIN
1
Leader opens with a genuine strength observed before naming the gap.
2
Leader uses SBI to describe one specific, observed behaviour and its impact — no character judgements.
3
Leader asks open questions to let the coachee diagnose the cause themselves rather than supplying it.
4
Leader demonstrates the desired behaviour once, briefly, then hands the conversation back.
5
Coachee rehearses the behaviour; leader gives one reinforcing and one adjusting piece of feedback.
6
Both agree one dated action and the date of the follow-up check-in.
DELIVERABLE
A completed coaching note per pair: the observed behaviour, the impact, the agreed action and the follow-up date.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
367

## Slide 368
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Measure training and coaching outcomes
1
Post-training assessment
Test whether the skill can be performed, not merely whether the session was enjoyed.
2
Observation on the job
The real proof: does the behaviour appear in actual work two weeks after the course?
3
Certification evidence
Badges or a letter from the awarding body give externally verifiable proof of a capability.
4
Retrospective discussion
Share what was learned in a team retrospective so one person's training benefits everyone.
5
Augment with coaching
Training alone decays fast; coaching after training converts knowledge into active use.
6
Knowledge-sharing pairs
Pair the trained person with a peer so they must explain it — teaching consolidates learning.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
368

## Slide 369
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Maintain mentorships and job shadowing
1
Longer-term partnerships
Mentoring is a relationship, not an event; value accrues over months of repeated contact.
2
Job shadowing
Observing an expert at work transfers both explicit procedure and the tacit judgement behind it.
3
Tailor to the context
Some organisations run formal mentoring with reporting; others keep it deliberately informal.
4
Use during transitions
Shadowing at handover moves skills from the project team into the receiving operations team.
5
Recruit stakeholders
Valued stakeholders make excellent mentors and their involvement deepens their engagement.
6
Mentor project managers
Many organisations grow PMs specifically through mentorship rather than formal training.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
369

## Slide 370
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Assess team member performance
1
Formal and informal methods
Combine structured assessments with continuous observation; neither alone gives a fair picture.
2
Baseline on joining
Assess when a member joins so you can measure development rather than guess at it later.
3
Monitor progress
Repeat the assessment so the conversation is about trajectory, not a single snapshot.
4
Self-regulating teams
Psychologically safe agile teams assess and correct their own performance in retrospectives.
5
Focus on the team
Team performance assessments target the team's capability; individual appraisal usually sits with line management.
6
Feed Develop Team
Assessment results identify the training, coaching and team-building the team actually needs next.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
370

## Slide 371
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Self-organising teams collaborate and learn
1
Encourage initiative
Expect team members to pick up work and raise problems without waiting for an assignment.
2
Cross-role coaching
Coach people on how to contribute to other project roles so the team is resilient to absence.
3
Surface tacit knowledge
Coach the individual who holds undocumented know-how into explaining and demonstrating it.
4
Use servant leadership
Support and enable rather than assign and check; self-organisation dies under close supervision.
5
Shadow during transitions
Use shadowing, coaching and mentoring to move skills from the project team to the organisation.
6
Ground rules still apply
Self-organising is not unbounded — the team charter defines the boundary they organise within.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
371

## Slide 372
ECO PEOPLE T2 · MANAGE CONFLICTS
Manage Team
Track team performance, provide feedback, resolve issues and manage team changes to optimise project performance.
INPUTS
Project management plan: resource management plan
Project documents: issue log, lessons learned register, project team assignments, team charter
Work performance reports
Team performance assessments
Enterprise environmental factors and organizational process assets
TOOLS & TECHNIQUES
Interpersonal and team skills: conflict management, decision making, emotional intelligence, influencing, leadership
Project management information system
OUTPUTS
Change requests
Project management plan updates: resource management plan, schedule baseline, cost baseline
Project document updates: issue log, lessons learned register, project team assignments
Enterprise environmental factors updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
372

## Slide 373
ECO PEOPLE T2 · MANAGE CONFLICTS
Who owns conflict on a project
Everyone owns it. You influence how it is handled.
Shared responsibility
All team members and stakeholders are responsible for managing conflict, not just the PM.
PM influences direction
You shape the handling through interpersonal skills and servant leadership, not authority.
Team resolves it
The team is empowered to resolve its own conflicts; the leader facilitates when they cannot.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
373

## Slide 374
ECO PEOPLE T2 · MANAGE CONFLICTS
Sources of conflict on projects
1
Competition for resources
Scarce people, budget and equipment force zero-sum choices between work streams.
2
Differing objectives and values
Goals that conflict at the organisational level surface as friction at the team level.
3
Role and responsibility disputes
Ambiguity about who decides and who delivers is the most common and most fixable source.
4
Differing work approaches
Two competent people with different methods each believe the other is doing it wrong.
5
Communication breakdown
Missing, late or ambiguous information gets filled in with assumption, then with blame.
6
Novelty of the project
Projects are unique and members often have not worked together before — no established norms exist yet.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
374

## Slide 375
ECO PEOPLE T2 · MANAGE CONFLICTS
Effective vs ineffective conflict management
Ineffective conflict management
Conflict suppressed, avoided or escalated badly
Destructive behaviour and personal attacks
Animosity that outlasts the disagreement itself
Poor performance as energy diverts from the work
Reduced productivity and lost calendar time
Attrition — good people leave dysfunctional teams
Effective conflict management
Conflict surfaced early and worked through openly
Improved understanding of the other position
Better decisions because assumptions were challenged
Higher performance from genuine, not artificial, agreement
Higher productivity as issues stop recurring
Stronger relationships that survive the next disagreement
Zero conflict is not the target. Zero conflict usually means people have stopped saying what they think.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
375

## Slide 376
ECO PEOPLE T2 · MANAGE CONFLICTS
Conflict as part of a psychologically safe culture
1
Disruption and innovation connect
The friction that produces new ideas is the same friction that feels uncomfortable.
2
Encourage disagreement
Actively invite dissent so risks are named while there is still time to act on them.
3
Separate people from positions
Attack the problem, not the person holding the opposing view.
4
Prevent escalation
Address friction at the level of a differing opinion, before it hardens into a personal contest.
5
Ground rules make it safe
Agreed norms tell people what disagreement is allowed to look like on this team.
6
Leader goes first
Safety is created when the leader publicly accepts challenge without punishing the challenger.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
376

## Slide 377
ECO PEOPLE T2 · MANAGE CONFLICTS
Leas' five levels of conflict — escalation
Chart: 
| L1 Problem to solve | L2 Disagreement | L3 Contest | L4 Crusade | L5 World war
Difficulty of resolution | 1 | 2 | 4 | 7 | 10
Focus on winning vs solving | 1 | 3 | 6 | 9 | 10
WHAT IT TELLS YOU
L1: information sharing and collaboration still work; the parties want a solution.
L2: self-protection begins — language becomes guarded and positions get defended.
L3: the goal shifts from solving the problem to winning against the other party.
L4: protecting one's own group becomes the point; the original issue is almost irrelevant.
L5: destroying the other party is the objective — separate the parties, escalate, do not mediate.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
377

## Slide 378
ECO PEOPLE T2 · MANAGE CONFLICTS
Leas' levels of conflict and your intervention
Level | What you hear | What to do
1 · Problem to solve | 'How should we handle this?' — focus on the issue, open language | Facilitate collaboratively; the team can resolve this themselves
2 · Disagreement | Guarded language, self-protection, humour used to deflect | Encourage direct dialogue; make it safe to state the real position
3 · Contest | 'I' vs 'you', winning matters, positions distorted to score points | Structure the conversation; refocus on shared objectives and data
4 · Crusade | 'Us' vs 'them', factions form, the issue becomes ideological | Bring in a neutral facilitator; the PM is likely seen as partisan
5 · World war | Destroying the other party is the goal; no resolution is acceptable | Separate the parties, escalate to sponsor/HR — mediation will fail
Intervention must match the level. Collaboration attempted at level 4 or 5 does not just fail — it burns your credibility as a neutral party.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
378

## Slide 379
ECO PEOPLE T2 · MANAGE CONFLICTS
The five conflict-resolution modes
Force / Direct (win-lose)
High assertiveness, low cooperation. Push your position through, usually with power.
Collaborate / Problem solve (win-win)
High on both. Work the underlying interests until both parties genuinely gain.
Withdraw / Avoid (lose-lose)
Low on both. Retreat from the situation or postpone the issue to another time.
Smooth / Accommodate (lose-win)
Low assertiveness, high cooperation. Concede your position to preserve the relationship.
Cooperativeness — concern for the other party →
Assertiveness — concern for own goal ↑
Compromise / Reconcile sits in the middle of the grid — moderate on both axes, and classified lose-lose because both parties give something up.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
379

## Slide 380
ECO PEOPLE T2 · MANAGE CONFLICTS
The five conflict approaches and when each is appropriate
Approach | Outcome | What it looks like | When it is right
Collaborate / Problem solve | Win-win | Incorporate multiple viewpoints; open dialogue to real consensus | PMI's default. Time exists, relationship matters, stakes are high
Compromise / Reconcile | Lose-lose | Both parties give something up to reach a workable middle | Equal power, moderate stakes, a temporary fix under time pressure
Smooth / Accommodate | Lose-win | Emphasise areas of agreement; concede to keep harmony | You are wrong, the issue matters far more to them, or goodwill is the real objective
Force / Direct | Win-lose | Pursue your view at the other party's expense; use position power | Safety, legal or ethical breach; genuine emergency; no time
Withdraw / Avoid | Lose-lose | Retreat from the situation or postpone the issue | Emotions too high to be productive; you need facts; the issue is trivial or will resolve itself
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
380

## Slide 381
ECO PEOPLE T2 · MANAGE CONFLICTS
A repeatable conflict-resolution sequence
STEP 1
Set the scene
Get the parties together with an agreed purpose; state the ground rules for the conversation.
STEP 2
Identify concerns
Each party states their position uninterrupted while the other listens without rebutting.
STEP 3
Clarify the issues
Summarise both positions back and confirm with each party that the summary is accurate.
STEP 4
Problem-solve jointly
Move from positions to interests and generate options that could satisfy both.
STEP 5
Create an action plan
Convert the agreement into specific, owned, dated actions — usually clearer roles.
STEP 6
Close and follow up
Confirm both parties are satisfied and schedule the check-in that verifies it held.
The four behaviours that make this work: open communication, active listening, joint problem solving, and a clear action plan that neither party can quietly ignore.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
381

## Slide 382
HANDS-ON ACTIVITY
Role play: a conflict over project responsibilities
In trios, work a real conflict: a senior member feels overloaded and over-responsible; a newer member feels distrusted and blocked from contributing. Third person facilitates. Full script in the Learner Guide.
30 MIN
1
Facilitator sets the scene, states the purpose and agrees ground rules for the conversation.
2
Each party states their concern for two minutes, uninterrupted, using 'I feel / I observe' language.
3
Facilitator summarises both concerns and gets explicit agreement that the summary is accurate.
4
Both parties generate options together; the facilitator captures them without evaluating.
5
Agree a concrete action plan — clear task ownership and a weekly check-in — and name the owner of each item.
6
Debrief: which of the five conflict modes was actually used, and which of Leas' levels did this conflict sit at?
DELIVERABLE
One completed conflict resolution record per trio: sources, level, mode used, agreed actions with owners, and the follow-up date.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
382

## Slide 383
ECO PEOPLE T2 · MANAGE CONFLICTS
Interpersonal skills that resolve conflict
1
Emotional intelligence
Use empathy to understand what is driving each party and to defuse the emotional charge first.
2
Influencing
Persuade parties to reconsider their tone, approach or mindset when direct authority would only harden positions.
3
Leadership
Steer the exchange toward a constructive direction and hold the group to the agreed ground rules.
4
Decision making
When the parties genuinely deadlock, offer a decision method or a solution that moves the situation forward.
5
Active listening
Listen for accusing language, caustic tone and defensive posture — these tell you the escalation level.
6
Political awareness
Understand what each party stands to lose organisationally, which is often the real driver.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
383

## Slide 384
ECO PEOPLE T2 · MANAGE CONFLICTS
Ground rules: establish, adhere, rectify
1
Where they live
Ground rules are documented in the team charter, created by the team rather than imposed by the PM.
2
What they cover
Meeting conduct, response times, decision rights, how disagreement is raised, escalation paths.
3
Foster adherence
Reference them regularly in real situations so they stay a live agreement rather than a forgotten document.
4
Detect violations
Watch for the quiet ones: interruptions, decisions made outside the agreed forum, missed commitments.
5
Rectify violations
Address privately and early using SBI; the whole team is watching whether the rule is real.
6
Revisit and update
When a rule stops fitting, the team changes it deliberately — it does not simply erode.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
384

## Slide 385
EXAM FOCUS
Conflict questions — the traps PMI sets
IF THE QUESTION SAYS
Two team members disagree; the PM should…
THE BEST ANSWER IS
Let them resolve it first. The team is empowered; you facilitate only if they cannot reach resolution.
IF THE QUESTION SAYS
'What is the BEST conflict resolution technique?'
THE BEST ANSWER IS
Collaborate / problem solve. It is the only genuine win-win and is PMI's default answer absent other constraints.
IF THE QUESTION SAYS
A safety or compliance breach is happening now
THE BEST ANSWER IS
Force / direct. Emergencies and ethical breaches are the legitimate case for asserting authority.
IF THE QUESTION SAYS
Emotions are running too high to discuss the issue
THE BEST ANSWER IS
Withdraw / avoid temporarily — cool down, gather facts, then return and collaborate.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
385

## Slide 386
EXAM FOCUS
More conflict and team traps
IF THE QUESTION SAYS
Conflict recurs on the same topic every week
THE BEST ANSWER IS
Go to root cause. Recurring conflict usually signals unclear roles or an unresolved structural constraint, not personalities.
IF THE QUESTION SAYS
A team member repeatedly breaks an agreed ground rule
THE BEST ANSWER IS
Address it directly and privately with the individual first, referencing the team charter the team itself created.
IF THE QUESTION SAYS
The sponsor asks you to overrule the team's technical decision
THE BEST ANSWER IS
Represent the voice of the team: present their reasoning and the impact, then negotiate rather than simply comply or refuse.
IF THE QUESTION SAYS
Conflict is at Leas' level 5 between two departments
THE BEST ANSWER IS
Separate the parties and escalate. Collaboration and mediation are not viable at that level.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
386

## Slide 387
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
How project teams decide
1
Team charter sets the rules
The charter identifies the decision-making and conflict-resolution criteria in advance.
2
Teams define their Way of Working
Mature teams establish their own norms for which decisions need which method.
3
Consensus is the aim
Teams try for genuine agreement first; a vote is what you use when consensus is not reachable.
4
Decide who decides
The most common decision failure is ambiguity about whether a group is advising or deciding.
5
Timebox the decision
An undecided decision has a cost; set a deadline and a fallback method before you start.
6
Record the rationale
Capture why, not just what — it prevents the same debate reopening three months later.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
387

## Slide 388
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Decision-making methods
Method | How it works | When to use it
Unanimity | Everyone agrees on a single course of action | High-cohesion teams; irreversible decisions; the Delphi technique converges toward it
Majority | More than 50% of the group supports the option | Use odd-numbered groups so a tie cannot block the decision
Plurality | The largest single block decides, even without 50% | More than two options on the table and no majority emerges
Autocratic | One individual decides for the whole group | Emergency, or the decision is genuinely one person's accountability
Delphi technique | Anonymous expert rounds with feedback until convergence | Expert estimates where seniority or politics would distort an open discussion
Multicriteria decision analysis | Score options against weighted criteria in a matrix | Comparing suppliers, designs or candidates on several dimensions at once
Fist of five | Each person shows 0-5 fingers to signal support level | Fast consensus check; anything below three triggers a discussion
Dot voting | Each participant places a fixed number of dots on options | Prioritising a long list of ideas quickly and visibly
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
388

## Slide 389
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Diverge then converge
STEP 1
Frame the question
Agree exactly what is being decided and what constraints any option must satisfy.
STEP 2
Diverge on the problem
Explore the problem space fully before anyone proposes a solution.
STEP 3
Diverge on solutions
Generate options without evaluation — brainstorming, nominal group technique, mind mapping.
STEP 4
Converge with criteria
Filter using agreed criteria, then score with multicriteria decision analysis or dot voting.
STEP 5
Decide and record
Choose, capture the rationale and dissent, and confirm who commits to the decision.
The classic failure mode is converging too early — the group evaluates the first idea and never generates the second.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
389

## Slide 390
HANDS-ON ACTIVITY
Practice: multi-criteria decision analysis
In table groups, choose between three candidate vendors for a project component using a weighted scoring matrix, then compare how the group's decision method changed the outcome.
25 MIN
1
List the decision criteria that genuinely matter (cost, capability, risk, delivery time, support).
2
Weight each criterion by importance and get the group to agree the weights before seeing the options.
3
Score all three vendors against each criterion, using evidence rather than preference.
4
Compute the weighted totals and identify the top-ranked option.
5
Re-run the same choice using dot voting alone and note whether the answer changes.
6
Debrief which method you would defend to a sponsor and why.
DELIVERABLE
A completed weighted scoring matrix with agreed weights, scores, the recommended vendor and a one-paragraph rationale.
TOOL
Pivot Analysis
https://alfredang.github.io/novapivot/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
390

## Slide 391
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Manage Communications
Ensure timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring and disposition of project information.
INPUTS
Project management plan: resource management plan, communications management plan, stakeholder engagement plan
Project documents: change log, issue log, lessons learned register, quality report, risk report, stakeholder register
Work performance reports
Enterprise environmental factors and organizational process assets
TOOLS & TECHNIQUES
Communication technology, methods and skills (competence, feedback, nonverbal, presentations)
Project management information system
Project reporting
Interpersonal and team skills: active listening, conflict management, cultural awareness, meeting management, networking
Meetings
OUTPUTS
Project communications
Project management plan updates: communications management plan, stakeholder engagement plan
Project document updates: issue log, lessons learned register, project schedule, risk register, stakeholder register
Organizational process assets updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
391

## Slide 392
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Barriers to communication
1
Language differences
Misunderstanding from differences in language, dialect or fluency — including polite over-agreement.
2
Cultural differences
Norms about directness, hierarchy and disagreement vary; the same words carry different meaning.
3
Technical jargon
Insider vocabulary excludes the very stakeholders whose decision you need.
4
Physical barriers and noise
Distance, poor connections, background noise and time-zone lag degrade the signal.
5
Psychological barriers
Stress, fear of blame or fatigue stop people hearing and stop people speaking.
6
Assumptions and perception
Filling gaps with what you expect to be true is the fastest route to a costly rework.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
392

## Slide 393
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Assertive vs aggressive communication
Assertive
Direct, respectful, confident — the target style
States a position clearly without attacking the other person
Uses 'I' language: 'I need the spec by Friday because…'
Says no to the request without rejecting the person
Invites the other view and genuinely listens to it
Produces clarity and preserves the relationship
Aggressive
Dominating, confrontational, disrespectful
Wins the exchange at the other person's expense
Uses 'you' accusations: 'you never deliver anything on time'
Interrupts, raises voice, uses status to close down debate
Treats disagreement as disloyalty
Produces short-term compliance and long-term silence
The two failure modes below assertive: PASSIVE (avoids confrontation, agrees then does not deliver) and PASSIVE-AGGRESSIVE (disguised hostility, indirect sabotage, sarcasm).
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
393

## Slide 394
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
The communication styles
Style | Behaviour | Effect on the team
Assertive | Direct, respectful, confident; states needs clearly | Issues get raised early and resolved; the target style
Aggressive | Dominating, confrontational, disrespectful | Compliance in the room, silence afterwards; risks go unreported
Passive | Submissive, avoids confrontation, indirect | Agreement that is not real; commitments quietly missed
Passive-aggressive | Indirect, disguised hostility, sarcasm | Corrosive; the conflict continues underground and cannot be resolved
Manipulative | Controlling and deceitful; uses influence covertly | Destroys trust permanently once detected; an ethics issue
Communication styles assessment is an explicit interpersonal and team skill in Plan Communications Management — use it to tailor your approach per stakeholder.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
394

## Slide 395
HANDS-ON ACTIVITY
Role play: overcoming a communication barrier
In pairs, run a conversation in which one party uses heavy technical jargon and unstated assumptions with a non-technical counterpart. Full script in the Learner Guide.
20 MIN
1
Speaker deliberately explains a solution using acronyms and internal jargon for ninety seconds.
2
Listener notes every point at which they lost the thread, without interrupting.
3
Speaker restarts, replacing every technical term with a plain outcome the listener cares about.
4
Listener asks clarifying questions; speaker answers without reintroducing jargon.
5
Both identify the assumptions the speaker made about the listener's prior knowledge.
6
Swap roles and repeat with a different topic.
DELIVERABLE
A short 'plain-language rewrite': the original jargon-heavy explanation beside the version a sponsor could act on.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
395

## Slide 396
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Where and how the team works
1
Colocation is best where possible
A shared physical space maximises informal communication and tacit knowledge transfer.
2
Tight matrix / war room
Deliberately putting the team in one room for a critical phase measurably raises throughput.
3
Environment affects performance
Noise, lighting, screens and meeting-room access are real performance variables, not comforts.
4
Foster meaningful interaction
Design contact points that support autonomy rather than surveillance.
5
Respect agreed working hours
Ground rules about core hours and response times protect focus and prevent burnout.
6
Hybrid is the normal case
Most teams are now partly distributed; plan for it rather than treating it as an exception.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
396

## Slide 397
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Managing virtual team members
1
Watch team dynamics
Distance hides friction; you must actively look for it rather than waiting for it to be reported.
2
Enforce transparency
Make work and status visible with Kanban-style boards so nobody has to ask what is happening.
3
Hold accountability
Clear ownership matters more remotely, where informal reminders do not happen naturally.
4
Use video deliberately
Cameras on for discussion so you can read body language, tone and hesitation.
5
Check active participation
Silence on a call is ambiguous — invite each person by name rather than asking 'any questions?'.
6
Overlap working hours
Protect a common window across time zones for the interaction that genuinely needs to be synchronous.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
397

## Slide 398
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Virtual team best practices
1
Manage the isolation risk
Remote members drift out of the informal loop; build in deliberate social contact.
2
Shared goals over individual output
Focus on team commitments so distributed members feel part of one outcome.
3
Instil shared commitment
A visible, common definition of done does more for cohesion than any social event.
4
Standardise the tooling
One agreed channel per purpose prevents information fragmenting across five tools.
5
Write more, assume less
Distributed teams need decisions recorded in writing because corridor clarification is unavailable.
6
Rotate meeting inconvenience
Do not always make the same time zone take the 11pm call.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
398

## Slide 399
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Negotiate and run effective meetings
1
Negotiation is a conversation
Treat it as a conversation with internal or external parties aimed at reaching agreement.
2
Aim for consensus
Use effective communication so collaboration, not victory, is the objective of the exchange.
3
Stay positive
Keeping the tone constructive materially increases the likelihood of a durable agreement.
4
Meetings: publish an agenda
State the purpose and the desired outcome; if you cannot, cancel the meeting.
5
Timebox discussion
Everyone's time is a project cost; protect it with explicit time limits per item.
6
Close with actions
End every meeting with decisions, owners and dates — otherwise it produced nothing.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
399

## Slide 400
ECO PEOPLE T1 · DEVELOP A COMMON VISION
Root-cause analysis of a misunderstanding of the vision
STEP 1
Detect the symptom
Work is being delivered that is technically correct but does not serve the intended outcome.
STEP 2
Break down the situation
Separate what was communicated, what was heard, and what was actually built.
STEP 3
Ask why five times
Drive past 'they misunderstood' to the mechanism — missing context, competing message, no feedback loop.
STEP 4
Identify the true root
Usually a vision never made concrete, or a middle layer translating it differently to each group.
STEP 5
Correct and re-promote
Restate the vision with concrete examples and verify understanding by asking them to restate it.
ECO People T1 explicitly requires you to 'break down situations to identify the root cause of a misunderstanding of the vision' — a new 2026 enabler.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
400

## Slide 401
ECO PEOPLE T1 · DEVELOP A COMMON VISION
Keep the common vision alive
1
Co-create it
A vision the key stakeholders helped write is defended; one they were shown is merely tolerated.
2
Promote it continuously
Repeat it at kick-off, at every review and in every decision rationale until it is boring to you.
3
Make it decidable
A useful vision resolves trade-offs — if it cannot settle an argument it is a slogan, not a vision.
4
Keep it current
Business environments move; a vision not revisited quietly becomes false and the team notices before you do.
5
Test understanding
Ask team members to state the vision in their own words; divergence is your early warning.
6
Connect daily work to it
Show each person how their work package moves the outcome — this is the strongest motivator you have.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
401

## Slide 402
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
AI's effect on team roles and upskilling
1
Roles shift, not vanish
Routine drafting, summarising and reporting move to AI; judgement, context and accountability stay human.
2
New capability gaps
Prompting, output verification and data handling become skills your gap analysis must now include.
3
Verification is a task
AI output must be reviewed by a competent human; build that review step explicitly into the workflow.
4
Upskill, do not displace
Plan training so existing members move up the value chain rather than being replaced by tooling.
5
Address the anxiety
Fear of replacement is a safety-level need in Maslow's terms and will block every other motivator.
6
Govern the use
Agree ground rules on confidentiality, attribution and permitted uses before shadow adoption sets them.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
402

## Slide 403
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Implement Risk Responses
Execute agreed-upon risk response plans. Planning responses without implementing them is a classic exam trap.
INPUTS
Project management plan: risk management plan
Project documents: lessons learned register, risk register, risk report
Organizational process assets
TOOLS & TECHNIQUES
Expert judgment
Interpersonal and team skills: influencing
Project management information system
OUTPUTS
Change requests
Project document updates: issue log, lessons learned register, project team assignments, risk register, risk report
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
403

## Slide 404
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Conduct Procurements
Obtain seller responses, select a seller and award a contract — the executing half of procurement management.
INPUTS
Project management plan: scope, requirements, communications, risk, procurement management plans; configuration management plan; cost baseline
Project documents: lessons learned register, project schedule, requirements documentation, risk register, stakeholder register
Procurement documentation, seller proposals
Enterprise environmental factors and organizational process assets
TOOLS & TECHNIQUES
Expert judgment
Advertising
Bidder conferences
Data analysis: proposal evaluation
Interpersonal and team skills: negotiation
OUTPUTS
Selected sellers
Agreements
Change requests
Project management plan updates
Project document updates: lessons learned register, requirements documentation, resource calendars, risk register, stakeholder register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
404

## Slide 405
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
The habit that carries you through the People domain
Facilitate first. Direct only when you must.
Empower before deciding
Ask whether the team can resolve it before you resolve it for them.
Understand before acting
Gather facts and hear the parties before choosing an intervention or escalating.
Escalate with a recommendation
When you must go up, bring the impact, the options and your recommended action.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
405

## Slide 406
RECAP
Topic 4 recap — Lead the Project Team
1
Execution processes
Direct and Manage Project Work produces deliverables, work performance data, issues and change requests.
2
Data → information → reports
Raw measurement becomes meaningful by comparison, then becomes a communication artifact.
3
Artifacts under control
Configuration management governs the product; version and document control keep the record honest.
4
Knowledge
Explicit knowledge is codified and shared; tacit knowledge needs trust, conversation and shadowing to move.
5
Team development
Tuckman: forming, storming, norming, performing, adjourning — direct, coach, support, delegate, close.
6
Motivation
Maslow, Herzberg, McGregor, McClelland and Vroom each answer a different question about why effort appears.
7
Leadership style
Servant leadership is the default; the right style is situational and deliberately chosen.
8
Emotional intelligence
Self-awareness, self-management, social awareness and social skill underpin every People-domain task.
9
Conflict
Collaborate is the best mode; Leas' levels tell you when collaboration is no longer viable and escalation is required.
10
Communication
Tailor to the stakeholder, remove barriers, be assertive, and make virtual work visible and written down.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
406

## Slide 407
WHAT YOU WILL BUILD
Hands-on Labs — Topic 4
1
Lab 15. RACI Responsibility Assignment Matrix
People T3, Process T4 · LO2 · 20 min in class + 25 min self-study
Produces: RACI matrix, Resource plan
2
Lab 16. Tuckman Diagnosis and Motivation Theory Application
People T3 · LO3 · 20 min in class + 25 min self-study
Produces: Team stage diagnosis, Motivation action plan
3
Lab 17. Conflict Resolution Role-Play across the Five Modes
People T2 · LO3 · 20 min in class + 30 min self-study
Produces: Conflict analysis, Resolution strategy
4
Lab 18. Communication Plan, Channels Formula and Status Report
People T8 · LO4 · 20 min in class + 30 min self-study
Produces: Communications management plan, Status report
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
407

## Slide 408
HANDS-ON ACTIVITY
Lab 15. RACI Responsibility Assignment Matrix
Case study: Contoso Training Portal Upgrade. People T3, Process T4 · LO2. Produces RACI matrix, Resource plan.
20 min in class
1
List the Lab 11 work packages down the rows and the project roles across the columns.
2
Open the RACI tool and assign Responsible, Accountable, Consulted and Informed for every work package.
3
Verify exactly ONE Accountable per row — two accountable parties means nobody is accountable.
4
Scan the columns for overload: a role Responsible for most rows is a single point of failure.
5
Reduce excessive Consulted entries — over-consultation is the most common cause of decision latency.
6
Review the matrix with the team and have each member confirm their assignments aloud.
DELIVERABLE
RACI matrix, Resource plan
TOOL
RACI Matrix
alfredang.github.io/raci/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
408

## Slide 409
HANDS-ON ACTIVITY
Lab 16. Tuckman Diagnosis and Motivation Theory Application
Case study: Contoso Training Portal Upgrade. People T3 · LO3. Produces Team stage diagnosis, Motivation action plan.
20 min in class
1
Assess which Tuckman stage the Contoso team is in, citing the observable behaviours that justify your diagnosis.
2
State the leadership action appropriate to that stage rather than the one you personally prefer.
3
Map each team member's dominant motivator using McClelland: achievement, affiliation or power.
4
Apply Herzberg to separate hygiene complaints from genuine motivator gaps — they need different remedies.
5
Design one specific intervention per team member, with a date and an observable success indicator.
6
Define how you will detect regression to an earlier stage after the next team change.
DELIVERABLE
Team stage diagnosis, Motivation action plan
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
409

## Slide 410
HANDS-ON ACTIVITY
Lab 17. Conflict Resolution Role-Play across the Five Modes
Case study: Contoso Training Portal Upgrade. People T2 · LO3. Produces Conflict analysis, Resolution strategy.
20 min in class
1
Read the conflict scenario and identify the true source: resources, priorities, technical opinion, or interpersonal style.
2
Assess the conflict's position on Leas' five levels — the level dictates whether the team can still resolve it themselves.
3
Role-play the conflict using each of the five modes in turn: collaborate, compromise, accommodate, force, avoid.
4
Record what each mode produced and the relationship cost it incurred.
5
Select the appropriate mode for this situation and justify it against the urgency and the relationship's importance.
6
Write the agreed resolution, the ground rule that prevents recurrence, and how adherence will be monitored.
DELIVERABLE
Conflict analysis, Resolution strategy
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
410

## Slide 411
HANDS-ON ACTIVITY
Lab 18. Communication Plan, Channels Formula and Status Report
Case study: Contoso Training Portal Upgrade. People T8 · LO4. Produces Communications management plan, Status report.
20 min in class
1
List every stakeholder group from Lab 07 with the information each actually needs — not everything you have.
2
Calculate the communication channels using N(N−1)/2 and state what the result implies for meeting design.
3
Specify format, frequency, method and owner for each communication.
4
Classify each as push, pull or interactive, and confirm anything requiring confirmed understanding is interactive.
5
Draft a one-page status report tailored to the steering committee: exceptions and decisions needed, not raw activity.
6
Draft the same status for the delivery team and note how radically the content differs for the same underlying facts.
DELIVERABLE
Communications management plan, Status report
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
411

## Slide 412
05
TOPIC
Monitor and Control the Project
Monitoring and controlling is where the plan meets reality. You measure actual performance against the baselines, decide whether the variance matters, and act — through change control, corrective action, quality control, risk response and impediment removal.
1
Monitor and control project work and report performance
2
Evaluate progress with earned value management
3
Control quality with the seven basic statistical tools
4
Run integrated change control and the change control board
5
Manage risks, issues and impediments to resolution
6
Control procurements and scale agile beyond one team
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
412

## Slide 413
ECO PROCESS T9 · EVALUATE PROJECT STATUS
The controlling mindset
You cannot manage what you do not measure — and you must not measure what you will not act on.
Measure against baseline
Variance only has meaning when compared to an approved scope, schedule and cost baseline.
Decide with thresholds
Governance sets the variance thresholds that trigger escalation, a change request or acceptance.
Act, then update artifacts
Every accepted variance ends in an updated plan, log or register so the record stays truthful.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
413

## Slide 414
ECO PROCESS T9 · EVALUATE PROJECT STATUS
What Monitoring and Controlling Actually Involves
1
Track
Collect work performance data from the work itself — hours booked, defects raised, stories done, invoices received.
2
Review
Convert raw data into work performance information by comparing it to the baseline and asking what the gap means.
3
Regulate
Take corrective or preventive action so future performance moves back toward the approved plan.
4
Report
Package information into work performance reports that a sponsor or steering committee can act on.
5
Change
Route anything that alters a baseline through integrated change control — never adjust a baseline informally.
6
Improve
Feed what you learn into process updates and OPAs so the next phase or project starts better than this one did.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
414

## Slide 415
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Monitor and Control Project Work — ITTO
Purpose: track, review and report overall progress so stakeholders understand true status and the team can forecast where the project will land if nothing changes.
INPUTS
Project management plan (all components)
Project documents: assumption log, basis of estimates
Cost and schedule forecasts
Issue log, lessons learned register, risk register
Milestone list and quality reports
Work performance information
Agreements and EEFs/OPAs
TOOLS & TECHNIQUES
Expert judgement on earned value and forecasting
Data analysis: alternatives, cost-benefit analysis
Earned value analysis and root cause analysis
Trend analysis and variance analysis
Decision making: voting on options
Meetings: status reviews and steering committees
OUTPUTS
Work performance reports
Change requests
Project management plan updates
Project document updates: cost and schedule forecasts
Issue log and lessons learned register updates
Risk register updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
415

## Slide 416
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Data to Information to Reports — the Performance Chain
Stage | What it is | Example | Who consumes it
Work performance data | Raw, unanalysed observations and measurements taken during execution | 42 hours booked; 3 defects logged; 5 of 8 stories done | Project team, delivery leads
Work performance information | Data analysed in context against the baseline to give it meaning | CPI 0.92, SPI 1.04 — over budget but slightly ahead of schedule | Project manager, functional managers
Work performance reports | Information packaged physically or electronically to drive decisions | Status report, dashboard, milestone schedule, EVM S-curve | Sponsor, steering committee, PMO
Change requests | Formal proposals to alter a baseline, document or deliverable | Add two developers to recover the critical path | Change control board
Exam cue: 'raw' or 'measurements taken' = data. 'Compared to plan' = information. 'Presented to the sponsor' = report.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
416

## Slide 417
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Report on Performance — the Reporting Toolkit
1
Milestone schedule
High-level visualisation of progress against planned milestone dates — the sponsor's favourite one-pager.
2
Quality reports
Charts and narrative built from collected quality metrics, defect counts and improvement recommendations.
3
EVM reports
Graphs and computed values from the earned value equations, including the PV/EV/AC S-curve and index trends.
4
Variance analysis reports
Graphs and commentary comparing actual results to expected results, with root causes for each gap.
5
Status reports
Period snapshot of scope, schedule, cost, risk and issues, usually with a RAG rating per dimension.
6
Dashboards
Information radiators refreshed automatically so stakeholders self-serve status instead of requesting it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
417

## Slide 418
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Developing Project Metrics and Reconciliation
1
Choose metrics that drive action
A metric no one would act on is overhead. Tie each measure to a decision it informs.
2
Baseline and threshold
Define the target and the tolerance band before measuring so variance is judged, not debated.
3
Leading and lagging
Lagging metrics (CPI, defects escaped) confirm; leading metrics (velocity trend, blocker age) warn early.
4
Reconcile the sources
Timesheets, finance ledger and the schedule tool disagree — reconcile them before publishing a number.
5
Cadence and ownership
Every metric needs an owner, a refresh cadence and a documented calculation method.
6
Review effectiveness
ECO 2026 asks you to continually assess whether your metrics and artifacts are still worth maintaining.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
418

## Slide 419
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Artifact Management Effectiveness (ECO 2026 Emphasis)
1
Identify and tailor artifacts
Select only the registers, logs and plans this project's complexity actually justifies.
2
Create, review, update
An artifact that is not maintained is worse than none — it misleads people who trust it.
3
Ensure accessibility
Stakeholders must be able to find the current version without asking the project manager for it.
4
Single source of truth
One authoritative location per artifact; everything else links to it rather than copying it.
5
Version and configuration
Configuration management controls the deliverable; change control governs the baseline.
6
Assess continually
Retire artifacts that no longer inform a decision and add ones the team keeps recreating informally.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
419

## Slide 420
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Continuous Improvement — Incremental vs Breakthrough
Small incremental improvement
Kaizen-style, team-owned, low risk
Many small changes made continuously by the people doing the work
Low cost, low risk, and reversible if the change does not help
Driven by retrospectives, suggestion systems and daily problem solving
Compounds over time — 1% per sprint is transformational over a year
Typical vehicles: Agile retrospectives, Lean waste reduction
Large breakthrough improvement
Re-engineering, sponsor-owned, high risk
A step change that redesigns a process, technology or operating model
High cost, high disruption, needs executive sponsorship and funding
Usually triggered by a strategic threat or a persistent capability gap
Delivers a large gain at once but risks organisational rejection
Typical vehicles: Six Sigma DMAIC projects, business process reengineering
Continuous improvement is a business strategy set at the organisational level and adopted by projects — usually implemented by the PMO through a structured framework such as Agile, Lean or Six Sigma.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
420

## Slide 421
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
The Continuous Improvement Loop on a Live Project
STEP 1
Observe
Collect metrics, defect data and team feedback from the current period.
STEP 2
Analyse
Use root cause analysis to find why the outcome differed from intent.
STEP 3
Design
Propose a countermeasure with a clear hypothesis of the effect.
STEP 4
Trial
Run the change for one iteration or reporting period only.
STEP 5
Adopt or drop
Keep what measurably helped; discard what did not, and record why.
STEP 6
Update OPAs
Push proven improvements into templates and process assets.
ECO Business Environment T6 asks you to utilise lessons learned, ensure improvement processes are updated, and update organisational process assets — improvement is not real until the OPA changes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
421

## Slide 422
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Curate Knowledge as an Asset
1
Document explicit knowledge
Write down what can be written down — decisions, configurations, runbooks — and archive it where others will look.
2
Surface tacit knowledge
Experience and judgement live in people. Pair work, shadowing and communities of practice move it.
3
Treat knowledge as an asset
Knowledge outlives the team. It belongs to the organisation, not to whoever happened to learn it.
4
Build psychological safety
People only share what did not work if admitting failure is safe. Blameless review is the enabler.
5
Make it findable
A lessons learned repository nobody can search has zero value; tag entries by process, phase and risk category.
6
Capture continuously
Record lessons as they occur, not at closure when the detail and the people have already gone.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
422

## Slide 423
ECO PEOPLE T3 · LEAD THE PROJECT TEAM
Realign Team Efforts with Value During Change
1
Prioritise team cohesion
When members join or depart, the team must re-form. Protect cohesion before chasing velocity.
2
Support realignment
Revisit working agreements, roles and the Definition of Done whenever the team's composition changes.
3
Welcome new members
Treat each joiner as a source of new knowledge and motivation, not simply as extra capacity.
4
Restate shared goals
Re-establish shared understanding of project goals and agreements so nobody optimises the wrong thing.
5
Collaborate on value
Ask each member explicitly how their work adds value; the answer often exposes hidden waste.
6
Navigate disruption
Expect a dip in performance after disruption; coach through it rather than escalating immediately.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
423

## Slide 424
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Perform Integrated Change Control — ITTO
Purpose: review, approve or reject every change request, manage changes to deliverables and baselines, and communicate the decision. This process is performed from project start to finish.
INPUTS
Project management plan: change management plan, configuration management plan, baselines
Project documents: basis of estimates, requirements traceability matrix
Risk report
Work performance reports
Change requests
Enterprise environmental factors and OPAs
TOOLS & TECHNIQUES
Expert judgement and change control tools
Data analysis: alternatives analysis, cost-benefit analysis
Decision making: voting, autocratic decision making, multicriteria decision analysis
Meetings: change control board meetings
Configuration management system
OUTPUTS
Approved change requests
Project management plan updates
Project document updates
Change log (records every request and its disposition)
Updated baselines where the change was approved
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
424

## Slide 425
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Causes of Project Changes
1
Inaccurate initial estimates
Estimates made with the least information ever available prove wrong as detail emerges.
2
New regulations
External legal, tax or safety requirements arrive mid-flight and are non-negotiable.
3
Missed requirements
Elicitation never reached a stakeholder group whose needs surface during review or UAT.
4
Specification changes
The business changes its mind because the market, competitor or strategy changed.
5
Risk response
An identified risk occurs and the agreed response requires a baseline change to implement.
6
Technology and vendor shifts
A supplier discontinues a component or a platform version reaches end of support.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
425

## Slide 426
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
The Four Change Request Types — Know These Cold
Type | Definition | Trigger | Example
Corrective action | Realigns the performance of the project work with the project management plan | Performance has already deviated from plan | Add a second tester because the defect backlog is growing
Preventive action | Ensures the future performance of project work aligns with the plan | A deviation is forecast but has not yet occurred | Book contractor capacity now because a resource gap is predicted
Defect repair | Modifies a nonconforming product, deliverable or component | A deliverable failed inspection or test | Rework a module that failed the acceptance test
Update | Modifies formally controlled project documents or a baseline | Approved content changes require the record to change | Revise the scope baseline after an approved scope addition
Corrective = fix the present. Preventive = protect the future. Defect repair = fix the product. Update = fix the document or baseline.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
426

## Slide 427
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Corrective vs Preventive Action
Corrective action
Reactive — the variance already happened
Triggered by measured performance that is already off plan
Aim is to bring future performance back onto the approved baseline
Usually discovered through variance analysis or an EVM index below 1.0
Example: CPI has dropped to 0.85, so rescope low-value work
Does not by itself change the baseline — it changes how work is done
Preventive action
Proactive — the variance is only forecast
Triggered by a forecast, trend or identified risk, not by actual damage
Aim is to stop the deviation ever appearing in the actuals
Usually discovered through trend analysis, risk review or reserve analysis
Example: cross-train a second engineer before the specialist goes on leave
Closely related to risk response — prevention is mitigation applied to work
Exam cue: 'has fallen behind' or 'is over budget' points to corrective action. 'May', 'is expected to', or 'trend suggests' points to preventive action.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
427

## Slide 428
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
The Change Request Flow
STEP 1
Identify and raise
Anyone may raise a change; it must be written, not verbal.
STEP 2
Log the request
Record it in the change log with a unique ID, requester and date.
STEP 3
Assess the impact
Analyse impact on scope, schedule, cost, quality, risk and resources.
STEP 4
Decide
The PM, CCB or sponsor approves, rejects or defers per the approval levels.
STEP 5
Communicate
Tell the requester and affected stakeholders the decision and the reason.
STEP 6
Implement and update
Execute the approved change, update baselines and all documents.
Rejected changes are still logged. The change log is the audit trail proving that governance was followed — an exam favourite.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
428

## Slide 429
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Change Control Systems and the Change Control Board
1
Change control system
The forms, tracking methods, processes and approval levels required to authorise or reject a requested change.
2
Change control board (CCB)
A formally chartered group that reviews, evaluates, approves, defers or rejects changes and records decisions.
3
Approval levels
The change management plan defines what the PM may approve alone and what must escalate to the CCB or the sponsor.
4
Configuration management system
Controls the product itself — versions, specifications and physical characteristics.
5
Change log
The register of every request with status, decision, decision date and rationale; shared with stakeholders.
6
Emergency change procedure
A documented fast path for urgent changes, with retrospective CCB ratification.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
429

## Slide 430
EXAM FOCUS · CHANGE CONTROL
Exam Traps — Integrated Change Control
IF THE QUESTION SAYS
A stakeholder asks you to add a small feature; there is budget available
THE BEST ANSWER IS
Do not agree on the spot. Assess the impact and submit a change request through integrated change control.
IF THE QUESTION SAYS
A change was already implemented by a team member without approval
THE BEST ANSWER IS
Determine the impact first, then process it through change control and update the affected documents and baselines.
IF THE QUESTION SAYS
The sponsor demands an urgent change during a steering meeting
THE BEST ANSWER IS
Analyse impact on all baselines and present options; the CCB — not the sponsor's verbal instruction — authorises the baseline change.
IF THE QUESTION SAYS
A change request is rejected
THE BEST ANSWER IS
Record the rejection and rationale in the change log and communicate it to the requester — rejected changes are still documented.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
430

## Slide 431
ECO BUSINESS ENV T3 · MANAGE AND CONTROL CHANGES
Agile Consideration — Handling Change
1
Change is expected
Adaptive approaches assume requirements will change; the process is designed to absorb rather than resist change.
2
Product Owner authority
The Product Owner holds autocratic decision-making power over scope — others must convince them.
3
Backlog is the change log
New or updated features enter the Product Backlog; updated user stories join the next Sprint Backlog.
4
Sprint scope is protected
Change is welcomed between iterations; the current sprint's committed scope stays fixed.
5
Scope evolves in layers
Roadmap to release backlog to iteration backlog — each layer reprioritised as needs are learned.
6
Validate against feedback
Check user stories and the Definition of Done against customer feedback and product requirements.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
431

## Slide 432
ECO PEOPLE T4 · ENGAGE STAKEHOLDERS
Monitor Stakeholder Engagement — ITTO
Purpose: monitor project stakeholder relationships and tailor strategies to engage stakeholders through modification of engagement strategies and plans.
INPUTS
Project management plan: resource, communications and stakeholder engagement management plans
Project documents: issue log, lessons learned register
Project communications
Risk register and stakeholder register
Work performance data
Enterprise environmental factors and OPAs
TOOLS & TECHNIQUES
Data analysis: alternatives analysis, root cause analysis, stakeholder engagement assessment matrix
Decision making: multicriteria decision analysis, voting
Data representation: stakeholder engagement assessment matrix
Communication skills: feedback and presentations
Interpersonal and team skills: active listening, cultural awareness, leadership, networking
Meetings
OUTPUTS
Work performance information
Change requests
Project management plan updates
Project document updates: issue log, lessons learned register, stakeholder register, risk register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
432

## Slide 433
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Validate Scope — ITTO
Purpose: formalise acceptance of completed deliverables. Control Quality verifies correctness internally; Validate Scope obtains the customer's formal acceptance.
INPUTS
Project management plan: scope management plan, requirements management plan, scope baseline
Project documents: lessons learned register, quality reports, requirements documentation
Requirements traceability matrix
Verified deliverables (output of Control Quality)
Work performance data
TOOLS & TECHNIQUES
Inspection: measuring, examining and validating deliverables against acceptance criteria
Walkthroughs, reviews, audits and product demonstrations
Decision making: voting to reach agreement on acceptance
User acceptance testing (UAT)
OUTPUTS
Accepted deliverables (signed off by the customer)
Work performance information
Change requests (for deliverables not accepted)
Project document updates: lessons learned register, requirements documentation, traceability matrix
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
433

## Slide 434
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Control Quality vs Validate Scope
Control Quality
Internal — is it built right?
Performed by the project team and quality function, usually before handover
Checks the deliverable against the quality requirements and specifications
Uses inspection, testing, measurement and the seven basic quality tools
Key output: verified deliverables plus quality control measurements
Nonconformance produces a defect repair change request
Validate Scope
External — is it the right thing?
Performed with the customer or sponsor, taking verified deliverables as input
Checks the deliverable against the agreed acceptance criteria
Uses inspection, demonstration, walkthroughs, UAT and formal sign-off
Key output: accepted deliverables recorded as formal acceptance
Non-acceptance produces a change request, not a silent rework
Sequence to remember: Control Quality produces verified deliverables, which become the input to Validate Scope, which produces accepted deliverables, which become the input to Close Project or Phase.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
434

## Slide 435
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Acceptance Criteria, Definition of Ready, Definition of Done
Concept | Scope of application | Who owns it | What it prevents
Acceptance criteria | Specific to one requirement, user story or deliverable | Product Owner / customer, agreed with the team | Arguing about 'finished' after the work is already built
Definition of Ready (DoR) | Applies to every item before it may enter an iteration | The team, agreed with the Product Owner | Starting work on an item too vague to estimate or complete
Definition of Done (DoD) | Applies to every increment the team produces | The whole delivery team | Hidden work — untested, undocumented, undeployed 'done'
Requirements traceability matrix | Links every requirement to its deliverable, test and acceptance | Project manager / business analyst | Requirements silently dropped between plan and delivery
Acceptance criteria may legitimately be modified during the life cycle — but only through the change control process.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
435

## Slide 436
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Control Scope — ITTO
Purpose: monitor the status of the project and product scope and manage changes to the scope baseline — this is where scope creep is caught.
INPUTS
Project management plan: scope, requirements and change management plans; scope and performance measurement baselines
Project documents: lessons learned register, requirements documentation, traceability matrix
Work performance data
Organizational process assets
TOOLS & TECHNIQUES
Data analysis: variance analysis comparing actual to baseline
Data analysis: trend analysis of scope growth over time
Inspection of the delivered scope against the WBS
Requirements traceability review
OUTPUTS
Work performance information (scope variance)
Change requests including corrective and preventive action
Project management plan updates: scope baseline, schedule baseline, cost baseline
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
436

## Slide 437
ECO PROCESS T2 · DEVELOP AND MANAGE PROJECT SCOPE
Scope Creep vs Gold Plating
Scope creep
Uncontrolled expansion, usually customer-driven
Requirements added without corresponding schedule, cost or resource change
Each addition feels small — the cumulative effect destroys the baseline
Root causes: weak scope baseline, no change control, eager-to-please PM
Control: a documented scope baseline plus enforced integrated change control
Detect it with trend analysis on requirement count and story point totals
Gold plating
Unrequested extras, usually team-driven
The team adds features the customer never asked for and will not pay for
Consumes budget and introduces risk with zero measured business value
Root causes: engineer enthusiasm, misread of what 'delighting the customer' means
Control: Definition of Done tied strictly to acceptance criteria
PMI's position is unambiguous — gold plating is never acceptable
Both are scope control failures. The response is the same: bring it back to the baseline, and route any genuine addition through a change request with a full impact assessment.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
437

## Slide 438
ECO BUSINESS ENV T8 · EVALUATE EXTERNAL BUSINESS ENVIRONMENT CHANGES
Monitor the External Business Environment
1
Change cuts both ways
External change brings opportunities to add or extend value, not only threats to defend against.
2
Survey the environment
Track regulatory, technology, geopolitical and market changes on a defined cadence, not ad hoc.
3
Stay vigilant for threats
A competitor launch or a regulation can invalidate the business case even while delivery is green.
4
Update the risk register
New external factors become new risks with new probability, impact and threshold values.
5
Reprioritise scope
Assess the impact on scope or backlog and reprioritise so the project still delivers the intended value.
6
Use structured tools
PESTLE, SWOT and horizon scanning give the scan discipline rather than relying on the PM's news feed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
438

## Slide 439
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Control Schedule — ITTO
Purpose: monitor the status of the project to update the schedule and manage changes to the schedule baseline. Determining the current status and influencing the factors that create schedule change are the core work.
INPUTS
Project management plan: schedule management plan, schedule baseline, scope baseline, performance measurement baseline
Project documents: lessons learned register, project calendars, project schedule
Resource calendars and schedule data
Work performance data
Organizational process assets
TOOLS & TECHNIQUES
Data analysis: earned value analysis, iteration burndown chart, performance reviews, trend analysis, variance analysis, what-if scenario analysis
Critical path method
Project management information system (PMIS)
Resource optimisation
Leads and lags
Schedule compression: crashing and fast tracking
OUTPUTS
Work performance information: SV and SPI
Schedule forecasts
Change requests
Project management plan updates: schedule baseline, cost baseline, performance measurement baseline
Project document updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
439

## Slide 440
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Earned Value Management
EVM answers three questions with one integrated set of numbers: where should we be, where are we, and what did it cost?
Planned Value (PV)
The authorised budget assigned to the work scheduled to be complete by now.
Earned Value (EV)
The measure of work actually performed, expressed in the budget authorised for that work.
Actual Cost (AC)
The realised cost actually incurred for the work performed in the period measured.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
440

## Slide 441
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
EVM Variable Glossary
Symbol | Name | Meaning in plain language | Units
PV | Planned Value | The value of work you planned to have finished by the measurement date | Currency
EV | Earned Value | The budgeted value of the work you actually finished | Currency
AC | Actual Cost | What you actually spent to finish that work | Currency
BAC | Budget at Completion | The total approved budget for the whole project | Currency
CV | Cost Variance | How much more or less you spent than the work was worth | Currency
SV | Schedule Variance | How much work you are ahead of or behind, valued in money | Currency
CPI | Cost Performance Index | Value earned per dollar spent — efficiency of spend | Ratio
SPI | Schedule Performance Index | Rate of progress against the planned rate | Ratio
EAC | Estimate at Completion | Forecast total cost when the project finishes | Currency
ETC | Estimate to Complete | Forecast cost of the remaining work only | Currency
VAC | Variance at Completion | Forecast overrun or underrun against BAC | Currency
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
441

## Slide 442
KEY FORMULAS · VARIANCE & INDEX
EVM Formulas — Variance and Index
Cost Variance
CV = EV - AC
Negative means you have spent more than the work was worth. Positive is good.
Schedule Variance
SV = EV - PV
Negative means less work is done than planned. Reaches zero at project end.
Cost Performance Index
CPI = EV / AC
Above 1.0 is under budget; below 1.0 means you get less than a dollar per dollar.
Schedule Performance Index
SPI = EV / PV
Above 1.0 is ahead of schedule; below 1.0 means work is arriving slower than planned.
Percent Complete
EV / BAC
The proportion of total authorised budget that has been earned so far.
Memory aid: every variance is EV minus something and every index is EV divided by something. If the answer is negative or below 1.0, it is bad.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
442

## Slide 443
KEY FORMULAS · FORECASTING
EVM Formulas — Forecasting
EAC — typical variance
EAC = BAC / CPI
Use when current cost performance is expected to continue for the rest of the project.
EAC — atypical variance
EAC = AC + (BAC - EV)
Use when the variance was a one-off and remaining work will run at the budgeted rate.
EAC — schedule constrained
EAC = AC + (BAC-EV)/(CPI x SPI)
Use when the remaining work must absorb both the cost and the schedule performance.
Estimate to Complete
ETC = EAC - AC
The forecast cost of the work that still remains after money already spent.
Variance at Completion
VAC = BAC - EAC
Forecast overrun (negative) or underrun (positive) measured at project completion.
Read the question for the phrase that selects the formula: 'rate will continue' = BAC/CPI; 'atypical / one-off' = AC + BAC - EV; 'must meet the deadline too' = the CPI x SPI form.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
443

## Slide 444
KEY FORMULAS · TCPI
EVM Formulas — To-Complete Performance Index
TCPI against BAC
TCPI = (BAC-EV)/(BAC-AC)
The cost efficiency the remaining work must achieve to finish within the original budget.
TCPI against EAC
TCPI = (BAC-EV)/(EAC-AC)
Use once the original budget is no longer achievable and a new EAC has been approved.
Interpretation above 1.0
TCPI > 1.0
You must perform better than you have been performing — the target is harder than the past.
Interpretation below 1.0
TCPI < 1.0
You may perform slightly worse than before and still hit the target — you have slack.
TCPI and CPI move in opposite directions. A CPI of 0.80 with plenty of work left implies a TCPI well above 1.0 — a warning that recovery is unrealistic.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
444

## Slide 445
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Interpreting the Indices — Above 1.0 vs Below 1.0
1
CPI above 1.0
Cost efficient. You earned more value than you spent. Confirm it is real progress, not under-reported costs.
2
CPI below 1.0
Cost inefficient. Every dollar buys less than a dollar of value. Investigate rate, rework and scope leakage.
3
SPI above 1.0
Ahead of plan. Check whether easy work was pulled forward, leaving the hard work still ahead.
4
SPI below 1.0
Behind plan. Look at the critical path first — non-critical lateness may not delay the project at all.
5
CPI low, SPI high
You are buying speed with money — typically overtime or extra resources. Confirm the trade was authorised.
6
CPI high, SPI low
You are underspending because too little work is happening — usually a resource or blocker problem, not thrift.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
445

## Slide 446
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Worked Example — Ten Printer Drivers
STEP 1
The task
Develop and install ten printer drivers, one per week, over ten weeks.
STEP 2
The budget
BAC is $100,000 — exactly $10,000 per printer driver.
STEP 3
Status at week 5
Four drivers are developed and installed; $47,500 has been spent.
STEP 4
PV = $50,000
Five drivers were scheduled by week 5: 5 x $10,000 of planned value.
STEP 5
EV = $40,000
Four drivers are genuinely complete: 4 x $10,000 of earned value.
STEP 6
AC = $47,500
The actual cost incurred to date, taken straight from the ledger.
Golden rule: EV is always the budgeted value of completed work — count the deliverables finished, then multiply by their budget. Never use actual cost to compute EV.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
446

## Slide 447
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Worked Example — Running the Numbers
Cost Variance
CV = 40,000-47,500 = -7,500
Negative: $7,500 more was spent than the completed work was actually worth.
Schedule Variance
SV = 40,000-50,000 = -10,000
Negative: one full driver's worth of work — $10,000 — is behind schedule.
Cost Performance Index
CPI = 40,000/47,500 = 0.84
Only 84 cents of value is earned per dollar spent — a serious cost problem.
Schedule Performance Index
SPI = 40,000/50,000 = 0.80
Work is arriving at 80% of the planned rate — four drivers where five were due.
Estimate at Completion
EAC = 100,000/0.84 = 118,750
If this rate continues the project finishes at $118,750, not $100,000.
Follow through: ETC = 118,750 - 47,500 = $71,250 still to spend, and VAC = 100,000 - 118,750 = -$18,750, a forecast overrun of $18,750.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
447

## Slide 448
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
The EVM S-Curve — PV, EV and AC Over Ten Weeks
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
Planned Value (PV) | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100
Earned Value (EV) | 9 | 18 | 27 | 34 | 40
Actual Cost (AC) | 11 | 22 | 32 | 40 | 47.5
WHAT IT TELLS YOU
PV is the straight planned baseline — $10K of value per week for ten weeks.
EV sits below PV, so the project is behind schedule (negative SV).
AC sits above EV, so the project is over budget (negative CV).
The gap between AC and EV widens each week — the trend, not the point, is the warning.
Extrapolating AC at the current CPI gives an EAC of roughly $119K against a $100K BAC.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
448

## Slide 449
ECO PROCESS T9 · EVALUATE PROJECT STATUS
CPI and SPI Trend — Is the Project Recovering?
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
CPI | 0.82 | 0.82 | 0.84 | 0.85 | 0.84 | 0.87 | 0.9 | 0.93
SPI | 0.9 | 0.88 | 0.84 | 0.85 | 0.8 | 0.83 | 0.88 | 0.91
WHAT IT TELLS YOU
A single index reading is a snapshot; the trend line tells you whether corrective action worked.
Both indices bottom out around week 5, the point at which corrective action was taken.
The recovery from week 6 onward suggests the added resources are earning value.
Neither index has yet reached 1.0, so the project is still both late and over budget.
Report the trend to the sponsor — 'improving but not recovered' is a defensible status.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
449

## Slide 450
EXAM FOCUS · EVM
Exam Traps — Earned Value
IF THE QUESTION SAYS
You are given AC and percent complete and asked for EV
THE BEST ANSWER IS
EV = BAC x percent complete. Actual cost never enters the earned value calculation.
IF THE QUESTION SAYS
CPI is 0.9 and the question says the variance was atypical
THE BEST ANSWER IS
Use EAC = AC + (BAC - EV). The atypical wording rules out the BAC/CPI form.
IF THE QUESTION SAYS
SPI is 0.85 but the project manager says the deadline is safe
THE BEST ANSWER IS
Check the critical path. SPI aggregates all work, so non-critical lateness can leave the finish date intact.
IF THE QUESTION SAYS
The question asks what to do about a negative CV of significant size
THE BEST ANSWER IS
Perform variance and root cause analysis first, then raise a change request for corrective action.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
450

## Slide 451
ECO PROCESS T8 · PLAN AND MANAGE SCHEDULE
Schedule Compression — Crashing vs Fast Tracking
Crashing
Buy time with money
Shortens duration for the least incremental cost by adding resources
Typical actions: approve overtime, add staff, pay a supplier to expedite
Works only on activities that lie on the critical path
Always increases cost and may increase risk through onboarding and rework
Does not always produce a viable alternative — some work cannot be parallelised
Fast tracking
Buy time with risk
Performs activities or phases in parallel that were planned in sequence
Typical action: start construction before the design is fully approved
Costs nothing directly but consumes contingency through rework
May result in rework, increased risk and ultimately increased cost
Only applies where the dependency is discretionary, not mandatory
Both techniques apply to the critical path only. Try fast tracking first if the budget is fixed and the dependencies are discretionary; crash first if the risk appetite is low and money is available.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
451

## Slide 452
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Control Costs — ITTO
Purpose: monitor the status of the project to update project costs and manage changes to the cost baseline. Any increase over authorised funding requires a change request.
INPUTS
Project management plan: cost management plan, cost baseline, performance measurement baseline
Project documents: lessons learned register
Project funding requirements
Work performance data
Organizational process assets
TOOLS & TECHNIQUES
Expert judgement
Data analysis: earned value analysis, variance analysis, trend analysis, reserve analysis
To-complete performance index (TCPI)
Project management information system (PMIS)
OUTPUTS
Work performance information: CV, CPI, EAC, VAC, TCPI
Cost forecasts (EAC and ETC)
Change requests
Project management plan updates: cost baseline, performance measurement baseline
Project document updates: assumption log, basis of estimates, cost estimates, risk register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
452

## Slide 453
ECO PROCESS T6 · PLAN AND MANAGE FINANCE
Reserve Analysis in Control
1
Contingency reserve
Funds and time set aside for identified risks — the 'known unknowns'. The PM controls and draws on it.
2
Management reserve
Held for unidentified risk — the 'unknown unknowns'. Only management releases it, and it sits outside the baseline.
3
Burn rate check
Compare reserve consumed against risk retired. Burning 60% of reserve at 20% complete is a red flag.
4
Release the surplus
When a risk passes without occurring, release its contingency back — do not silently absorb it as slack.
5
Cost baseline vs budget
Cost baseline = estimates plus contingency reserve. Project budget = cost baseline plus management reserve.
6
Reserve in adaptive work
Agile teams reserve capacity rather than money — a percentage of each sprint held for emergent work.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
453

## Slide 454
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Control Quality — ITTO
Purpose: monitor and record the results of executing quality activities to assess performance and ensure the project outputs are complete, correct and meet customer expectations.
INPUTS
Project management plan: quality management plan
Project documents: lessons learned register, quality metrics, test and evaluation documents
Approved change requests
Deliverables
Work performance data
Enterprise environmental factors and OPAs
TOOLS & TECHNIQUES
Data gathering: checklists, check sheets, statistical sampling, questionnaires and surveys
Data analysis: performance reviews, root cause analysis
Inspection and testing / product evaluations
Data representation: cause-and-effect diagrams, control charts, histograms, scatter diagrams, Pareto charts
Meetings: approved change request review, retrospectives
OUTPUTS
Quality control measurements
Verified deliverables
Work performance information
Change requests (defect repair)
Project management plan updates
Project document updates: issue log, lessons learned register, risk register, test documents
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
454

## Slide 455
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
What Quality Control Does
1
Assess project approaches
Judge whether the way the work is being done can produce a conforming result at all.
2
Evaluate deliverables
Inspect and test the product against its quality requirements before it reaches the customer.
3
Review processes
Evaluate the quality of project activities and processes through structured reviews and audits.
4
Detect and prevent
Focus on both detecting defects that exist and preventing the causes that keep producing them.
5
Measure, do not guess
Quality control is quantitative — the seven basic tools turn opinion into evidence.
6
Feed improvement
Every defect analysed is a candidate process improvement, not simply a task to rework.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
455

## Slide 456
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Prevention vs Inspection — and the Cost of Quality
Cost of conformance
Money spent to prevent failure
Prevention costs: training, documented process, right equipment, time to do it right
Appraisal costs: testing, destructive test loss, inspection and audit effort
Spent proactively during the project, inside the approved budget
PMI's position: prevention is preferred over inspection — quality is planned in
A dollar spent on prevention typically saves many dollars of failure cost
Cost of nonconformance
Money spent because of failure
Internal failure costs: rework and scrap found before the customer sees it
External failure costs: liabilities, warranty work, lost business, reputation
Spent reactively, usually outside the plan and outside the contingency estimate
External failure is by far the most expensive category and the hardest to reverse
Rises exponentially the later in the life cycle the defect is discovered
Quality is planned in, not inspected in. Inspection keeps defects away from the customer but does nothing to stop the process producing them — that requires prevention and root cause analysis.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
456

## Slide 457
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Quality Audits
1
What it is
A structured, independent review to determine whether project activities comply with organisational and project policies.
2
When it happens
May be scheduled at defined milestones or conducted ad hoc when performance triggers concern.
3
Quality policy
Confirms the quality management policy is understood and genuinely applied, not merely published.
4
Information and methods
Examines how quality information is collected and which analytical methods are used on it.
5
Cost of quality
Reviews whether prevention, appraisal and failure costs are tracked and are trending in the right direction.
6
Process design
Assesses whether the quality processes themselves are fit for the complexity and risk of this project.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
457

## Slide 458
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
The Seven Basic Quality Tools
Tool | What it shows | Use it when | Key reading
Check sheet | Tally of occurrences by category, collected at the point of work | You need to gather defect data consistently in the first place | Which category is being tallied most often
Histogram | Distribution and spread of a measured variable across bins | You want to see the shape, centre and spread of the data | Skew, outliers and whether the process is centred on target
Pareto chart | Ranked bar chart of defect categories with a cumulative line | You must decide which few problems to attack first | The 80/20 rule — roughly 80% of effects from 20% of causes
Cause-and-effect (fishbone) | Candidate causes grouped into categories around one problem | You need to explore why a defect keeps recurring | Which branch holds the most plausible root causes
Scatter diagram | Correlation between two variables plotted against each other | You suspect one factor drives a quality defect | Direction and tightness of the relationship, not causation
Control chart | A process plotted over time against mean, UCL and LCL | You must judge whether a process is stable and predictable | Points outside limits or non-random patterns within them
Flowchart | The sequence of steps and decision points in a process | You need to see where handoffs, loops and waste occur | Rework loops, unnecessary approvals and unclear ownership
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
458

## Slide 459
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
The Control Quality Analysis Sequence
STEP 1
Collect
Use check sheets to gather defect data consistently at the source.
STEP 2
Distribute
Plot the data on a histogram to see spread, centre and outliers.
STEP 3
Prioritise
Build a Pareto chart to find the vital few categories driving the pain.
STEP 4
Diagnose
Run cause-and-effect analysis on the top categories to find root causes.
STEP 5
Correlate
Use a scatter diagram to test whether a suspected factor really drives the defect.
STEP 6
Monitor
Track the fixed process on a control chart to confirm the improvement holds.
This sequence turns raw complaints into a defensible improvement case. Skipping straight to a solution without the Pareto and root cause steps is the most common quality mistake — and a common exam distractor.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
459

## Slide 460
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Pareto Chart — Defect Categories on a Software Release
Chart: 
| Requirements gaps | Integration errors | UI defects | Data migration | Performance | Documentation
Defect count | 58 | 34 | 21 | 12 | 7 | 4
WHAT IT TELLS YOU
The two leading categories account for roughly 66% of all defects raised.
The 80/20 rule says fix the vital few, not the trivial many — start left.
Requirements gaps are an upstream failure; fixing them prevents downstream rework.
The long tail on the right rarely justifies dedicated corrective action.
Rebuild the chart after the fix — the ranking should visibly change.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
460

## Slide 461
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Histogram — Defect Resolution Time Distribution
Chart: 
| 0-2 days | 3-5 days | 6-8 days | 9-11 days | 12-14 days | 15+ days
Number of defects | 12 | 31 | 24 | 15 | 9 | 21
WHAT IT TELLS YOU
The histogram shows shape and spread; unlike Pareto it is not ranked by size.
The peak at 3-5 days is the typical resolution time for routine defects.
The second cluster at 15+ days is a warning of a distinct second population.
That long tail is usually a different root cause — escalated or vendor-dependent items.
Investigate the tail separately; averaging the two populations hides both problems.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
461

## Slide 462
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Control Chart — Is the Process In Control?
Chart: 
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Measured value | 50 | 53 | 48 | 51 | 49 | 52 | 54 | 55 | 56 | 57 | 58 | 66
Mean | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
Upper control limit | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62 | 62
Lower control limit | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
WHAT IT TELLS YOU
Control limits are set by the process itself (usually plus or minus three sigma).
Specification limits come from the customer — a process can be in control and still fail spec.
Point 12 breaches the UCL: an assignable cause that must be investigated.
Points 5 to 11 rise for seven consecutive readings — the rule of seven flags a trend.
A process is out of control if a point breaches a limit OR shows a non-random pattern.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
462

## Slide 463
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Common Cause vs Assignable (Special) Cause
Common cause variation
The noise the process always has
Natural, random variation inherent in the way the process is designed
Produces points that fall randomly within the upper and lower control limits
Present all the time — it is the process behaving exactly as built
Reducing it requires redesigning the process, which is a management decision
Reacting to individual common-cause points is 'tampering' and increases variation
Assignable cause variation
A signal that something changed
A specific, identifiable event that is not part of normal process behaviour
Produces a point outside the control limits or a non-random pattern within them
Examples: a new supplier batch, an untrained operator, a changed tool setting
Must be investigated and eliminated — this is where corrective action belongs
The rule of seven catches it even when every point is still inside the limits
Exam cue: 'a point outside the control limits', 'seven consecutive points rising', or 'a sudden shift' all mean assignable cause — investigate. Random scatter within limits means leave it alone.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
463

## Slide 464
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Scatter Diagram — Correlation Between Two Variables
Chart: 
| 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80
Defects found | 4 | 6 | 9 | 11 | 15 | 18 | 22 | 27
Overtime hours worked | 5 | 8 | 11 | 16 | 19 | 24 | 29 | 35
WHAT IT TELLS YOU
A scatter diagram shows the relationship between two variables on two axes.
Here defect count rises steadily with overtime hours — a positive correlation.
Tight clustering along a line implies a strong relationship worth acting on.
Correlation is not causation — confirm with root cause analysis before acting.
Use it to test a hypothesis produced by a fishbone diagram, not to generate one.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
464

## Slide 465
ECO PROCESS T7 · PLAN AND OPTIMIZE QUALITY OF PRODUCTS/DELIVERABLES
Statistical Sampling and Inspection
1
Why sample
Testing every unit is often impossible or destructive; a valid sample infers population quality at a fraction of the cost.
2
Sample size and frequency
Both are determined during Plan Quality Management and documented in the quality management plan.
3
Attribute sampling
The result is binary — the unit conforms or it does not. Used for pass/fail inspection.
4
Variable sampling
The result is measured on a continuous scale, which is what makes control charts possible.
5
Tolerance vs control limit
Tolerance is the customer's acceptable range; control limits describe the process's own behaviour.
6
Inspection outcome
Inspection produces verified deliverables and, where the unit fails, a defect repair change request.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
465

## Slide 466
ECO PROCESS T4 · PLAN AND MANAGE RESOURCES
Control Resources — ITTO
Purpose: ensure the physical resources assigned to the project are available as planned, and monitor planned versus actual utilisation, taking corrective action where they diverge.
INPUTS
Project management plan: resource management plan
Project documents: issue log, lessons learned register, physical resource assignments, project schedule, resource breakdown structure, resource requirements, risk register
Work performance data
Agreements
Organizational process assets
TOOLS & TECHNIQUES
Data analysis: alternatives analysis, cost-benefit analysis, performance reviews, trend analysis
Problem solving
Interpersonal and team skills: negotiation, influencing
Project management information system (PMIS)
OUTPUTS
Work performance information
Change requests
Project management plan updates: resource management plan, schedule baseline, cost baseline
Project document updates: assumption log, issue log, lessons learned register, resource breakdown structure, risk register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
466

## Slide 467
ECO PEOPLE T8 · PLAN AND MANAGE COMMUNICATION
Monitor Communications — ITTO
Purpose: ensure the information needs of the project and its stakeholders are met — the right information, to the right people, in the right format, at the right time.
INPUTS
Project management plan: resource, communications and stakeholder engagement management plans
Project documents: issue log, lessons learned register, project communications
Work performance data
Enterprise environmental factors and OPAs
TOOLS & TECHNIQUES
Expert judgement on communication effectiveness
Project management information system (PMIS)
Data representation: stakeholder engagement assessment matrix
Interpersonal and team skills: observation and conversation
Meetings including retrospectives and status reviews
OUTPUTS
Work performance information
Change requests
Project management plan updates: communications management plan, stakeholder engagement plan
Project document updates: issue log, lessons learned register, stakeholder register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
467

## Slide 468
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Monitor Risks — ITTO
Purpose: monitor implementation of agreed risk responses, track identified risks, identify and analyse new risks, and evaluate risk process effectiveness throughout the project.
INPUTS
Project management plan: risk management plan
Project documents: issue log, lessons learned register, risk register, risk report
Work performance data
Work performance reports
TOOLS & TECHNIQUES
Data analysis: technical performance analysis, reserve analysis
Audits: risk audits examining risk process effectiveness
Meetings: risk reviews as a standing agenda item
Risk reassessment and reprioritisation
OUTPUTS
Work performance information
Change requests including corrective and preventive action
Project management plan updates
Project document updates: assumption log, issue log, lessons learned register, risk register, risk report
Organizational process assets updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
468

## Slide 469
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Monitor Risks — What You Are Actually Doing
1
Enable decisions
Give decision-makers current information on overall risk exposure and on the individual risks that matter.
2
Track status continuously
Monitor each risk's status, probability and impact — all three change as the project moves.
3
Identify new risks
New risks emerge from every change, every phase gate and every shift in the external environment.
4
Reassess current risks
Re-score existing risks; yesterday's low probability risk may now be nearly certain.
5
Close outdated risks
Retire risks whose window has passed and release their contingency reserve back to the project.
6
Improve the process
Risk audits ask whether the risk process itself is working, not just whether individual risks are managed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
469

## Slide 470
ECO BUSINESS ENV T4 · REMOVE IMPEDIMENTS AND MANAGE ISSUES
When a Risk Becomes an Issue
Risk
A future uncertain event
Has not happened yet; described with a probability and an impact
Lives in the risk register with an owner and an agreed response strategy
Managed proactively — avoid, transfer, mitigate, accept, escalate
Funded from the contingency reserve if it is an identified risk
Language cue: 'may', 'could', 'if this occurs'
Issue
A present certain condition
Has already happened and is affecting the project right now
Lives in the issue log with an owner, an action and a target resolution date
Managed reactively — resolve, escalate, or accept a workaround
Consumes real budget and schedule, not contingency probability
Language cue: 'has occurred', 'is blocking', 'the team cannot proceed'
ECO Business Environment T4 explicitly requires you to recognise when a risk becomes an issue. The moment it occurs, move it from the risk register to the issue log — the response strategy becomes an action plan.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
470

## Slide 471
ECO BUSINESS ENV T4 · REMOVE IMPEDIMENTS AND MANAGE ISSUES
Issue and Impediment Resolution
STEP 1
Capture
Log the issue with a clear statement of impact, owner and raise date.
STEP 2
Evaluate impact
Quantify the effect on schedule, cost, quality and the team's flow.
STEP 3
Prioritise
Rank against other impediments; highlight the ones blocking the critical path.
STEP 4
Intervene
Apply an intervention strategy within your authority to remove or minimise it.
STEP 5
Escalate if needed
Use the governance escalation path when the block is outside your control.
STEP 6
Reassess
Continually review open items to confirm blockers are actually being addressed.
An impediment that stays open past its target date is itself a risk. Ageing reports on the issue log are one of the most useful leading indicators a project manager has.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
471

## Slide 472
ECO BUSINESS ENV T4 · REMOVE IMPEDIMENTS AND MANAGE ISSUES
Prioritising Impediments — Impact vs Ability to Resolve
Escalate immediately
High impact, outside your authority. Use the governance escalation path with a clear ask, a deadline and the consequence of inaction.
Remove now
High impact and within your control. Swarm the team on it today; this is the highest-value use of the project manager's time.
Monitor and log
Low impact, outside your control. Keep it visible on the issue log and watch for it growing rather than spending effort now.
Delegate and track
Low impact and resolvable locally. Assign an owner and a due date; do not consume leadership attention on it.
Ability to resolve within the team
Impact on delivery
Impediment removal is the project manager's and scrum master's signature servant-leadership act. Speed matters more than elegance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
472

## Slide 473
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Sustainability and Security Risk Monitoring (ECO 2026)
1
IT security risk
The ECO explicitly names poor IT security as a risk register entry — monitor vulnerabilities, access and vendor posture.
2
Security response execution
Executing the risk management plan includes delivering security risk responses, not merely logging them.
3
Sustainability risk
Environmental, energy and lifecycle impacts of the deliverable are now monitored risks with real thresholds.
4
Regulatory drift
Compliance obligations change mid-project; a control that was adequate at planning may not be at delivery.
5
Compliance measurement
Measure the extent to which the project is in compliance rather than assuming it is.
6
Communicate risk status
The ECO requires you to communicate the status of a risk's impact — silence is not a risk response.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
473

## Slide 474
ECO BUSINESS ENV T2 · PLAN AND MANAGE PROJECT COMPLIANCE
Manage Compliance During Control
1
Test and validate
Validate deliverables against compliance requirements continuously and at every phase end, not only at closure.
2
Identify approvers
Know which authorised stakeholders can sign a compliance acceptance before you need the signature.
3
Remediate early
Unresolved compliance issues cause timeline damage, cost overruns and increased risk exposure.
4
Early warning
A compliance review programme gives early warning of potential threats before an external auditor finds them.
5
Capture variances
Structured checks let you capture variances and take action while remediation is still cheap.
6
Analyse consequences
Document what noncompliance would actually cost — it is what unlocks the funding to fix it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
474

## Slide 475
ECO BUSINESS ENV T5 · PLAN AND MANAGE RISK
Agile Consideration — Risk and Team in Control
1
Risks as user stories
Risks are raised as user stories carrying probability and impact ratings so they compete for capacity.
2
Prioritised in the backlog
Risk stories are prioritised alongside value features — risk work becomes visible, funded work.
3
Retrospective as risk review
Each retrospective doubles as a risk reassessment for the coming iteration.
4
T-shaped teams
Agile teams prefer dedicated, T-shaped members — broad capability with one deep specialism.
5
Skills over roles
Specific job titles matter less than having every skill needed to complete the feature inside the team.
6
Osmotic communication
Co-located teams learn quickly by osmosis; distributed teams must engineer that flow deliberately.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
475

## Slide 476
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Control Procurements — ITTO
Purpose: manage procurement relationships, monitor contract performance, make changes and corrections as appropriate, and close out contracts correctly.
INPUTS
Project management plan: requirements, risk, procurement and change management plans; schedule baseline
Project documents: assumption log, lessons learned register, milestone list, quality reports, requirements documentation, risk register, stakeholder register
Agreements and procurement documentation
Approved change requests
Work performance data
TOOLS & TECHNIQUES
Expert judgement in contract administration and claims
Claims administration
Data analysis: performance reviews, earned value analysis, trend analysis
Inspection and audits
Procurement performance reviews
OUTPUTS
Closed procurements
Work performance information
Procurement documentation updates
Change requests
Project management plan updates: risk management plan, procurement management plan, schedule and cost baselines
Project document updates and OPA updates
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
476

## Slide 477
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Types of Contract Change
Change type | Definition | Typical trigger | Handling
Administrative change | Non-substantive change, usually to the contract administration method | New invoicing address, changed contract officer | Documented by the contracts function; no renegotiation
Contract modification | Substantive change to the contract requirements or product requirements | Approved scope change affecting the vendor's deliverable | Formal, signed by both parties, priced before work starts
Supplemental agreement | An additional agreement related to the contract but negotiated separately | Extra work outside the original statement of work | Negotiated as a separate instrument with its own terms
Constructive change | A change made by the buyer through action or inaction, not by formal order | Buyer directs extra work verbally, or delays an approval | Frequently disputed; the source of most claims
Termination | Ending the contract before completion, for cause or for convenience | Vendor default, or the buyer no longer needs the deliverable | Follows the termination clause; settlement of costs incurred
Constructive change is the exam's favourite: the buyer never issued a change order, but their behaviour effectively directed extra work — and they may still be liable for it.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
477

## Slide 478
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Managing Disputes and Contract Problems
1
Warranty
A promise, explicit or implied, that goods or services will meet a standard covering reliability, fitness for use and safety.
2
Waiver
A binding provision where one party forfeits a claim without the other becoming liable — waivers can be granted inadvertently.
3
Breach of contract
Failure to meet some or all obligations of a contract, which may entitle the other party to remedy or damages.
4
Work with the vendor first
Most contract problems are solved commercially with the supplier before they become legal ones.
5
Work with your organisation
Engage procurement, finance and functional departments; act within your documented threshold.
6
Get expert help early
Legal problems serious enough to cause project issues need specialist help before positions harden.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
478

## Slide 479
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Claims Administration and Dispute Escalation
STEP 1
Claim raised
A contested change or potential constructive change is formally asserted.
STEP 2
Document the facts
Assemble the evidence: correspondence, records, inspection results.
STEP 3
Negotiate
Settlement through direct negotiation is always the preferred route.
STEP 4
Mediation
A neutral third party helps the parties reach their own agreement.
STEP 5
Arbitration
The ADR method named in the contract; a neutral issues a binding decision.
STEP 6
Litigation
The last resort — slow, public, expensive and relationship-ending.
Claims usually arise from a lack of agreement on compensation for a change, or a lack of agreement that a change occurred at all. If unresolved, handle through the alternative dispute resolution method established in the contract.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
479

## Slide 480
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
The Contract Change Control System
1
Purpose
A system specifically dedicated to controlling changes to contracts and the resulting product requirements.
2
Relationship to ICC
May be a component of integrated change control or a separate organisational system, depending on the OPAs.
3
Documentation
Specifies exactly how a contract change is requested, priced, authorised and recorded.
4
Dispute resolution
Includes the dispute-resolution process and the ADR method that applies when the parties disagree.
5
Approval levels
Defines who may sign a contract change at each value band — rarely the project manager alone.
6
Audit trail
Every change instruction must be traceable to an authorised signature; verbal direction creates constructive change risk.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
480

## Slide 481
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Scaling agile
One Scrum team is a delivery method. Many teams on one product is an organisational design problem.
Coordination overhead
Dependencies between teams grow faster than team count — coordination becomes the constraint.
Shared definition of done
Multiple teams must agree what 'done' and 'integrated' mean or the increment never assembles.
Value stream focus
Scaling frameworks organise around products and value streams rather than functional silos.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
481

## Slide 482
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
eXtreme Programming (XP)
1
Five core values
Communication, Simplicity, Feedback, Respect and Courage — the behavioural foundation the practices rest on.
2
Four core activities
Coding, Testing, Listening and Designing — the only activities XP considers essential to producing software.
3
Whole team
Everyone needed to do the work sits within the team, including the on-site customer representative.
4
Planning game
Planning Poker on user stories: the team estimates, high and low estimators explain, and the team re-estimates to consensus.
5
Pair programming
Two developers on one workstation — continuous review that spreads knowledge and catches defects at the keystroke.
6
Test-driven development
Write the failing test first, then the code that passes it, then refactor — quality is built in.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
482

## Slide 483
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Feature Driven Development (FDD)
1
Feature teams
Small teams dedicated to delivering one client-valued feature at a time, rather than one technical layer.
2
Develop by feature
Work is decomposed into features small enough to be completed in about two weeks and demonstrated.
3
Individual class ownership
One named owner is responsible for each group of code, giving clear accountability for quality.
4
Domain object modelling
Sequence and context diagrams describe how the code interacts before it is written.
5
Inspections
Formal inspection of both the code and the result — FDD is more document-friendly than most agile methods.
6
Regular builds and CM
Configuration management maintains versions of every change; regular builds merge to the main branch.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
483

## Slide 484
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Crystal
1
Technologies change techniques
There is no one method — the right practices depend on the technology being used.
2
Cultures change norms
What works in one organisation's culture will not transplant unchanged into another.
3
Distances change communication
Co-location changes what communication mechanisms are necessary and sufficient.
4
Sized by team and criticality
Crystal grades a project by team size and criticality — Clear, Yellow, Orange, Red.
5
More governance when riskier
Larger and riskier projects need more governance; small teams need very little.
6
Agile favours the small
Because agile favours small teams, Crystal Clear and Crystal Yellow are the commonly used variants.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
484

## Slide 485
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Crystal Core Properties and Techniques
1
Frequent delivery
Ship working software to real users regularly — the single most important property in Crystal.
2
Reflective improvement
Reflection workshops — Crystal's name for the retrospective — adjust the method as you go.
3
Close communication
Osmotic communication in a shared space, plus easy access to expert users when questions arise.
4
Personal safety and focus
People must be able to speak up without fear, and have protected time to concentrate.
5
Methodology shaping
Deliberately tailor the method to this project and team rather than adopting a framework unmodified.
6
Blitz planning and Wideband Delphi
Group planning and group estimation where outliers explain before re-estimating.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
485

## Slide 486
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Dynamic Systems Development Method (DSDM)
1
The inverted triangle
DSDM is where the alternate constraints triangle comes from: time and cost are fixed, scope is variable.
2
Focus on the business need
Every decision is tested against whether it serves a real, agreed business need.
3
Build on firm foundations
Build incrementally, but only after enough foundation work to know the architecture is sound.
4
Never compromise quality
Quality is fixed alongside time and cost — scope is the only variable DSDM allows you to flex.
5
Timeboxing
Short fixed iterations, plus timeboxed spikes for research or problem solving that would otherwise expand indefinitely.
6
MoSCoW prioritisation
Must have, Should have, Could have, Won't have this time — the mechanism that makes scope flexible.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
486

## Slide 487
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
Scaling Frameworks Compared
Framework | Core idea | Coordination mechanism | Best fit
Scrum of Scrums | A representative from each team attends a shared stand-up | Program and ultimately portfolio Scrums report progress and cross-team blockers | A handful of teams on one product, minimal added structure
LeSS (Large Scale Scrum) | Large Scale Scrum is Scrum — treat many teams as one team | One Product Owner, one backlog, one sprint; transparency via Kanban and radiators | Several teams that can genuinely share a single product backlog
SAFe | Organise around value streams — the products and services themselves | Agile Release Trains: teams of teams pulling in anyone needed to deliver value | Large enterprises needing portfolio-level funding and governance alignment
Disciplined Agile | A decision framework rather than a prescribed method | Guided choices on lifecycle and practices per team context | Organisations with genuinely heterogeneous delivery contexts
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
487

## Slide 488
ECO PROCESS T1 · DEVELOP AN INTEGRATED PROJECT MANAGEMENT PLAN AND PLAN DELIVERY
LeSS vs SAFe
LeSS — Large Scale Scrum
Descale the organisation
Applies Scrum ways of working to programs and portfolios only when necessary
Empirical process control: update and improve the process as you go
Manages through transparency — Kanban boards and information radiators
'More with LeSS': more ownership with fewer roles, more learning with less defined process
Keeps one Product Owner and one product backlog across all teams
SAFe — Scaled Agile Framework
Add structure to the enterprise
Organises project teams around value streams — products or services, not functions
Agile Release Trains are teams of teams, adding anyone needed to deliver the value
Each value stream carries OKRs: written objectives and measurable key results
Uses human-centred design and Lean portfolio management above the team level
Prescriptive: defined roles, cadences and planning events at every level
LeSS reduces organisational structure to let Scrum work at scale; SAFe adds structure to connect agile teams to enterprise funding and governance. Neither is 'more agile' — they solve different constraints.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
488

## Slide 489
ECO PROCESS T9 · EVALUATE PROJECT STATUS
Iteration Burndown — Reading Adaptive Progress
Chart: 
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Ideal remaining | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 0
Actual remaining | 40 | 39 | 37 | 36 | 30 | 29 | 22 | 15 | 9 | 3
WHAT IT TELLS YOU
A burndown is the adaptive equivalent of an EVM S-curve — remaining work over time.
The flat stretch on days 2-4 signals a blocker, not slow work.
The steep drop from day 6 is typical of stories finishing in a batch at the end.
Ending above zero means committed scope was not completed — carry it to the next sprint.
Trend across several sprints matters more than any one sprint's line.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
489

## Slide 490
EXAM FOCUS · CONTROL
Exam Traps — Monitoring, Quality and Issues
IF THE QUESTION SAYS
A team member reports a problem that is already affecting the schedule
THE BEST ANSWER IS
It is an issue, not a risk. Record it in the issue log, assign an owner, and determine the impact before escalating.
IF THE QUESTION SAYS
Seven consecutive control chart points fall above the mean, all inside the limits
THE BEST ANSWER IS
The rule of seven signals an assignable cause. Investigate — do not wait for a point to breach the control limit.
IF THE QUESTION SAYS
A deliverable passed the team's testing but the customer refuses to sign
THE BEST ANSWER IS
Control Quality verified it, but Validate Scope has failed. Raise a change request and review the acceptance criteria with the customer.
IF THE QUESTION SAYS
The vendor performed extra work because you delayed an approval
THE BEST ANSWER IS
That is a constructive change. Assess the claim, document the facts, and negotiate before invoking the contract's ADR clause.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
490

## Slide 491
RECAP · TOPIC 5
Topic 5 Recap — Monitor and Control the Project
1
Data becomes decisions
Work performance data becomes information becomes reports becomes change requests — that chain is the whole domain.
2
EVM is one integrated system
PV, EV and AC generate every variance, index and forecast. Learn EV first; everything else follows.
3
Indices below 1.0 are bad
CPI and SPI below 1.0 mean over budget and behind schedule. Trends matter more than single readings.
4
Choose the right EAC
'Rate continues' uses BAC/CPI. 'Atypical' uses AC+BAC-EV. 'Must hit the date' uses the CPI x SPI form.
5
Every change is a request
Nothing changes a baseline without integrated change control — and rejected changes are still logged.
6
Corrective vs preventive
Corrective fixes a variance that happened. Preventive stops one that is only forecast.
7
Quality is planned in
Prevention beats inspection. The seven basic tools turn defect opinion into a defensible improvement case.
8
Control chart signals
A breach of the limits or seven consecutive points one side means assignable cause — investigate it.
9
Risk becomes issue
The moment a risk occurs, move it to the issue log and switch from response strategy to resolution action.
10
Scaling is organisational
LeSS descales structure; SAFe adds it. Both exist to manage dependencies, not to make teams more agile.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
491

## Slide 492
WHAT YOU WILL BUILD
Hands-on Labs — Topic 5
1
Lab 19. Kanban Board with WIP Limits and Lead/Cycle Time
Process T9 · LO5 · 20 min in class + 25 min self-study
Produces: Kanban board, Cycle time measurements
2
Lab 20. Earned Value Management and Schedule Compression
Process T9 · LO5 · 25 min in class + 35 min self-study
Produces: EVM calculation sheet, Forecast (EAC/ETC), Compression decision
3
Lab 21. Root Cause Analysis with 5 Whys, Fishbone and Pareto
BE T4 · LO3 · 25 min in class + 35 min self-study
Produces: 5 Whys chain, Fishbone diagram, Pareto chart
4
Lab 22. SPC Control Chart and Statistical Process Analysis
Process T7 · LO5 · 30 min in class + 30 min self-study
Produces: Control chart, Stability verdict, Capability summary
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
492

## Slide 493
HANDS-ON ACTIVITY
Lab 19. Kanban Board with WIP Limits and Lead/Cycle Time
Case study: Contoso Training Portal Upgrade. Process T9 · LO5. Produces Kanban board, Cycle time measurements.
20 min in class
1
Open the Kanban tool and create columns matching Contoso's real workflow, including any waiting states.
2
Populate the board with the current sprint's stories from Lab 10.
3
Set explicit WIP limits per column based on team size, then observe what the limits block.
4
Record the start and finish date of each item to measure lead time and cycle time.
5
Identify the bottleneck column — where work queues rather than flows — and propose a specific intervention.
6
Apply Little's Law to forecast delivery from your measured throughput rather than from optimism.
DELIVERABLE
Kanban board, Cycle time measurements
TOOL
Kanban Board
alfredang.github.io/kanban/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
493

## Slide 494
HANDS-ON ACTIVITY
Lab 20. Earned Value Management and Schedule Compression
Case study: Contoso Training Portal Upgrade. Process T9 · LO5. Produces EVM calculation sheet, Forecast (EAC/ETC), Compression decision.
25 min in class
1
Record the given Contoso data: BAC, and the PV, EV and AC at the reporting period.
2
Calculate the variances: CV = EV − AC and SV = EV − PV, stating whether each is favourable.
3
Calculate the indices: CPI = EV / AC and SPI = EV / PV, and interpret each against 1.0.
4
Forecast the outcome: EAC = BAC / CPI, then ETC = EAC − AC and VAC = BAC − EAC.
5
Calculate TCPI = (BAC − EV) / (BAC − AC) and state whether the required efficiency is realistically achievable.
6
Decide between crashing and fast tracking to recover, quantifying the added cost or the added risk of your choice.
DELIVERABLE
EVM calculation sheet, Forecast (EAC/ETC), Compression decision
TOOL
Statistics
alfredang.github.io/novastats/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
494

## Slide 495
HANDS-ON ACTIVITY
Lab 21. Root Cause Analysis with 5 Whys, Fishbone and Pareto
Case study: Contoso Training Portal Upgrade. BE T4 · LO3. Produces 5 Whys chain, Fishbone diagram, Pareto chart.
25 min in class
1
Review the Contoso defect data and write the problem statement as a measurable gap, not an opinion.
2
Open the 5 Whys tool and drill from the presenting symptom to a root cause you can actually act on.
3
Open the Fishbone tool and group candidate causes under people, process, technology, environment, materials and measurement.
4
Open the Pareto tool, enter the defect counts by category and identify the vital few driving roughly 80% of the defects.
5
Compare what each tool surfaced — the three disagree, and the disagreement is the most useful output.
6
Propose a countermeasure for the top two root causes, each with an owner, a date and a verification measure.
DELIVERABLE
5 Whys chain, Fishbone diagram, Pareto chart
TOOL
5 Whys + Fishbone Diagram
alfredang.github.io/5whys/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
495

## Slide 496
HANDS-ON ACTIVITY
Lab 22. SPC Control Chart and Statistical Process Analysis
Case study: Contoso Training Portal Upgrade. Process T7 · LO5. Produces Control chart, Stability verdict, Capability summary.
30 min in class
1
Enter the twenty process measurements into the SPC tool and plot them in time order.
2
Calculate the process mean and the upper and lower control limits.
3
Identify any point falling outside the control limits and investigate it as an assignable cause.
4
Apply the rule of seven: seven consecutive points on one side of the mean signals a non-random shift even inside the limits.
5
Use the Statistics tool to compute mean, standard deviation and the distribution shape.
6
State whether the process is in control, and separately whether it is acceptable — the two are different questions.
DELIVERABLE
Control chart, Stability verdict, Capability summary
TOOL
SPC / Control Chart + Statistics
alfredang.github.io/novaspc/
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
496

## Slide 497
06
TOPIC
Close the Project
Closure is a process, not an event. You obtain formal acceptance, transition the deliverable into operations, settle every contract and account, harvest the knowledge, and confirm the benefits the business case promised — then you turn to the exam itself.
1
Close Project or Phase and the closure criteria
2
Acceptance, transition and readiness for handover
3
Contracts, procurement and financial closure
4
Lessons learned, retrospectives and knowledge transfer
5
Benefits realisation and confirming delivered value
6
PMP exam structure, question types and study strategy
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
497

## Slide 498
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Why closure matters
A project that is not formally closed never stops consuming the organisation's money, attention and risk.
Acceptance ends ambiguity
Formal sign-off is the point at which 'nearly done' becomes contractually and legally done.
Transition protects benefits
Value is realised in operations, not in delivery — a poor handover destroys the business case.
Knowledge outlives the team
Lessons learned move into the repository so the next project starts from your experience.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
498

## Slide 499
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Three Threads of Closing
1
Project or phase closure
Complete every activity, obtain acceptance, settle contracts and accounts, release resources and archive.
2
Benefits realisation
Confirm the value the business case promised is being measured and delivered, and hand ownership of that measurement over.
3
Knowledge transfer
Move explicit and tacit knowledge from the team into the organisation before the team disbands.
4
Phase gate closure
Closing a phase uses the same process — acceptance, lessons learned, archive — before the next phase is authorised.
5
Administrative closure
Financial accounts closed, purchase orders settled, systems access revoked, facilities returned.
6
Celebration and recognition
Recognising the team's contribution is a genuine closure activity, not a nicety — it shapes future engagement.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
499

## Slide 500
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Close Project or Phase — ITTO
Purpose: finalise all activities for the project, phase or contract. This is the only process whose output is the formal, archived record that the project ever happened.
INPUTS
Project charter
Project management plan (all components)
Project documents: assumption log, basis of estimates, change log, issue log, lessons learned register, milestone list, project communications, quality control measurements, quality reports, requirements documentation, risk register, risk report
Accepted deliverables
Business documents: business case, benefits management plan
Agreements and procurement documentation
Organizational process assets
TOOLS & TECHNIQUES
Expert judgement in management control, audit, legal and procurement closure
Data analysis: document analysis, regression analysis, trend analysis, variance analysis
Meetings: closeout reporting, lessons learned sessions, retrospectives, celebration
OUTPUTS
Project documents updates (lessons learned register finalised)
Final product, service or result transition
Final report
Organizational process assets updates: project files, project or phase closure documents, historical information, lessons learned repository
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
500

## Slide 501
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Project Closure vs Phase Closure
Project closure
The whole endeavour ends
Performed once, when all phases are complete or the project is terminated
Releases all resources, closes all contracts and all financial accounts
Transitions the final product, service or result to operations or the customer
Produces the final report summarising performance against every baseline
Archives the complete project record into the organisational process assets
Phase closure
A gate between stages
Performed at the end of each phase in a predictive or hybrid life cycle
Confirms phase deliverables are accepted before the next phase is authorised
Resources may be released, retained or reassigned depending on the next phase
Produces a phase-end report and a go / no-go / hold recommendation
Captures lessons learned while they are fresh, not at the very end
Both use the same process. A phase gate is the cheapest place to kill a project that has lost its business case — which is precisely why governance defines phase-end criteria in advance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
501

## Slide 502
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Why Projects or Phases Close
1
Deliverables accepted
Stakeholders accept deliverables against acceptance criteria established in the project management plan.
2
Criteria may evolve
Acceptance criteria can legitimately be modified during the life cycle — through change control, never informally.
3
Traceability confirms completion
The requirements traceability matrix proves every requirement was completed and approved.
4
Iteration assessment
At the end of an iteration, team and stakeholders assess the product against their mutually agreed Definition of Done.
5
Phase gate reached
The phase's exit criteria are met and governance authorises moving to the next phase.
6
Termination
The business case has failed, funding is withdrawn, or the need has disappeared — closure still applies in full.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
502

## Slide 503
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Close Project or Phase — the Activity Sequence
STEP 1
Confirm completion
Verify all work in the scope baseline is complete and all deliverables verified.
STEP 2
Obtain acceptance
Secure formal, documented customer acceptance against the acceptance criteria.
STEP 3
Transition
Hand the product to operations or the customer with training and documentation.
STEP 4
Close contracts
Settle claims, finalise payments, close purchase orders and archive agreements.
STEP 5
Close financials
Notify enterprise functions, close accounts, and release remaining budget.
STEP 6
Archive and release
Archive all project information into OPAs and release the team and facilities.
Conclude external obligations including legal, regulatory and contractual matters — transfer of liability and closure of all accounts in the financial system are frequently forgotten and frequently examined.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
503

## Slide 504
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Acceptance of Deliverables
1
Acceptance criteria first
Criteria are agreed at the start, in the requirements documentation and the scope baseline.
2
Verified before accepted
Control Quality produces verified deliverables; Validate Scope converts them into accepted deliverables.
3
Formal and documented
Acceptance must be written and signed by an authorised stakeholder — verbal approval is not acceptance.
4
Traceability matrix
Use the requirements traceability matrix to prove every requirement reached completion and approval.
5
Partial acceptance
Where some deliverables fail, accept what passes and raise change requests for the remainder — do not stall everything.
6
Conditional acceptance
Acceptance with a punch list must carry named owners and dates, or the residual work is never done.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
504

## Slide 505
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Transition and Handover to Operations
1
Adoption drives benefits
Effective transitions enable end-user awareness, increasing adoption and therefore benefits realisation.
2
Training
Users and operators need training on the new product or service before, not after, they depend on it.
3
Documentation
Operating manuals, as-built documentation and troubleshooting guides transfer with the deliverable.
4
Communication
Sustained communication between the project team and the receiving organisation prevents the classic silent handover.
5
Post-implementation support
Agree the hypercare period, the support model and who pays for it, before the team disbands.
6
Warranty and defect window
Define the warranty period and the process for defects discovered after acceptance.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
505

## Slide 506
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Readiness for Transition
Delay the handover
The product works but operations cannot run it. Invest in training, runbooks and support staffing before transitioning.
Transition now
Product and operations are both ready. Execute the handover, start hypercare and begin measuring benefits.
Not ready — hold
Neither side is ready. Do not transition; a forced handover here converts a project problem into an operational crisis.
Fix defects first
Operations are prepared but the product fails acceptance. Complete defect repair and re-validate scope.
Operational readiness of the receiving organisation
Product readiness of the deliverable
ECO Process T10 asks you to validate readiness for transition — to operations or the next phase. Readiness is two-sided.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
506

## Slide 507
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Contents of the Final Report
1
Summary-level description
What the project was, what it delivered, and the period over which it ran.
2
Scope objectives
The scope objectives, the criteria used to evaluate them, and evidence that they were met.
3
Quality objectives
Quality objectives, the criteria applied, and the actual quality achieved against them.
4
Cost and schedule performance
The acceptable variance ranges, the actual variances, and the reason for each.
5
Benefits and business case
Whether the intended benefits were achieved, and if not, when they are expected to be.
6
Risks, issues and recommendations
Summary of how risks and issues were managed and what future projects should do differently.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
507

## Slide 508
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Finalising Contracts and Procurement Documentation
1
Contract schedule and scope
Collect, index and file the contractual schedule and the final agreed statement of work.
2
Quality and cost performance
File the supplier's quality records and the cost performance data against the agreement.
3
Change documentation
Every contract change, modification and supplemental agreement is archived with its authorisation.
4
Payment and financial records
Payment records, invoices and financial documents complete the commercial audit trail.
5
Inspection results
Inspection and acceptance test results evidence that the supplier met the agreed standard.
6
As-built documentation
'As-built' or 'as-developed' documents, manuals and troubleshooting and technical documentation.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
508

## Slide 509
ECO PROCESS T5 · PLAN AND MANAGE PROCUREMENT
Procurement Closure Sequence
STEP 1
Verify delivery
Confirm all contracted work and deliverables have been received and inspected.
STEP 2
Resolve claims
Settle any open claims or disputes through negotiation or the contract's ADR method.
STEP 3
Final payment
Release final payment and retention once the acceptance conditions are satisfied.
STEP 4
Formal notice
Issue written notice of contract completion as required by the agreement.
STEP 5
Archive
Index and file the complete procurement file for audit and future reference.
STEP 6
Evaluate the vendor
Record supplier performance so future sourcing decisions are evidence-based.
Early termination is a valid form of procurement closure. The termination clause defines the rights of both parties and the settlement of costs already incurred.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
509

## Slide 510
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Releasing Resources and Updating OPAs
1
Release people
Return team members to their functional units with a written performance summary and a genuine thank you.
2
Release physical resources
Return equipment, facilities and licences; unclaimed assets keep costing the organisation.
3
Close financial accounts
Close cost centres and purchase orders so no further charges can be booked to a finished project.
4
Revoke access
Remove system and data access — an open security question is a real compliance finding at audit.
5
Update OPA templates
Push improved templates, checklists and estimating data back into the organisational process assets.
6
Update historical databases
Actual durations and costs make the next project's analogous and parametric estimates better.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
510

## Slide 511
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Lessons Learned Register vs Repository
Lessons learned register
Live, project-level, updated continuously
A project document created early and updated throughout the whole life cycle
Captures the situation, the impact, and the recommendation as events happen
Owned by the project manager and visible to the whole project team
Feeds every phase gate review, retrospective and status conversation
Its final state is an input to the closure process and the final report
Lessons learned repository
Organisational, permanent, cross-project
An organisational process asset holding lessons from all completed projects
Updated at closure when the register's contents are transferred and indexed
Owned by the PMO, searchable by process, phase, risk category and domain
Consulted at the start of new projects to avoid repeating known mistakes
Its value depends entirely on discipline at closure — the register is not enough
Exam cue: 'during the project' or 'the team recorded' points to the register. 'For future projects' or 'the organisation' points to the repository.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
511

## Slide 512
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Finalising Lessons Learned for the Final Report
1
Scope changes
What changed, why it changed, and whether the change control process caught it early enough.
2
Schedule impacts
Which estimates proved wrong and what the estimating assumptions should have been.
3
Risks and issues
Which risks materialised, which responses worked, and which risks were never identified at all.
4
Stakeholder relationships
Which engagement strategies built trust and which stakeholders were persistently misjudged.
5
Vendor relationships
Supplier performance, contract type fit, and what to negotiate differently next time.
6
Artifacts and recommendations
Which artifacts earned their keep, and specific recommendations for comparable future projects.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
512

## Slide 513
ECO BUSINESS ENV T6 · CONTINUOUS IMPROVEMENT
Conducting the Project Retrospective
1
Internalise learning
The goal is that the team internalises learning about both the work product and the process used to build it.
2
Capture successes and challenges
Record what went well as deliberately as what went badly — repeatable success is a finding.
3
Qualitative data
How people felt — morale, safety, frustration — is real data and often explains the numbers.
4
Quantitative data
Measurements: velocity, defect escape rate, cycle time, variance against baseline.
5
Root cause to action plan
Use the data to find root causes, design countermeasures and build an action plan for next time.
6
Praise and motivate
Praise, congratulate and motivate the team — closure is the last chance to reinforce what you want repeated.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
513

## Slide 514
ECO PEOPLE T7 · HELP ENSURE KNOWLEDGE TRANSFER
Knowledge Transfer Before the Team Disbands
1
Identify critical knowledge
Decide what knowledge is genuinely critical to operating and evolving the deliverable.
2
Gather it deliberately
Interviews, documentation sprints and recorded walkthroughs capture what people carry in their heads.
3
Foster the environment
People share tacit knowledge when they trust the audience and have time set aside to do it.
4
Explicit to the repository
Codified knowledge goes into searchable, indexed assets with clear ownership after the project ends.
5
Tacit through people
Pairing, shadowing and communities of practice are the only reliable transfer mechanisms for judgement.
6
Name the successor
Every critical knowledge area needs a named operational owner before the last team member leaves.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
514

## Slide 515
ECO PROCESS T3 · HELP ENSURE VALUE-BASED DELIVERY
Benefits Realisation and Confirming Value
1
Benefits outlive the project
Most benefits are realised in operations, months after the project team has been released.
2
Benefits management plan
It names each benefit, its metric, its target, its timeframe and its accountable owner.
3
Verify the measurement system
ECO Process T3 requires you to verify a system is actually in place to track the benefits.
4
Hand over the measurement
Transfer benefit tracking to a business owner with the authority and budget to act on the readings.
5
Compare to the business case
Report actual against the promised business case — honestly, including where it fell short.
6
Value in adaptive delivery
Adaptive projects confirm value every increment, so closure confirms cumulative rather than deferred value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
515

## Slide 516
ECO PROCESS T10 · MANAGE PROJECT CLOSURE
Premature and Terminated Project Closure
1
Termination is legitimate
Stopping a project whose business case has failed protects the organisation — it is not a personal failure.
2
Common triggers
Funding withdrawn, strategy changed, technology superseded, regulator intervened, or the benefit disappeared.
3
Closure still applies fully
Every closure activity is performed: acceptance of partial work, contract settlement, archiving, release.
4
Document the reason
Record precisely why the project was terminated — this is among the most valuable lessons in the repository.
5
Salvage the value
Completed components, research and built assets may be reusable elsewhere; identify them before archiving.
6
Manage the team
Termination hits morale hardest. Communicate early, honestly, and support each member's next assignment.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
516

## Slide 517
EXAM FOCUS · CLOSING
Exam Traps — Closing
IF THE QUESTION SAYS
The customer has stopped responding and will not sign acceptance
THE BEST ANSWER IS
Follow the escalation path in the communications and governance plans; do not close the project without documented formal acceptance.
IF THE QUESTION SAYS
The project is cancelled halfway through by the sponsor
THE BEST ANSWER IS
Perform Close Project or Phase in full — acceptance of partial work, contract closure, lessons learned and archiving all still apply.
IF THE QUESTION SAYS
A team member asks to move to a new project before closure is complete
THE BEST ANSWER IS
Complete knowledge transfer and lessons learned capture before releasing them; resource release is a closure activity, not a favour.
IF THE QUESTION SAYS
The benefits will not be measurable for another twelve months
THE BEST ANSWER IS
Hand the benefits management plan and its measurement system to an accountable business owner; the project still closes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
517

## Slide 518
RECAP · CLOSING
Closing Recap
1
Accept before you close
Formal, documented acceptance against agreed criteria is the gateway to every other closure activity.
2
Verified then accepted
Control Quality verifies; Validate Scope accepts; Close Project archives. Learn that sequence.
3
Transition is two-sided
Readiness means the product works and operations can actually run it — check both.
4
Close every contract
Claims settled, payments made, procurement file archived, vendor performance recorded.
5
Register to repository
The lessons learned register becomes part of the organisational lessons learned repository at closure.
6
Benefits need an owner
Hand measurement to an accountable business owner — the project ends, the benefits do not.
7
Termination closes fully
A cancelled project runs the complete closure process, including documenting why it was stopped.
8
Update the OPAs
Templates, estimating data and historical records are the organisation's return on your experience.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
518

## Slide 519
PMP EXAM PREPARATION
PMP exam preparation
The exam does not test what you memorised. It tests what you would do next, in a situation described in four lines.
Situational by design
Most items describe a scenario and ask for the best next action, not a definition.
Approach-agnostic
Predictive, adaptive and hybrid appear throughout all three domains, not in separate sections.
Mindset over method
PMI rewards the servant leader who investigates, communicates and follows the process.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
519

## Slide 520
PMP EXAM PREPARATION
PMP Exam Structure — July 2026 Content Outline
Element | Specification | What it means for you
Total questions | 180 questions | Every item is presented; you cannot tell which ones count
Scored questions | 170 scored items | Your result is calculated from these alone
Pretest questions | 10 unscored pretest items | Trialled for future forms — never leave one blank
Time allowed | 240 minutes (4 hours) | About 80 seconds per question including reading time
Breaks | Two 10-minute breaks | Two 10-minute breaks — the first after the case-study section, the second midway through the independent questions.
Approach mix | About 40% predictive | About 40% predictive; the remaining 60% split between adaptive/agile and hybrid.
Tutorial and survey | Outside the 240 minutes | The tutorial and the closing survey do not consume exam time
Attempts | Up to three within the one-year eligibility period | After three attempts you must wait before reapplying
Once you review your responses and start a break, you cannot return to the questions in the section you have just completed.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
520

## Slide 521
PMP EXAM PREPARATION
Domain Weighting — Where the Questions Come From
Chart: 
| People 33% | Process 41% | Business Environment 26%
Percentage of items | 33 | 41 | 26
WHAT IT TELLS YOU
Process at 41% is the largest single domain — roughly 70 of the 170 scored items.
People at 33% means leadership and stakeholder items outnumber pure Business Environment items.
Business Environment at 26% covers governance, compliance, change, risk and improvement.
Weighting applies to items, not to study hours — weak areas deserve disproportionate time.
Every domain contains predictive, adaptive and hybrid scenarios; none is 'the agile domain'.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
521

## Slide 522
PMP EXAM PREPARATION
Study Effort vs Domain Weight — Plan Your Revision
Chart: 
| People | Process | Business Environment
Exam weight (%) | 33 | 41 | 26
Suggested revision hours | 24 | 32 | 20
WHAT IT TELLS YOU
Allocate revision roughly in proportion to domain weight, then adjust for your mock results.
Process carries the formulas and the process anatomy — it needs the most contact hours.
People is high weight and highly situational; practice questions beat re-reading notes.
Business Environment is compact but dense in compliance and governance vocabulary.
Re-plan after every mock exam: the domain you scored worst on gets the next block.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
522

## Slide 523
PMP EXAM PREPARATION
The Six Question Types
Type | How it works | Strategy
Multiple choice | One best answer from four options — the bulk of the exam. | Eliminate two options first, then choose between the remaining pair using the PMI mindset.
Multiple response | More than one correct answer; the item tells you how many. | Read the stem for how many answers are required and select exactly that number.
Matching | Drag items from one column to match a second column. | Do the pairs you are certain of first; the remaining items are constrained by elimination.
Enhanced matching | Matching that includes an image or diagram for context. | Study the image before reading the options — the diagram usually resolves the ambiguity.
Graphic-based (NEW) | Read a chart, graph, diagram or image, then answer from it. | Extract the specific data point the question asks for; do not interpret the whole chart.
Case study | A scenario with supporting visuals, then a series of linked questions. | Read the full scenario once, then answer each linked question referring back to the exhibit.
Graphic-based questions are NEW in the July 2026 outline — expect to read control charts, network diagrams, burndowns and EVM S-curves directly.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
523

## Slide 524
PMP EXAM PREPARATION
PMP Certification Eligibility
Educational background | Project management experience | Training
Upper-secondary / secondary school completion (EQF Level 4 / ISCED 3-4) | Minimum 60 months (5 years) of non-overlapping experience leading projects in the past 10 years | 35 hours of commercial project management training
Recognised associate-level, higher-certificate or advanced vocational programme (EQF Level 5 / ISCED 5) | Minimum 48 months (4 years) of non-overlapping experience leading projects in the past 10 years | 35 hours of commercial project management training
Bachelor's degree or higher, or a qualification mapped to EQF Level 6 / ISCED 6 | Minimum 36 months (3 years) of non-overlapping experience leading projects in the past 10 years | 35 hours of commercial project management training
Bachelor's or postgraduate degree from a PMI GAC-accredited programme | Minimum 24 months (2 years) of non-overlapping experience leading projects in the past 10 years | 35 hours of commercial project management training
Experience must be in leading and directing projects, accrued within the last 10 years. Applications may be audited — keep contact details for verifiers.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
524

## Slide 525
PMP EXAM PREPARATION
How to Read a Situational Question
STEP 1
Read the last line first
The actual question is at the end; knowing it changes how you read the stem.
STEP 2
Identify the process group
Are you planning, executing, monitoring or closing? It narrows the answers.
STEP 3
Find what already happened
Past-tense facts tell you which steps are done and cannot be the answer.
STEP 4
Spot the real problem
The scenario's noise is deliberate; name the single issue being asked about.
STEP 5
Eliminate two options
Remove anything reactive, blaming, escalating too early or bypassing process.
STEP 6
Choose the PMI answer
Prefer investigating, communicating and following the documented process.
'Best', 'first', 'next' and 'most likely' are not decoration. 'First' usually means gather information; 'next' means the step after what was described; 'best' means the most complete and process-compliant option.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
525

## Slide 526
PMP EXAM PREPARATION
Common Distractor Patterns
Distractor | Why it looks right | Why it is wrong
Escalate to the sponsor immediately | Escalation is a real governance tool and sounds decisive | PMI expects you to gather facts and act within your authority first
Ask the team to work overtime | It appears to solve a schedule problem directly | It ignores root cause, damages the team, and skips impact analysis
Update the plan / baseline directly | The plan clearly needs to change | Baselines change only through approved change requests
Do nothing and continue monitoring | Sometimes genuinely correct in risk acceptance scenarios | Usually a trap when the scenario describes an active impact
Remove the team member | It removes the visible symptom quickly | Conflict and performance are addressed through coaching first
Add the change because the customer asked | Customer satisfaction sounds like the PMI value | Every scope change requires impact analysis and change control
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
526

## Slide 527
FORMULA SHEET · EVM
Formula Sheet Recap — Earned Value
Cost Variance
CV = EV - AC
Negative means over budget. Every variance is EV minus something.
Schedule Variance
SV = EV - PV
Negative means behind schedule. Always zero at project completion.
Cost Performance Index
CPI = EV / AC
Below 1.0 means you earn less than a dollar of value per dollar spent.
Schedule Performance Index
SPI = EV / PV
Below 1.0 means work is arriving slower than the plan assumed.
Estimate at Completion
EAC = BAC / CPI
The default forecast when current cost performance is expected to continue.
Also carry: ETC = EAC - AC, VAC = BAC - EAC, and TCPI = (BAC - EV) / (BAC - AC).
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
527

## Slide 528
FORMULA SHEET · ESTIMATING & RISK
Formula Sheet Recap — Estimating, Float and Risk
PERT triangular
(O + M + P) / 3
Simple average of optimistic, most likely and pessimistic estimates.
PERT beta
(O + 4M + P) / 6
Weighted average giving the most likely estimate four times the weight.
PERT standard deviation
(P - O) / 6
The spread of the estimate; a proxy for how uncertain the activity is.
Total float
LS - ES or LF - EF
Delay available without delaying project completion. Zero float = critical path.
Expected Monetary Value
EMV = Probability x Impact
Sum the EMV of every branch to value a decision tree; threats are negative.
Communication channels
n(n-1) / 2
Channels grow quadratically with people — the case for smaller teams.
Point of confusion to settle now: total float belongs to a path; free float is the delay available without delaying the very next activity.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
528

## Slide 529
PMP EXAM PREPARATION
Exam Day Strategy
1
Pace deliberately
180 questions in 240 minutes is about 80 seconds each. Check your position at every 45-question mark.
2
Answer everything
There is no penalty for a wrong answer, and 10 items do not count anyway — never leave a blank.
3
Mark and move on
If an item takes more than two minutes, choose your best option, flag it and move on.
4
Use the breaks
Take both 10-minute breaks even if you feel fine — fatigue damages accuracy far more than it damages speed.
5
Case study section first
The case-study section comes before the first break; read the exhibit carefully once rather than repeatedly.
6
Trust your first instinct
Change an answer only when you find a specific fact in the stem that you missed the first time.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
529

## Slide 530
PMP EXAM PREPARATION
The PMI Mindset — the Tiebreaker on Every Item
1
Be proactive
Prevent problems rather than react to them; the answer that anticipates usually beats the answer that responds.
2
Gather facts first
Understand the situation before acting, escalating or blaming — 'analyse the impact' is rarely wrong.
3
Serve the team
Remove impediments, empower and coach; do not command, punish or reassign as a first response.
4
Follow the process
Use the documented change, risk, quality and escalation processes — never bypass governance for speed.
5
Communicate directly
Talk to the person concerned before involving their manager or the sponsor.
6
Deliver value
When options conflict, choose the one that protects the business value and the customer's real need.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
530

## Slide 531
PMP EXAM PREPARATION
Your Study Plan After This Course
1
Week 1
Consolidate notes; review every ITTO and the formula sheet from memory.
2
Week 2
Complete the PMI Study Hall or equivalent domain quizzes; log weak areas.
3
Week 3
First full 180-question timed mock; analyse every wrong answer's reason.
4
Week 4
Targeted revision on the two weakest domains plus formula drills.
5
Week 5
Second full timed mock; target above 70% in all three domains.
6
Week 6
Light review, sleep, and sit the exam — do not cram the final 48 hours.
Submit your PMI application early — it can take up to five business days to review, and audited applications take longer. Your one-year eligibility period starts when the application is approved.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
531

## Slide 532
PMP EXAM PREPARATION
The 35 PDUs and Maintaining Your Certification
1
This course = 35 contact hours
It satisfies PMI's requirement for 35 hours of commercial project management training.
2
Keep your evidence
Retain the certificate of completion and the course outline in case your application is audited.
3
CCR cycle
Once certified you must earn 60 PDUs every three years to maintain the PMP credential.
4
Education PDUs
Minimum 35 of the 60 must be education PDUs across the PMI Talent Triangle.
5
Talent Triangle
Ways of Working, Power Skills, and Business Acumen — at least 8 PDUs in each per cycle.
6
Giving back PDUs
Up to 25 PDUs may come from volunteering, creating content or working as a practitioner.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
532

## Slide 533
EXAM FOCUS · WHOLE COURSE
Final Exam Traps — Whole-Course Review
IF THE QUESTION SAYS
A risk you identified has now occurred and is delaying the team
THE BEST ANSWER IS
It is now an issue. Move it to the issue log, implement the planned response, and reassess the remaining risk exposure.
IF THE QUESTION SAYS
CPI is 0.85 and the sponsor asks whether you will finish within budget
THE BEST ANSWER IS
Calculate EAC. At BAC/CPI the forecast exceeds BAC, so report the forecast overrun and present recovery options.
IF THE QUESTION SAYS
A stakeholder was never identified and now objects to a delivered feature
THE BEST ANSWER IS
Update the stakeholder register, analyse their influence and interest, and revise the engagement plan before negotiating scope.
IF THE QUESTION SAYS
The team wants to add a nice extra feature at no cost to the customer
THE BEST ANSWER IS
That is gold plating. Deliver to the acceptance criteria; route any genuine addition through integrated change control.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
533

## Slide 534
RECAP · TOPIC 6
Topic 6 Recap — Close the Project and Exam Readiness
1
Closure is a process
Acceptance, transition, contract and financial closure, archiving and release — performed in full, every time.
2
Formal acceptance is required
Written sign-off against agreed acceptance criteria is what makes a project complete.
3
Transition drives benefits
Training, documentation and support determine adoption, and adoption determines value.
4
Register becomes repository
Lessons learned move from a project document into an organisational process asset at closure.
5
Retrospectives use both data types
Qualitative feelings and quantitative measures together produce real root causes.
6
Benefits need an accountable owner
Hand over the measurement system; most benefits arrive after the team has gone.
7
Exam: 180 in 240 minutes
170 scored plus 10 pretest items, with two 10-minute breaks and roughly 80 seconds per question.
8
Exam: 33 / 41 / 26
People, Process and Business Environment weighting — with about 40% predictive and 60% adaptive or hybrid.
9
Six question types
Including the new graphic-based items and the case-study section that precedes the first break.
10
Answer with the PMI mindset
Investigate first, follow the process, serve the team, and protect the business value.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
534

## Slide 535
WHAT YOU WILL BUILD
Hands-on Labs — Topic 6
1
Lab 23. Project Closure, Benefits Realisation and Lessons Learned
Process T10, BE T6 · LO5 · 60 min in class
Produces: Closure checklist, Final report, Lessons learned register
2
Lab 24. Capstone: Consolidated Project Plan and Mock Exam
All domains · LO1-LO5 · 105 min in class + 15 min self-study
Produces: Consolidated project management plan, Mock exam score analysis by domain
3
Everything you have built
These final labs consolidate the artifacts from Labs 01-22 into one integrated plan and an exam-readiness score.
Consolidates: Closure checklist, Consolidated project management plan, Final report, Lessons learned register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
535

## Slide 536
HANDS-ON ACTIVITY
Lab 23. Project Closure, Benefits Realisation and Lessons Learned
Case study: Contoso Training Portal Upgrade. Process T10, BE T6 · LO5. Produces Closure checklist, Final report, Lessons learned register.
60 min in class
1
Verify every deliverable against the acceptance criteria agreed in the charter and scope statement.
2
Obtain and record formal stakeholder sign-off — informal agreement is not closure.
3
Confirm transition readiness: documentation, training and support arrangements for the receiving team.
4
Close all procurements, settle final payments and archive the contracts and financial records.
5
Run the retrospective and write the lessons learned into the organisational repository, not just the project folder.
6
Confirm the benefits measurement system is live and the benefits owner accepts accountability past project end.
DELIVERABLE
Closure checklist, Final report, Lessons learned register
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
536

## Slide 537
HANDS-ON ACTIVITY
Lab 24. Capstone: Consolidated Project Plan and Mock Exam
Case study: Contoso Training Portal Upgrade. All domains · LO1-LO5. Produces Consolidated project management plan, Mock exam score analysis by domain.
105 min in class
1
Consolidate every artifact from Labs 01-23 into one integrated project management plan with a contents page.
2
Verify internal consistency: the WBS, schedule, budget, RACI and risk register must all describe the same project.
3
Present the plan to the class as though to a steering committee, in ten minutes, defending your key trade-offs.
4
Sit the full 180-question mock exam under timed conditions — 240 minutes, closed book, two breaks.
5
Score the mock by ECO domain and compare against the 33/41/26 weighting to expose your weakest area.
6
Rewrite your Lab 01 study plan using the mock results, naming the specific topics to revisit before booking the exam.
DELIVERABLE
Consolidated project management plan, Mock exam score analysis by domain
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
537

## Slide 538
EXAM SIMULATION
Practice Exam
exams.tertiaryinfotech.com
PMP Practice Examination
180 questions · 240 minutes · ECO 2026 weighting
People
33%
Process
41%
Business Environment
26%
Sit it under exam conditions
Four hours, no notes, no phone — the timing pressure is what you are actually practising.
Review by domain, not by score
Your weakest domain tells you where the remaining study time should go.
Practise the new question types
Graphic-based and case-study items behave differently from plain multiple choice.
Repeat until consistent
Aim for three full mocks at a stable pass standard before you book the real exam.
Access the practice exams at exams.tertiaryinfotech.com using the credentials issued on Day 1. Your attempts and domain-level scores are saved to your learner record.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
538

## Slide 539
AFTER THE COURSE
Your Next 90 Days
1
Submit the PMI application
Use this course for the 35 contact hours; document your project experience against the eligibility rules.
2
Build a study schedule
Plan 8–10 weeks of study, weighting your time by the domain percentages: Process 41%, People 33%, Business Environment 26%.
3
Practise by question type
Drill the new graphic-based and case-study formats, not just multiple choice.
4
Re-run the labs at work
Apply the charter, WBS, EVM and control-chart labs to a live project to consolidate the learning.
5
Take full mock exams
Sit at least three timed 180-question mocks under exam conditions before booking.
6
Maintain your certification
The CCR programme requires 60 PDUs every three years once you are certified.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
539

## Slide 540
CONTINUE YOUR PATHWAY
Recommended Courses
1
WSQ — Fundamentals of Microsoft Project
Build and control real schedules, baselines and resource plans in MS Project.
2
WSQ — Effective Project Management for Small Projects
A lighter-weight toolkit for projects that do not warrant full PMP rigour.
3
WSQ — Certified Lean Six Sigma Green Belt
Go deeper on DMAIC, SPC and the statistical quality tools introduced here.
4
WSQ — Agile Project Management with Scrum
Extend the adaptive content into full Scrum practice and certification.
5
WSQ — Business Analysis Fundamentals
Strengthen requirements elicitation, traceability and stakeholder analysis.
6
WSQ — Data Analytics for Managers
Turn project and operational data into the metrics your governance board wants.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
540

## Slide 541
WE ARE HERE TO HELP
Support
1
Email
enquiry@tertiaryinfotech.com — for course, certificate and funding queries.
2
Telephone
6100 0613 — office hours, Monday to Friday.
3
LMS / TMS
lms-tms.tertiaryinfotech.com — slides, learner guide, labs and your completion record.
4
Problem-solving tools
The live 5 Whys, Fishbone, Pareto, SPC and Statistics tools stay available to you after the course.
5
Certificate
Issued after attendance, assessment and TRAQOM survey requirements are met.
6
Course materials
Retain your copy — it is your reference for the PMI application and for the exam itself.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
541

## Slide 542
DAY 4
Final Assessment
Two instruments. One outcome: Competent.
Written Assessment — 1 hour
Five short-answer questions (K1–K5) across the ECO domains, processes and formulas. 3:30pm–4:30pm.
Case Study — 2 hours
One applied project scenario with five linked questions (A1–A8). 4:30pm–6:30pm.
Result
Competent or Not Yet Competent against all five learning outcomes.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
542

## Slide 543
WHAT HAPPENS ON DAY 4
Assessment Flow
STEP 1
Briefing
The assessor explains the rules, timing and materials before any paper is distributed.
STEP 2
Written Assessment
Short-answer questions covering the ECO domains, processes, formulas and terminology.
STEP 3
Case Study
A project scenario with linked questions requiring applied judgement rather than recall.
STEP 4
Submission
All question papers, answer scripts and rough working are handed back to the assessor.
STEP 5
Marking & Outcome
Scripts are marked against the LO criteria and you are graded Competent or Not Yet Competent.
STEP 6
Feedback / Re-assessment
Results are released with feedback; one re-assessment is offered where required.
Digital attendance must be taken for the assessment session itself — it is a separate record from the AM and PM class scans.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
543

## Slide 544
BEFORE YOU LEAVE
Digital Attendance & TRAQOM Survey
1
Scan AM and PM, every day
Digital attendance is taken twice daily. Both scans are required for each of the four days.
2
Assessment attendance is separate
Take attendance again for the assessment session on Day 4 — it is a distinct record.
3
75% minimum for funding
SSG funding is conditional on the attendance rate recorded in the digital attendance system.
4
Scan with your own identity
Proxy attendance voids funding for both the absent learner and the person who scanned.
5
TRAQOM quality survey
Mandatory at course end. Your certificate is released only after the survey is submitted.
6
Where to go
Both the attendance QR code and the TRAQOM link are issued by the trainer at lms-tms.tertiaryinfotech.com.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
544

## Slide 545
END OF COURSE
Thank You
Now go and pass the exam.
35 PDUs earned
You have the contact hours PMI requires for the application.
24 labs completed
You leave with a full set of working project artifacts.
ECO 2026 covered
Every domain and task on the July 2026 outline has been taught.
Project Management Professional (PMP) 35 PDU Training | TGS-2024045797
© 2026 Tertiary Infotech Academy Pte Ltd
545