## Make or Buy Analysis
Make or Buy Analysis
|  | The Most Cost-Effective Option is: | Make
| Initial Costs | Ongoing Costs |  |  |  |  | TOTAL
Cost to Make | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
e.g. Project costs | 1500 | [5 empty] | 1500
e.g. People costs | 200 | 100 |  |  |  |  | 300
e.g. System costs |  | 50 |  |  |  |  | 50
e.g. Ongoing Costs |  |  | 100 |  |  |  | 100
e.g. Maintenance |  | 50 | 50 | 50 | 100 | 200 | 450
0
0
TOTAL | 1700 | 200 | 150 | 50 | 100 | 200 | 2400
Cumulative Chart | 1700 | 1900 | 2050 | 2100 | 2200 | 2400
Cost to Buy | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
e.g. Initial contract | 1000 | [5 empty] | 1000
e.g. System cost | 200 | [5 empty] | 200
e.g. Other Costs | 200 | [5 empty] | 200
e.g. Ongoing fees |  | 100 | 300 | 400 |  |  | 800 | ◀ Insert more rows to add more costs. Copy the formulas and formatting from an existing row from above.
e.g. Ongoing maintenance |  | 100 | 100 | 100 | 100 | 100 | 500 | ◀ Insert more columns to add more years (or weeks or months). Copy over an existing column to ensure the formulas carry over.
0
0
TOTAL | 1400 | 200 | 400 | 500 | 100 | 100 | 2700
Cumulative Chart | 1400 | 1600 | 2000 | 2500 | 2600 | 2700

## Make Buy or Other Analysis
Make or Buy Analysis
|  | The Most Cost-Effective Option is: | Make
| Initial Costs | Ongoing Costs |  |  |  |  | TOTAL
Cost to Make | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
e.g. Project costs | 1500 | [5 empty] | 1500
e.g. People costs | 200 | 100 |  |  |  |  | 300
e.g. System costs |  | 50 |  |  |  |  | 50
e.g. Ongoing Costs |  |  | 100 |  |  |  | 100
e.g. Maintenance |  | 50 | 50 | 50 | 100 | 200 | 450
0
0
TOTAL | 1700 | 200 | 150 | 50 | 100 | 200 | 2400
Cumulative Chart | 1700 | 1900 | 2050 | 2100 | 2200 | 2400
Cost to Buy | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
e.g. Initial contract | 1000 | [5 empty] | 1000
e.g. System cost | 200 | [5 empty] | 200
e.g. Other Costs | 200 | [5 empty] | 200
e.g. Ongoing fees |  | 100 | 300 | 400 |  |  | 800 | ◀ Insert more rows to add more costs. Copy the formulas and formatting from an existing row from above.
e.g. Ongoing maintenance |  | 100 | 100 | 100 | 100 | 100 | 500 | ◀ Insert more columns to add more years (or weeks or months). Copy over an existing column to ensure the formulas carry over.
0
0
TOTAL | 1400 | 200 | 400 | 500 | 100 | 100 | 2700
Cumulative Chart | 1400 | 1600 | 2000 | 2500 | 2600 | 2700
Cost of Other | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
e.g. Project costs | 700 | [5 empty] | 700
e.g. People costs | 200 | [5 empty] | 200
e.g. System costs | 200 | [5 empty] | 200
e.g. Ongoing Costs |  | 200 | 400 | 500 | 100 |  | 1200
|  | 100 | 100 | 100 | 200 | 200 | 700
0
0
TOTAL | 1100 | 300 | 500 | 600 | 300 | 200 | 3000
Cumulative Chart | 1100 | 1400 | 1900 | 2500 | 2800 | 3000

## ©
Make or Buy Analysis Template
© 2024 David McLachlan
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
You may make archival copies and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
Do not delete this worksheet.
Limitation of Liability
This template and any related documentation are provided to you "as is." While every effort has been made to provide an outstanding product, without limiting the above you accept that this template may not meet your requirements, operate error free, or identify any or all errors or problems. This agreement does not affect any statutory rights you may have as a consumer.